## FCO
Project name	JAKARTA: New Embassy	TEL AVIV: Embassy Upgrade	UKERP	Echo	Prism and Firecrest Re-procurement Programme	ABUJA: New Office and Residence
Department	FCO	FCO	FCO	FCO	FCO	FCO
MPA RAG rating / (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the MPA Annual Report)	Amber/Green	Green	Amber	Amber/Green	Amber	Amber
Description / aims	This project is for the construction of a new Embassy on a greenfield site in Jakarta. Following a review, the current facility has been identified as being inappropriate for our needs and a new site was acquired in 2009.	This project is to upgrade the structure of the Embassy offices in Tel Aviv to give an increase in the protection against seismic activity and to reconfigure the offices internally to achieve a more efficient and open plan layout. To renew the mechanical and electrical systems with energy efficient characteristics including a new centralised air handling system with a heat recovery system. To relocate the currently outhoused Consular / Visa section within the Embassy.	The FCO intends to maximise the efficiency of its London estate by consolidating its core activities into the Main Building on King Charles Street (KCS). This will support the wider Cabinet Office strategy of consolidating the HMG Estate in Central London. It will free up the Old Admiralty Building (OAB) freehold for other Government Department use. There are significant savings for the FCO on operating costs and for the wider Government on lease rentals. This UK Estates Reform (UKER) project is a catalyst to provide a more modern working environment for FCO staff, to help deliver Diplomatic Excellence, to embed flexible working, and to drive efficiency across the FCO.	Echo is a new global network for voice and data services currently delivered through the FCO Telecommunications Network (FTN) to FCO Overseas Posts. It will also replace the Managed Telephony Service (MTS) delivered to FCO sites across the UK. The Echo Programme will make a substantial contribution to delivering the FCO’s ICT Strategy and, in turn, support Diplomatic Excellence which is the FCO’s reform and modernisation programme.	To renew the contracts for the following business critical ICT services: / • Prism : FCO's Oracle based enterprise resource and financial planning (ERP) contract with Cap-Gemini. / • Firecrest: FCO's Microsoft based desktop infrastructure and management contract with Hewlett Packard. / and procure a new ICT Management service / • SMI : FCO's new Service Management Integration contract	To provide fit for purpose and secure offices for the British High Commission in Abuja, Nigeria. The existing Chancery and unclassified offices are located in split locations, both of which are rented and were opened in 1991 as a 'temporary' solution. Abuja has firmly become established as the administrative capital of Nigeria and it has been the FCO's intention for some time to have offices that are fit for purpose for the next thirty years, that comply with current FCO security standards and provide an effective platform for a wide cross-section of UK government departments.
Departmental narrative, actions on Delivery Confidence Assessment
Project - start date	01/04/2004	28/10/2009	01/06/2011	09/06/2009	01/01/2011	01/12/2010
Project - end date	01/09/2014	01/11/2013	01/08/2016	31/12/2012	30/11/2013	01/12/2017
Departmental narrative on schedule, including any deviation from planned schedule	The start was delayed for 5 months after FBC approval; work started on site in June 2011.	Occupation of the Embassy from the decant accommodation delayed by 3 months to ensure the testing and commissioning was to the correct standards.	On schedule	The programme rollout to overseas Posts was delayed, largely as a result of Olympics activities taking higher priority and an end date of 31/3/2013 is currently forecast.	On schedule	On schedule
2012/13 Budget (£million)	11.06	3.82	1.44	29.96		0.95
2012/13 Forecast (£million)	11.06	2.62	1.44	32.07		0.95
Total budgeted whole life costs (£million) / (including non-government costs)	29	22	79	179		39
Departmental narrative on budget/forecast variance for 2012/13 / (if variance is more than 5%)		Predicted variance reflects potential saving derived from GMP agreement with contractor. Final account remains under discussion.		The programme rollout to overseas Posts was delayed, largely as a result of Olympics activities taking higher priority. Operation of the existing Foreign Office Telecoms Network (FTN) therefore had to be extended and the increase in the 12/13 budget reflects the additional costs.
Departmental narrative on budgeted whole life costs