## gmpp-data-HMT-q2-2012-13_ELPS
Project name	Project OSCAR	Equitable Life Payment Scheme
Department	HMT	HMT
MPA RAG rating / (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the MPA Annual Report)	Amber	Amber/Red
Description / aims	OSCAR replaces the COINS financial reporting system which supports fiscal management and spending control within HMT, produces Parliamentary Estimates and Public Expenditure Statistics.	The Scheme was established to makes payments to eligible Equitable Life policyholders for their Relative Loss as a consequence of regulatory failure.
Departmental narrative, actions on Delivery Confidence Assessment	Confidence in project delivery is generally high. Amber status reflects a necessary deviation from the original delivery schedule. Although identified costs are on an upward trajectory, the project is still expected to deliver within its total budget and in line with the timeframes required by the business.	The Scheme aims to distribute up to £1billion in the first 3 years, but anticipates undershooting this target as a result of not successfully tracing all policyholders. To mitigate against this the Scheme is implementing a publicity campaign to encourage people to come forward.
Project - start date	24/08/2011	01/05/2010
Project - end date	07/02/2013	01/04/2014
Departmental narrative on schedule, including any deviation from planned schedule	Delays to the very complicated WGA elements of the project mean that we are now working towards signing off the final delivery milestone at the end of May 2013	On schedule
2012/13 Budget (£million)	4.71	19,853,558
2012/13 Forecast (£million)	4.668	£20,494,997 (as of 14th January 2013)
Total budgeted whole life costs (£million) / (including non-government costs)	19.56	59,173,700
Departmental narrative on budget/forecast variance for 2012/13 / (if variance is more than 5%)	Spend in 2012/2013 has been higher than forecasted, due to the WGA dealys. This overspend is likely to be offset by an underspend in 2011/2012	Within tolerance.
Departmental narrative on budgeted whole life costs	Total whole life costs currently exceed that originally forecast. Whole life costs include a generous allowance for future upgrades during the life of the project and will only be used if essential. As a result, it is quite possible that the overspend may be reduced before the end of the life of the solution.	The Scheme is broadly on budget with less than 3% overspend against the original, total outturn of £58m. HMT is working to identify potential opportunities for reducing the remaining operational costs, and has already identified c£500k cost reductions.