## Test_Schedule
DBS SYSTEM TEST SCHEDULE BETWEEN DBS AND					RB NAME
-----------------------------------------------------------------------------------------------------------------------------------------------------------
				Evidence Outstanding
Scheduled commencement date:			21/09/2009			<---Change to match date in RB Test Schedule				Key:	Not Started
				In Progress
				Defect
				Complete
				Configuration change
Test Case Number	Application limit	Number of Applications	Script Ref's	Test Case Features					Test Schedule duration (10 working days)					Contingency ?????
				RbNumber	Csignumber	Name	Application Ref numbers	Special notes	Monday, 21/09/2009	Tuesday, 22/09/2009	Wednesday, 23/09/2009	Thursday, 24/09/2009	Friday, 25/09/2009	Saturday, 26/09/2009	Sunday, 27/09/2009	Monday, 28/09/2009	#REF!	Tuesday, 29/09/2009	Wednesday, 30/09/2009	Thursday, 01/10/2009	Friday, 02/10/2009	Saturday, 03/10/2009	Sunday, 04/10/2009	Monday, 05/10/2009	Tuesday, 06/10/2009	Wednesday, 07/10/2009
1	50	1	RB1 (CRB01), CAP1(CRB03), CAP1(CRB04)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	MRS A'BCD THISISTEST CASEONEFORENAME MIDDLENAMEOFTESTCASEONE ABCDEFTHISISTESTCASEONESURNAME			RB NAME produce CRB01 file and send to DBS	DBS Process CRB01 and return CRB03 and CRB04 back to RB NAME	RB NAME process CRB03 and CRB04		RB NAME receive a disputed application from DBS				ENSURE KEY CHANGE IS MADE AT BOTH DBS AND RB
3	ANY	NA	RB3(CRB01)	n/a (no xml produced)	n/a (no xml produced)	N/A AD only no xml	n/a					RB NAME ONLY
4	50	1	RB4(CRB01) CAP4(CRB04)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	DUCHESS QUENTIN-HOGG MIDDLENAME-THISISTHEFIRSTMIDDLENAMEFORTESTCASEX A '-ANDERSON		Non BLANK			RB NAME produce CRB01 file and send to DBS	DBS Process CRB01 and return CRB03 and CRB04 back to RB NAME	process CRB03 and CRB04
5*	50	1	CAP5(CRB02)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	Not specified just valid CRB01					RB NAME produce CRB01 file and send to DBS	DBS add message id and filename of CRB01 received to the Pre-prepared CRB02 (CONTAINING ALL 11 ERROR MESSAGES) and return to RB NAME	process CRB02
6	50	4	CAP6a(CRB03) CAP6b(CRB03) CAP6c(CRB03) CAP6d(CRB03)	Valid Rbnumber A N OTHER- RbNumberB1 / and VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2, / AN other VALID -STANDARD -CSigNumberB2, / CANCELLED CSIGNUMBER- SCRIPT 6C-CsigNumberA5, / CSIGNUMBER NOT YET REGISTERED SCRIPT 6B- CsigNumberA4,	MISS CASESIXA TESTSIX MISS CASESIXB TESTSIX MISS CASESIXC TESTSIX MISS CASESIXC TESTSIX					RB NAME produce CRB01 file and send to DBS	DBS Process CRB01 and return CRB03 back to
7	50	1	RB7 (CRB01)			MRS A'BCD THISISTEST CASEONEFORENAMEABCDEFGHIJKLMNOPQRSTUVWXYZAB ABCDEFTHISISTESTCASEONEMIDDLENAMEABCDEFGHIJKLMNOPQRSTUVWXYZA ABCDEFTHISISTESTCASEONESURNAMEABCDEFGHIJKLMNOPQRSTUVWXYZABCD					produce CRB01 file and send to DBS			RB NAME process CRB03
9*	50	50	RB9(CRB01) CAP9(CRB03) CAP9(CRB04)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	MR APPLICANT ONE - FIFTY (50 APP'S)		Non BLANK					produce CRB01 file containing 50 applications and send to DBS (ENSURE THAT THIS FILE ONLY CONTAINS 50 APPLICATIONS SEPARATE TO OTHER CASES RUN THIS DAY)			RB NAME process CRB03 and CRB04
10	50	1	RB10(CRB01)	n/a (no xml produced)	n/a (no xml produced)	MR APPLICANT MULTIPLE					RB NAME ONLY
11	50	4	RB11(CRB01) CAP11(CRB03) CAP11(CRB04)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2, / VALID -STANDARD MANDATORY -CsigNumberA3	DR CASE ELEVEN-ONE DR CASE ELEVEN-TWO DR CASE ELEVEN-THREE MR CASE ELEVEN-FOUR					RB NAME produce CRB01 file and send to DBS	DBS Process CRB01 and return CRB03 and CRB04 back to
12	50	1	CAP12(CRB04) CAP12(CRB03)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	DR REJECT INTEGRITY VALIDATIONTESTCASETWELVE		Integrity keys fail on CRB03 and CRB04				RB NAME produce CRB01 file and send to DBS	DBS Process CRB01 and return corrupted CRB03 and CRB04 back to
20*	RB=1, CRB04=50	2	RB20(CRB01) CAP20(CRB03) CAP20(CRB04)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2, / VALID -STANDARD MANDATORY -CsigNumberA3	MRS NEW TESTCASETWENTY KEY MRS NEW TESTCASETWENTY KEY		Before RB NAME and DBS update secret keys DBS must ensure all original key CRB01 have been processed.					RB NAME produce 2xCRB01 files and send to DBS (NEW KEY)	DBS Process CRB01 and return CRB03 and CRB04 (with less than the maximum level of applications i.e. 2 on 1 file) back to RB NAME	process CRB03 and CRB04	#REF!
21*	RB=1, CRB04=50	2	CAP21(CRB02)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	MR REJECT FILE ONECASETWENTYONE MR REJECT FILE TWOCASETWENTYONE					RB NAME produce 2xCRB01 files and send to DBS	DBS Process CRB01 and ENSURE return 2 CRB02 files back to			RB NAME only RESEND ONE CRB01 file AFTER CORRECTION
23*	50	0	CAP23(CRB02)	OTHER-RBnumber C1	OTHER CsigNumberC2	N/A CRB02 FOR DIFF RB		The CRB02 sent toRB NAME is one intended for another RB (including another RB's RBnumber)					DBS send pre-prepared CRB02 intended for another RB to RB NAME
24*	50	1	RB24(CRB01) CAP24(CRB02)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	MR CASETWENTYFOUR INTEGRITY KEY		Before RB NAME and DBS update secret keys DBS must ensure all original key CRB01 have been processed.					RB NAME produce CRB01 file (with one application) and send to DBS after key changes (NEW KEY)	DBS Process CRB01 and return CRB02 back to / RB NAME process CRB02
25*	RB=1, CRB04=50	1	RB25(CRB01) CAP25(CRB02)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	MR IVORCASETWENTYFIVE MISMATCH		RB NAME to set Secret Key to original key before CRB02 processed in final step					RB NAME produce one CRB01 file and send to DBS-(original secret key)			DBS Process CRB01 and CREATE CRB02 'message integrity failure, as processed with new key'	Do not send CRB02 file to until confirmed all remaining Scenarios completed including 13 and 19 and have now configured back to original secret key used prior to change in Scenarios 20+ 24	#REF!
26*	50	1	CAP26(CRB02)	VALID -STANDARD -RBNumber A1	VALID -STANDARD FULL(ADDRESS)-CSigNumberA2	DR REJECT INTEGRITY VALIDATIONCASETWENTYSIX		Ensure CRB01 file manually amended before processed by DBS				RB NAME produce CRB01 file and send to DBS	File is corrupted -DBS Process CRB01 and return CRB02 back to
16

## Runs
Run 1					Run 2	Date 19/11/2008					Run 3
TEST CASES	Name	Scripts	Date Run	Comments	Clean Run (Y/N) Date Complete	Incidents Raised	TEST CASES	Date Run	Name	Comments	Clean Run (Y/N) Date Complete	Incidents Raised	TEST CASES	Date Run	Incidents Raised	Comments	Clean Run (Y/N) Date Complete
1	MRS A'BCD THISISTEST CASEONEFORENAME MIDDLENAMEOFTESTCASEONE ABCDEFTHISISTESTCASEONESURNAME	RB1 (CRB01), CAP1(CRB03), CAP1(CRB04)
3	N/A AD only no xml	RB3(CRB01)
4	DUCHESS QUENTIN-HOGG MIDDLENAME-THISISTHEFIRSTMIDDLENAMEFORTESTCASEX A '-ANDERSON	RB4(CRB01) CAP4(CRB04)
5	Not specified just valid CRB01	CAP5(CRB02)
6	MISS CASESIXA TESTSIX MISS CASESIXB TESTSIX MISS CASESIXC TESTSIX MISS CASESIXC TESTSIX	CAP6a(CRB03) CAP6b(CRB03) CAP6c(CRB03) CAP6d(CRB03)
7	MRS A'BCD THISISTEST CASEONEFORENAMEABCDEFGHIJKLMNOPQRSTUVWXYZAB ABCDEFTHISISTESTCASEONEMIDDLENAMEABCDEFGHIJKLMNOPQRSTUVWXYZA ABCDEFTHISISTESTCASEONESURNAMEABCDEFGHIJKLMNOPQRSTUVWXYZABCD	RB7 (CRB01)
9	MR APPLICANT ONE - FIFTY (50 APP'S)	RB9(CRB01) CAP9(CRB03) CAP9(CRB04)
10	MR APPLICANT MULTIPLE	RB10(CRB01)
11	DR CASE ELEVEN-ONE DR CASE ELEVEN-TWO DR CASE ELEVEN-THREE MR CASE ELEVEN-FOUR	RB11(CRB01) CAP11(CRB03) CAP11(CRB04)
12	DR REJECT INTEGRITY VALIDATIONTESTCASETWELVE	CAP12(CRB04) CAP12(CRB03)
20	MRS NEW TESTCASETWENTY KEY MRS NEW TESTCASETWENTY KEY	RB20(CRB01) CAP20(CRB03) CAP20(CRB04)
21	MR REJECT FILE ONECASETWENTYONE MR REJECT FILE TWOCASETWENTYONE	CAP21(CRB02)
23	N/A CRB02 FOR DIFF RB	CAP23(CRB02)
24	MR CASETWENTYFOUR INTEGRITY KEY	RB24(CRB01) CAP24(CRB02)
25	MR IVORCASETWENTYFIVE MISMATCH	RB25(CRB01) CAP25(CRB02)
26	DR REJECT INTEGRITY VALIDATIONCASETWENTYSIX	CAP26(CRB02)

## Incidents_DETAILS
INCIDENT REF	DESCRIPTION	Test Case	RAISED ON	CLEARED ON