CONTRACTORS FRAMEWORK

THE LOCAL COMPETITION

Guidance for Framework Users and Panel Members

November 2013

Framework Users wishing to use the EFA Contractors Framework are required to obtain the prior written consent of the EFA.

EFA and its advisers accept no liability whatsoever for any expense, liability, loss, claim or proceedings arising from reliance placed upon this Local Competition Guidance.

Abstract

This Local Competition Guidance document has been developed to provide Framework Users and Panel Members with guidance, direction and instruction to operate the Contractors Framework effectively and efficiently. It also seeks to ensure that the Framework User is able to undertake the Local Competition process in a manner that enables compliance with applicable regulations. The document details: the Local Competition process; the documents relevant to the conduct of the procurement process. This could be either documents to be produced by the Framework User or other guidance documentation that would be of benefit to the Framework User; other physical deliverables required of the Contractors Framework User; and typical timescales for procurement stages. Framework Users will be required to follow this Local Competition Guidance. The Local Competition Guidance should be read in conjunction with the other published guidance and template documents, in particular the following are of relevance: Feasibility Study Template; Preliminary Invitation to Tender (PITT) Template and Evaluation Matrix; Invitation to Tender (ITT) Templates and Evaluation Matrix; Final Business Case Template.

Contents

1.	Introduction	1

2.	Types of scheme	3

3.	Local Competition Process and Timetable	3

4.	Overview of the Local Competition	10

5.	Pre Procurement – Feasibility Study	10

6.	PITT Stage - Initial Engagement and Short-listing	12

7.	ITT stage - Invitation to Tender and Evaluation	14

8.	Evaluation of PITT and ITT	16

9.	The Application of a voluntary standstill period and the Appointment of Selected Panel Member	16

10.	Final Business Case and Contract Award	18

11.	Future School Call off Procedure	19

12.	Design and Build Contracts and Early Works Agreement	19

13.	Interface with Other Contracts	20

14.	Further Assistance	20

15.	Academies’ Development Agreement	20

Appendix A	22

Appendix B	23

Appendix C	40

Appendix D	41

THE LOCAL COMPETITION

Guidance for Framework Users and Panel Members

Introduction

The Education Funding Agency (“EFA”) has established a Contractors Framework (the “Contractors Framework”) which commenced operation on 14 November 2013 of a number of design and build contractors for each Sector ( “Panel Members”) to succeed the previous contractors framework set up by Partnerships for Schools (which expired on 11 November 2013).

The Contractor’s Framework operates across two Sectors:

- Sector North covers the North West, North East, Yorkshire and The Humber, East Midlands and West Midlands;

- Sector South covers the East of England, South East, South West and London.

A map and list of the areas covered by each of the Sectors is shown in Appendix D of this Document.

The purpose of this Guidance document is primarily to provide contracting authorities that wish to use the Contractors Framework (“Framework Users”) with advice on how to use the Contractors Framework and how to conduct a “Local Competition” to select a Panel Member. This document will also be of use to Panel Members so that they will understand what is expected of them through the process. The Contractors Framework was procured by EFA on behalf of DfE who is acting as central purchasing body on behalf of itself (for further information on the DfE please see www.education.gov.uk) and the bodies listed below. The potential Framework Users are:

- Education Funding Agency (EFA);

- Local authorities in England (for a list of local authorities in England  please see https://www.gov.uk/find-your-local-council);

- Community schools in England;

- Voluntary controlled schools in England;

- Voluntary aided schools in England;

- Special (any legal form) schools in England;

- Diocesan and other relevant faith authorities in England;

- Foundation schools in England;

- Trust schools in England;

- University Technical Colleges in England;

- Studio schools in England (for further information on studio schools please see www.studioschoolstrust.org/welcome);

- Academy trusts established or to be established in England (economic operators should note that free schools and university technical colleges are established as academy trusts);

- Further education colleges in England (please see http://www.aoc.co.uk/en/about_colleges/index.cfm );

- City technology colleges;

- And all educational establishments in England on the EduBase register at http://www.education.gov.uk/edubase/home.xhtml

Other wider educational and community facilities may also be procured under the Contractors Framework, especially where co-located. Such wider educational and community facilities may include, but are not limited to: Sure Start provision; Early Years provision; day care provision; libraries; leisure; and health facilities, where these complement educational facilities.

For the avoidance of doubt, the eligible bodies above shall include any providers of state funded education and shall also include any statutory successors and organisations created as a result of reorganisation or organisational change. In such circumstances clarification will be issued to Framework Users and Panel Members.

The Contractors Framework was procured under the Restricted Procedure of the Public Contracts Regulations 2006 (the “Regulations”). This document details the process to be followed to ensure the Regulations are adhered to.  In particular, the Framework Design and Build Contracts must be used to contract with a Panel Member.  The use of an alternative form of contract will not be permitted for any Scheme procured through the Contractors Framework.

All Framework Users will also be required to enter into an Access Agreement and Confidentiality Agreement with the Secretary of State for Education (being the legal entity for the EFA and DfE) which will stipulate the terms under which the Contractors Framework will be managed and the information available to Framework Users.  Framework Users will need to complete and submit a Feasibility Study (the “FS”) to the EFA for approval (see below).  If the works are not being funded by the EFA, the Framework User must also confirm that all capital costs will be met by the Framework User.

This Guidance document has been developed to enable Framework Users to operate the Contractors Framework effectively and efficiently. It also seeks to ensure that the Framework User is able to undertake the Local Competition process in a manner that enables compliance with all applicable law and the Regulations.

The Local Competition Guidance is intended to guide Framework Users through the operation of the Contractors Framework. There are also template documents for Framework Users to use to develop their requirements at each stage of the process. These are:

Feasibility Study (FS) template;

Preliminary Invitation to Tender (PITT) Template and Evaluation Matrix;

Invitation to Tender (ITT) Templates and Evaluation Matrix;

Template Standstill Notice for unsuccessful Panel Member (where standstill period is applied by Framework User);

Template Selected Panel Member Letter (which includes optional provisions relating to standstill (where standstill period is applied by Framework User)); and

Final Business Case (FBC) Template.

These documents will usually be made available online from the following link http://www.education.gov.uk/schools/adminandfinance/schoolscapital/funding/a00202925/contractors-framework  or via the EFA PD. Where the need for further information arises, EFA will develop and issue such information and publish it online or make it available through the EFA PD.

Types of scheme

The EFA anticipates that the Contractors Framework will be used to deliver:

- a Scheme (single school);

- a batched programme of Schemes to be procured on the basis of using one sample school to select the Panel Member - such Panel Member subsequently delivering the Future School Scheme(s).  It is anticipated that it may be necessary to have a number of Schemes on site at the same time as part of an enhanced delivery profile for specific programmes. Note that Future School Schemes may be procured via the Framework User procuring the sample scheme or by Secondary Framework Users  (see paragraph 11 below) as part of the same batch.  Future School Schemes within a batch may also be spread across multiple local authority areas within a Sector (but not across different Sectors).

The Local Competition procedure is designed to be identical for each of these types of Scheme.  The Framework was procured on the basis there will only be one sample school developed during the Local Competition – this is further highlighted in Section 7 of this Document.

Local Competition Process and Timetable

This document sets out the procedure that must be adopted by any Framework User wishing to use the Contractors Framework for a Local Competition.  In summary, the Local Competition is expected to run as follows:

| Stage | Task / Timescale | Document(s) Required | Purpose of Document(s) | Location of Document (the location indicated is the current intended location and may be subject to change) |
| --- | --- | --- | --- | --- |
| Feasibility Study (FS) | Enter into the Access Agreement with the Secretary of State for Education (being the legal entity for the EFA and DfE) before submission of the FS to EFA. | Access Agreement | Governs the terms under which the Contractors Framework is managed and the information available to Framework Users. | The Access Agreement will be provided to Framework Users by EFA and will be available online. |
|  | Enter into Confidentiality Agreement before submission of FS to EFA. | Confidentiality Agreement | Provides for the Framework User to be bound by confidentiality obligations in respect of pricing/rates and other information provided by the Panel Member and made available to the Framework User by EFA. | The Confidentiality Agreement will be provided to Framework Users by EFA and will be available online. |
|  | Preparation of the FS is expected to take between 6 to 10 weeks however Framework Users should aim to optimise their programme to reduce this timescale as far as possible | FS template | FS to be approved by EFA. Approval of FS will confirm Local Competition process can commence | The FS template will be available online. The EFA Project Director / Project Manager allocated to the Scheme will be able to provide advice on the format of the FS. |
| PITT - Initial Engagement and Shortlisting | This stage should take no more than two weeks | Invitation to all Panel Members to take part in Local Competition by way of completion of PITT. The PITT must be sent to all Panel Members on the relevant Sector Framework. PITT, PITT Evaluation Matrix and draft ITT. | To enable an evaluation of initial responses to shortlist two Panel Members. See paragraph 6 below for more information | Template PITT and ITT will be available online. |
| ITT and Evaluation | This stage should take between 6 to 8 weeks. The ITT period is generally split into a 4 to 6 week design development competition and a 2 week ITT evaluation period. If the Framework User is applying a voluntary standstill period to its Local Competition, this standstill period needs to be factored into the timetable. However, it is expected that such period will run concurrently with the Selected Panel Member’s preparation to submit planning and therefore it is not likely to have any impact on the programme duration for contract award. | ITT to be sent to two short listed Panel Members. Documents required for ITT: Volume 1 – Information and Instructions for Panel Members Volume 2 – FS as approved by EFA. Volume 3 – Design and Build Contract, Early Works Agreement (and Future Schools Agreement if relevant) Volume 4 – Surveys and Collateral Warranties Volume 5 – Authority’s Requirements Volume 6 – Pricing Schedules Volume 7 – Technical Questions and evaluation matrix Volume 8 –Documents to support Planning Application If a standstill period is being applied by the Framework User, the following template letters will need to be completed and sent to the relevant Panel Members: Template Selected Panel Member letter (which includes optional provisions where a standstill period is applied); and Template Standstill Notice to be sent to unsuccessful Panel Member. | To enable an evaluation of Scheme specific requirements in order to select the preferred Panel Member. See paragraph 7 for more information. | Template ITT will be available online or from the EFA PD. Template Standstill Notice and Template Selected Panel Member Letter will be available from EFA PD. |
| Final Business Case (FBC) /Contract Award | This stage should take up to16 weeks, based on 3 weeks planning documentation preparation and 13 weeks planning period; where the planning process period is shortened these timescales can be reduced accordingly. | Final Business Case template | FBC to be approved by EFA in order to release funding for the Scheme. | FBC template will be available online (the EFA Project Director / Project Manager allocated to the Scheme will advise on the format of the FBC). |
|  |  | Design and Build Contract | Design and Build Contract to be entered into by successful Panel Member and Framework User in order to commence Scheme. | Design and Build Contract available on request from EFA |
|  |  | Future Schools Agreement Early Works Agreement | Where the procurement involves more than one school a Future Schools Agreement will be signed. This provides the basis and the process for the development of the Future Schools. Governs any early or advance works | Future Schools Agreement is available from EFA on request Available on request from the EFA |
|  |  | Development Agreement | The appropriate Development Agreement is to be signed between the Framework User (other than an Academy Trust) and the Academy Trust where the Framework User is procuring on behalf of the Trust and provides the basis upon which the Academy Trust participates in the process of design finalisation and has its interest recognised and governs the licence and leasing arrangements and design and construction of the Academy. Where the Academy Trust is the Framework User, a different form of Development Agreement may or may not be necessary and projects should check with the EFA PD to ascertain. | Development Agreement available on request from EFA |

Overview of the Local Competition

Before the Framework User can start the Local Competition process, the Framework User will need to have prepared a FS. This will need to be approved by the EFA in order to permit the Framework User to engage with the Panel Members.

Each Local Competition will have the following stages:

- Pre-Procurement Feasibility Study (FS);

- Preliminary Invitation to Tender (PITT) - Initial Engagement and Short Listing;

- Invitation to Tender (ITT) and Evaluation Matrix; and

- Final Business Case (FBC) and Contract Award.

Each stage is described in sections 5 to 10 below, with the programme shown at Appendix A.

Pre Procurement – Feasibility Study (6- 10 weeks)

All Framework Users wishing to use the Framework MUST seek prior permission of the EFA to do so.

The Framework User will prepare a Feasibility Study (FS) which will be approved by EFA in order to permit the Framework User to issue a PITT to the Panel Members.  The minimum requirements for the FS are set out in the FS template and the format of the document and any additional requirements for an individual project would be advised by the EFA Project Director. The FS should demonstrate that all appropriate issues have been addressed and that the project is ready to move to procurement. The FS sets out the options that have been considered for the Scheme and also recommends a preferred option for the Scheme which has been scoped and costed within the agreed funding envelope.  The FS will also need to document the agreed procurement strategy particularly for any Future Schools Scheme(s).  Preparation of the FS is expected to take between  6 to 10 weeks, however Framework Users should aim to optimise their programme to reduce this timescale as far as possible. In demonstrating a project is ready for procurement the FS needs to contain the following as a minimum:

- a clear brief for Panel Members to respond to – including an accommodation schedule and adjacency diagrams;

- surveys as referred to in the Feasibility Study template, where indicated with appropriate collateral warranties having been agreed with appropriate consultants upon which the successful Panel Member can rely;

- confirmation that the parties understand the requirements of Clause 4 and Schedule 15 of the Design & Build Contract regarding matters of land title and will provide all such information as required under the terms of the Contract;

- where an independent procurement is taking place for ICT equipment, a clearly stated  position on affordability, procurement and integration;

- confirmation that the Framework User is either the owner of the site OR where the Framework User is not the owner of the site, confirmation that relevant arrangements/agreements are in place to demonstrate that the Framework User will be in possession and/or occupation of the Site and that the terms of such possession and/or occupation will  allow the Framework User to grant the ancillary rights under the D&B Contract and thereby allow the  Scheme development and construction; confirmation that the site is clear and unencumbered (or provide details of any encumbrances to which the site is subject);

- where funding is being provided via a party external to EFA, evidence that such funding is secured;

- a costed feasible control option within budget;

- a letter of support from the relevant local planning authority in lieu of outline planning permission, and details of any discussions with statutory consultees;

- details of an agreed approvals process to be followed by the Framework User to enable quick decision making;

- copy of signed Access Agreement and Confidentiality Agreements;

- where applicable, details of any consents required or granted in respect of the development (eg in respect of disposals, listed building consents, etc).

The Framework User should consider employing a Project Manager/Technical Adviser to undertake the day to day running of the Scheme and to develop the Scheme through to FS stage.  Alternatively, the Framework User can use its own internal resources to undertake the role of Project Manager / Technical Adviser if they are sufficiently qualified and experienced.  For some programmes, EFA may engage Technical Advisers on behalf of the Framework User; the EFA Project Director will advise whether this is the case for your scheme.

The control option prepared by the Framework User (as part of the development of the Feasibility Study (FS)) will be included in the FS and be available for Panel Members to review as part of the Local Competition.   The Framework User cannot novate the control option to the Contractor and will not provide collateral warranties for this control option.  As stated above, the purpose of the control option is to demonstrate a deliverable option within the funding envelope and assist in the briefing process.  The control option done by or on behalf of the Framework User is expected to be up to the design equivalent of RIBA Stage A/B only.  The Framework User should ensure there is no conflict of interest once the Local Competition process commences, ie an architect or other consultant or supplier providing initial design work or other services in relation to the FS for that Scheme on behalf of the Framework User should not be put forward by a Panel Member as part of their supply chain in response to the Local Competition invitation for that Scheme. Framework Users are advised that Panel Members who contravene this requirement will be in breach of their Framework Agreement(s) and may have the Framework Agreement terminated.

The Contractor will be expected to provide ICT infrastructure (passive, active and associated components) as defined in the design guide and ICT responsibility matrix. The position on ICT equipment and integration must be made clear in the FS (eg provided by decant of legacy equipment, a separate ICT procurement, or variation in funding and scope of the Contractors works), which should include a description of how any design and construction interfaces will be managed. In all cases, so that the interface is properly managed, the Framework User will need to provide to the Panel Members at ITT stage, any project specific context to supplement the design guide and ICT responsibility matrix.

The Framework User may undertake market testing with the Panel Members. This should take the form of a “Panel Member Information event” and ideally would take place at least seven working days prior to the PITT being issued.

The Framework User will prepare its Preliminary Invitation to Tender (“PITT”) and Invitation to Tender (“ITT”) in accordance with the templates provided by the EFA.  The ITT must be drafted in parallel with the FS as it will be issued in draft with the PITT to all Panel Members.  The content of the PITT and ITT are described in sections 6 and 7 of this Local Competition Guidance.

PITT Stage - Initial Engagement and Short-listing (2 weeks)

Once the FS for a Scheme has been approved and the Scheme has been given approval to proceed by EFA, the Framework User will send the PITT to ALL of the Panel Members in the appropriate Sector to invite them to take part in the Local Competition.  It is permissible to write to Panel Members via e-mail.  The Framework User must include all Panel Members in the invitation regardless of any communication they have received from Panel Members in advance of the PITT issue relating to their intention, or otherwise, to bid.

The Framework User should issue the PITT document with the invitation to take part in the Local Competition, including a draft ITT that has been worked up in parallel with the FS.  The PITT and draft ITT must be approved by EFA prior to issue by the Framework User.  The Framework User’s procurement strategy and timeline will need to be agreed with EFA as part of the FS approval process, and Framework Users should make the strategy and timeline clear to all of the Panel Members when they are invited to take part in the Local Competition.

Panel Members will be required to express an interest in the Scheme by submitting responses to the PITT. Panel Members must either fully respond to the PITT or decline.  Where a Panel Member declines, they must provide written reasons for declining on or before the relevant closing date for the PITT responses.

The purpose of the PITT will be to select a short list of two Panel Members.  A period of one week should be given for completion of the PITT by Panel Members. Evaluation of responses by the Framework User should take one week to complete.   If it is decided to undertake clarification interviews, they should be conducted within this week in accordance with paragraph 6.5 below.

The PITT will be designed to establish key local issues, such as:

- confirmation of Panel Member supply chain members and their availability and capacity to deliver at the current time for the sample school only;

- how each Panel Member intends to approach the Scheme and develop the designs (designs for the Scheme are not required at this stage);

- the Panel Members’ understanding of the key local issues to be addressed;

- the Panel Members’ ability to deal with local interface issues, for example working with an existing ICT partner or integrating with an existing ICT procurement; and/or interface with FM providers such as catering providers

- Outline approach for taking forward any Future School Schemes.  The PITT questions in the template document are intended to cover most issues that Framework Users would require at this stage in the process, although making minor amendments to reflect local or project specific issues may be accepted.  Where it is considered amendments may be required, this should be discussed with the EFA PD.

- Where a PITT relates to a batched procurement, the questions regarding   Future School Schemes should relate to the procurement methodology and other information required to demonstrate how the Panel Member would deliver the Future School Scheme. No supply chain information or designs in respect of the Future School are required in the PITT and Framework Users should not encourage Panel Members to provide such information.  Note that any Future School Schemes need to be identified in the PITT by name and address – generic programme-wide wording is not acceptable.

The PITT template includes details of the evaluation criteria and weightings that have already been notified to Framework Users in accordance with the Regulations. The Framework User has no flexibility to alter the weightings within the evaluation criteria but can include sub-criteria and sub-criteria weightings. The Framework User must disclose any specific sub-criteria and sub-criteria weightings it proposes to utilise in the evaluation of the PITT.

It is not a requirement to interview Panel Members that have responded to the PITT, however, the Framework User may choose to do so. Where a Framework User chooses to do this they will only be required to interview a maximum of 4 (four) Panel Members. The selection for interview will be on the basis of being ranked in order after the evaluation of responses to the PITT.  The interview will not be scored separately.  Any new information provided at interview that is not provided within the written submission will not be taken into account in the moderation of the scores.  The purpose of the interviews is to provide clarification on points made in the written PITT submission where such is required.  Clarifications may be used in moderation of the evaluation of the written responses to the PITT.  Dates of potential interviews should be advised in the PITT and Panel Members given 2 clear days’ notice prior to attending interview.

At the end of the PITT stage the Framework User will select a short list of two Panel Members and will release the final ITT documents to those shortlisted Panel Members.

The Framework User will inform those Panel Members who have been unsuccessful at the PITT stage at the same time as they inform those Panel Members who have been short listed.  The Framework User shall provide written feedback on the reasons why the Panel Member has been unsuccessful, including that Panel Member’s evaluated scores and the lowest and highest scores from the competition. EFA must be consulted in any written communication and may attend any feedback sessions with Panel Members. A copy of the full evaluation matrix with completed scores shall be provided to EFA by the Framework User.

The PITT stage should take no more than two weeks.

ITT stage - Invitation to Tender and Evaluation (6-8 weeks)

Following issue of the ITT to the two short listed Panel Members, these Panel Members must be given between four and six weeks to engage with the Framework User in order to develop their bids, depending on the complexity of the Scheme, most large or complex Schemes will require the full six weeks, however, there may be some instances where it may be possible to complete eg small, straightforward Schemes in a shorter period.  The ITT period should be discussed and agreed with the EFA PD, and included in the timeline contained within the FS.

Should Panel Members decide to decline to respond to an ITT, they must provide detailed written reasons for doing so prior to the closing date for the ITT.

During the ITT period Panel Members will be given regular access to the Design User Group and key Framework User representatives.  The short listed Panel Members should be encouraged to proactively seek and respond to the briefing information whilst also managing aspirations to provide a solution to meet the Authority’s Requirements at or below the funding envelope for the Scheme.

The Scheme(s) will be developed at or below the available funds and within the Panel Member’s agreed Pricing Schedule incorporated in each Panel Member’s Framework Agreement with the EFA.

The relevant Pricing Schedules will be made available to Framework Users via the EFA PD when they have short listed two Panel Members.  All Framework Users must have signed the Access Agreement and Confidentiality Agreement with EFA governing release of such information. The level of design at ITT stage for the Scheme will be detailed in the ITT.  There will be only one sample Scheme.  Where there is a batched procurement, the two shortlisted Panel Members may not be requested to commence the design of Future School Scheme(s) during the Local Competition period.

Where EFA is funding the Scheme, the Framework User will have received notification of the funding allocation agreed with EFA as part of the FS approval process. Where the scheme is not funded by EFA, the Framework User will have included details of the confirmed funding for the scheme in the Feasibility Study and tender documents.

In developing their bids, the shortlisted Panel Members will be required to ensure that the Contract Sum (if a Lump Sum Design and Build Contract is used) or the Guaranteed Maximum Cost (GMC) (where the Target Cost Design and Build Contract is used) for that Scheme is no greater than the funding envelope advised and any funding contributed by the Framework User, subject to relevant VAT rules / legislation.  The selected option of Design and Build Contract to be used must be made clear to all the Panel Members when they are invited to take part in the Local Competition

The draft ITT should have been attached in draft form to the PITT in order that Panel Members had the information necessary to respond to the PITT questions.  The final ITT will comprise the following:

Volume 1		Information and Instructions to Bidders

Volume 2		Agreed Feasibility Study

Volume 3	The appropriate Design and Build Contract(s) and Future Schools Agreement (if relevant)

Volume 4	Surveys undertaken by the Framework User and all supporting collateral warranties

Volume 5		Authority’s Requirements

Volume 6 		Pricing Schedules

Volume 7 		Technical Requirements and evaluation matrix

Volume 8 		Documents to support a Planning Application

The information requested in the ITT should be based on the template ITT.  This template also includes details of the evaluation criteria that have already been notified to Framework Users in accordance with the original procurement process to select Panel Members.  The Framework User must ensure that the ITT is compliant with the Contractors Framework and agree the ITT with EFA prior to issue.

The information requested in the template ITT will  include:

- the design approach;

- materials specifications;

- fittings, furniture and equipment details;

- programmes, method statements and decant/phasing plans;

- cost proformas and whole life cost analysis; and

- technical and design information as set out in Volume 7 of the ITT.

Where the ITT is for the sample Scheme in a batched procurement, it may contain questions relating to the Panel Member’s approach to delivering the Future School Schemes. This may include for example, procurement methodology, approach to resourcing, delivery mechanisms, and other similar information, but no design will be required and Panel Members should not be asked to provide details of their supply chain for Future School Schemes.

Shortlisted Panel Members will have four to six weeks to respond to the ITT.

The Framework User will need to allow two weeks to evaluate the ITT and appoint a Selected Panel Member.

Framework Users may insert where necessary appropriate questions that will test the Panel Members’ understanding of local and project specific matters. Framework Users should note that generic questions (detailed in Appendix C) were asked of the Panel Members by EFA as part of the process used to establish the Contractors Framework.  Framework Users should take care not to repeat such generic questions but are advised to use appropriate adaptations to ensure relevance to local and project specific matters. Panel Members should also be reminded that their responses must be project specific and have due regard for local matters.

Evaluation of PITT and ITT

Under the Regulations EFA was required to indicate the evaluation criteria and weightings to be used for the PITT and ITT stages of the Local Competition.  The relevant criteria and weightings will be set out in the template PITT and ITT documents, with required weightings included.

The Framework User must use the weighting for each evaluation criterion indicated in the documentation.

The Framework User may also use scoring thresholds for the available score under the evaluation criteria.  Such details must be set out in the PITT and ITT so that Panel Members are fully aware of any scoring threshold against the relevant criteria.  Such a scoring threshold could be, at the Framework User’s discretion, set at 50% so that any Bidder failing to achieve a score of 50% or more of the available score against the relevant criteria will be excluded.

As explained above, this process needs to be made clear to Panel Members when they are invited to take part in the Local Competition in order to ensure full transparency.

The Application of a voluntary standstill period and the Appointment of Selected Panel Member

The 2009 Remedies Regulations (the “Remedies Regulations”) amended the Regulations by introducing detailed rules regarding the application of the standstill period and a new remedy of “ineffectiveness” which applies to framework agreements set up after 20 December 2009.

A declaration of ineffectiveness is available as a remedy in various situations, one of which is where there have been breaches in the mini competition rules for frameworks and the opportunity for pre-contractual remedies has not been properly allowed (for example, by not applying a standstill period prior to award).

The standstill obligation stipulated by the Remedies Regulations does not apply to above threshold call-offs from framework agreements. However, the quid pro quo for this is that ineffectiveness will in principle apply if the rules for making the call-off are breached.  As an alternative to running this ineffectiveness risk, Framework Users can apply the standstill period voluntarily, in which case ineffectiveness will not be available as a remedy for breaches of the call-off rules, provided the Framework User applied the standstill period properly.  As stated above, the ground for ineffectiveness that relates to call-offs under a framework only applies where there has been a breach of the mini competition procedural rules imposed by regulations 19(7) (b), (8) and (9) of the Regulations.  The Local Competition process under the Contractors Framework complies with these rules.  However, the Framework User may wish to consider the level of confidence it has in how well it has followed the Local Competition process in deciding whether or not to apply a standstill period.  If the Framework User is confident that its compliance with the Local Competition process is robust and the contract is needed promptly, then dis-applying the standstill period may be more attractive, whereas if there are even slight concerns about the Local Competition process that has been run by the Framework User, then it may be best to apply the standstill period and thereby limit the risk of ineffectiveness.  Whether or not to apply a standstill period is a decision which needs to be taken by the Framework User as it affects their procurement. If a standstill period is applied, then the Framework User needs to factor this into its timetable and ensure Bidders are made aware of this.  However, it is anticipated that the standstill period will run concurrently with the Selected Panel Member’s preparation and submission of planning documents to the relevant planning authority so it is not expected to have any adverse effect on the timescales for award.

Following the completion of the evaluation of the ITT submissions, the Framework User shall inform the shortlisted Bidders of the outcome of the evaluation process and shall confirm which Bidder shall be appointed the Selected Panel Member (the “Selected Panel Member” or “SPM”) on the basis of the evaluation process, using the standard form of appointment letter a template of which is available from the EFA PD.

If the Framework User is applying a standstill period, it must inform all “tenderers” and any “candidates” (i.e. any rejected applicants that have not been informed of the reasons of the rejection in their application) of the decision to award the call-off contract by sending a standstill notice in writing by the most rapid means of communication practicable.

Where the standstill notice is to be sent to a tenderer (in this case, the other Bidder who progressed to ITT stage) the standstill notice must include:

The criteria for the award of the call-off contract;

The reasons for the decision, including: the characteristics and relative advantages of the successful tender, the score (if any) obtained by the Bidder which is to receive the notice, and the SPM to be awarded the call-off contract;

The reasons (if any) why the unsuccessful Bidder did not meet the technical specifications;

The name of the SPM;

A precise statement of either:

When the standstill period is expected to end and, if relevant, how its ending might be affected by any, and if so what, contingencies; or

The date before which the Framework User will not, in conformity with regulation 32A of the Regulations, enter into the call-off Contract.

A Template Standstill Notice and Template SPM Letter are available from the EFA PD.  The Template Selected Panel Member Letter contains optional provisions to be used where a standstill period is applied.

Upon appointment of a SPM to a Scheme by the Framework User, the SPM will work with the Framework User and client team to further develop designs and submit a full planning application prior to contract award.

For batched scheme procurements,  following appointment as SPM, and prior to award of a Design and Build Contract, the SPM may be requested to commence work contributing to the Feasibility Study OR be issued with the Invitation to Submit Proposals (ISP) for the Future School Schemes pursuant to an award of a Future Schools Agreement. The process described in Schedule 1 of the Future Schools Agreement must be followed in respect of any Future School Schemes.

Reserve Bidder

Framework Users may, in the circumstances set out in this section, appoint the unsuccessful ITT Bidder as a reserve bidder. This will only be appropriate where the Framework User considers that the unsuccessful Bidder offers a compliant, affordable and appropriate offer. In such circumstances the SPM must be informed that a Reserve Bidder is to be appointed and that the Reserve Bidder will be appointed as the replacement SPM in circumstances where, for instance: (a) the SPM has developed the ITT submission during the post-ITT period such that the ITT submission is no longer affordable; (b) the SPM has developed the ITT submission during the post-ITT period such that it is materially different to that submitted at ITT stage; and, (c) in the reasonable view of the Framework User the SPM has or is behaving in a manner which threatens the successful delivery of the Scheme. These circumstances only apply in respect of the Sample School. Other circumstances may give rise to termination of the appointment of the SPM and these should be discussed and agreed with EFA where relevant.

The replacement of the SPM with a reserve bidder may only be exercised (in accordance with this section) during the period between appointment of SPM and the grant of planning permission for the Sample School.

Where the Framework User is undertaking a project which is, in whole or part, funded by the EFA then the prior agreement of EFA must be sought prior to exercising the discretion set out in this section.

The unsuccessful ITT Bidder should be asked to confirm their commitment to keeping their offer open for a period of 16 weeks and accept the status of reserve bidder. This can be done as part of the standstill letter to be sent to the unsuccessful bidder as set out in section 9.6 above (please note Template Standstill Notice contains optional wording if a reserve bidder option is to be used). For the SPM the notification that there is a reserve bidder, including the circumstances where the reserve bidder may become the replacement SPM, should be set out in the letter of appointment (the template Selected Panel Letter contains optional reserve bidder wording).

Final Business Case and Contract Award (up to 16 weeks)

It is important to note that there will be no contractual commitment from the Framework User until the Design and Build Contract is awarded, so the SPM will be expected to carry all development costs at risk until contract award.  Framework Users should note that all Panel Members entered into the Contractors Framework Agreement on this basis.

Between appointment as SPM and contract award, the SPM will be expected to:

- Finalise the designs, construction programme and obtain all statutory consents in preparation for the construction phase including full planning permission;

- Engage with the client team, both to gain any final briefing information and to appraise design status;

- Contribute to the feasibility study for any Future School Scheme(s)

- Carry out any designs of any Future School Scheme(s) as agreed in the procurement strategy before contract award;

- Prepare and agree room data sheets with relevant stakeholders and the Framework User; and

- Submit contractor’s proposals, contract sum analysis and cash flow information to the Framework User prior to the anticipated date of contract award.

During this period, the Framework User will be required to prepare a Final Business Case (FBC), which will be reviewed and approved by EFA.  The FBC will either confirm that there has been no material change to the Scheme objectives since the FS or that any changes have the appropriate and evidenced approvals. The Scheme needs to demonstrate it is affordable, is supported by stakeholders and that the procurement process has been robust.  On approval, for Schemes funded via EFA, funds will be released for the Scheme, and the Scheme will be able to reach contract award. For Schemes funded from other providers EFA will issue an approval letter.

The FBC template will be available online, template documents would be available from the EFA PD.

Future School Call off Procedure (see also schedule 1 of the Future Schools Agreement)

A Framework User may include within a PITT or ITT a Future School Scheme on behalf of another Framework User (“Secondary Framework User”).  Such a scheme may be delivered pursuant to a Future Schools Agreement.  In such cases, the Secondary Framework User would be the party to enter into the Design and Build Contract with the selected Panel Member (and Early Works Agreement where appropriate) for such Future School Scheme.

The Framework User/Secondary Framework User must follow the procedure set out in Schedule 1 of the Future Schools Agreement in respect of the procurement of Future School Schemes

Design and Build Contracts and Early Works Agreement

The choice of contract to be used, which should be indicated to Panel Members when invited to take part in a Local Competition, will vary according to the nature of the Scheme.  Information on the appropriate contract to use and issues to consider is set out in Appendix B.

Framework Users should note that as part of setting up the Contractors Framework Panel, the Panel Members have provided unqualified statements of acceptance of the Design and Build Contract, Early Works Agreement, Framework Agreement and Future Schools Agreement terms.  As a consequence, neither the Framework User nor Panel Member is permitted to make changes to any EFA template contract other than where indicated in the contracts themselves (including their schedules and appendices).

EFA approval of the Design and Build Contract(s) to be entered into will be required with the Framework User providing a table of any relevant derogations in EFA prescribed format at least three weeks prior to anticipated contract award.  The procedure set out in the ‘EFA Derogations guidance’ (as issued from time to time) document should be followed.  This document can be obtained from the EFA Project Director.

There is a prescribed form of Early Works Agreement which must be used for early or advance works.

Interface with Other Contracts

Where ICT works and services are procured or provided separately, in part or in full, by the Framework User or directly by the school or school trust, where they are not the Framework User, the Selected Panel Member will be required to work closely with the preferred ICT Service Provider. This is to ensure that all works are integrated to support school operational readiness at building occupation. There may also need to be an interface with key facilities management providers, for example catering.  The interface will be managed by the Framework User, and the Selected Panel Member will need to work closely with the relevant provider(s).

The Framework User must ensure that any commissioning under the Design and Build Contract that interfaces with ICT provision is fully detailed in the Authority’s Requirements. No Interface Agreement is permitted to be used under the Framework.

For the avoidance of doubt, the Framework User shall not enter into any other type of contract with the Panel Member other than those contracts that have been commissioned as part of the Framework procurement

Further Assistance

Framework Users using the Contractors Framework can get advice and assistance from their EFA Project Director.

Academies’ Development Agreement

Framework Users (other than Academy Trusts) should note that an Academies’ Development Agreement has been prepared to regulate the relationship between the Framework User and the Academy Trusts. The Academies’ Development Agreement (to be entered into between the Framework User (other than an Academy Trusts) will be executed simultaneously with the Design and Build Contract. It provides the basis upon which the Academy Trust participates in the process of design finalisation, is consulted by the Framework User in relation to construction and commissioning matters and more generally has its interest recognised in terms that the Framework User will in turn take into account within its relationship with the Panel Member.

The Academies’ Development Agreement also envisages the novation of the Design and Build Contract to the Academy at a date immediately following completion of the Defects Liability Period (defined in the Design and Build Contract).  The purpose of novation is that the Academy then has a direct relationship with the Panel Member for the purpose of enforcing the Design and Build Contract generally and specifically in relation to Intellectual Property Rights and Latent Defects. This approach also allows the Framework User to drop out of the contractual chain.

# Appendix A

Programme for Delivering the Local Competition

Appendix B

Design and Build Contracts, Future Schools Agreement and Early Works Agreement– Summary of Key Points for a Framework User

The two Design and Build Contracts to be used under the Contractors Framework Agreement are largely based on the standard form BSF Design and Build Contracts previously used for the BSF Programme.  It is likely that a large proportion of the issues set out below will need to be addressed on either Design and Build Contract used by a Framework User depending on the specific requirements of a Scheme.

The terms of the two Design and Build Contracts are fixed.  Amendments to any of the terms are not permitted (other than those allowable through the footnote or the operation of square brackets or as otherwise noted in the contracts) and will not be agreed by EFA.  The footnotes and parentheses of the standard document (together with this Summary) will guide a Framework User as to the options it has and decisions it needs to take to produce an agreed form.

General comments and background

The Design and Build Contracts (“Design and Build Contracts”) are to be used where the Framework User, stated as the “Authority” in the contracts, is using capital funding to procure either substantial new building works or substantial refurbishments pursuant to the Contractors Framework.  The parties to the Design and Build Contract will be the Authority and the Panel Member who has been selected following the Local Competition procedure under the Contractors Framework Agreement, identified in the contract at the “Contractor”.  A separate Design and Build Contract must be used for each Scheme.

The two standard forms of Design and Build Contract, which will be used depending on the type of works to be undertaken, are as follows:

Lump Sum Option

A fixed-price contract, where the price of the original contract work remains fixed, to be used for the vast majority of Schemes whether they are predominantly or exclusively of a new build nature or predominantly or exclusively refurbishment.  It is important to note that the price may still be subject to modification on account of ordered variations, claims and other matters.

Target Cost Option

A cost reimbursable contract may be used for Schemes which are predominantly or exclusively refurbishments.  This form of contract is sometimes called gainshare – painshare, with the theory being that there are advantages for both the Authority and the Contractor.  The idea is to offer an incentive to the Contractor such that the Contractor keeps a proportion of any savings on the final cost compared with the agreed target.  The target cost sharing mechanism is set at 50/50 in this contract.  Perhaps more significantly, the Contractor is required to absorb half of any overruns up to the guaranteed maximum cost threshold and all of the overrun from that threshold onwards.

Only one school Scheme can be procured under any Design and Build Contract.  Where, exceptionally, more than one Sample School is designed and priced under the Local Competition, a separate Design and Build Contract must be entered into for each school Scheme.  The Authority will enter into a Future Schools Agreement with the Contractor for the procurement of non-sample Schools (provided the Authority has included that such non-sample future schools are to be procured under the Future Schools Agreement as part of the Local Competition Procedure for the Sample School(s)). The Future Schools Agreement must be signed at the same time as the Design and Build Contract for the sample Scheme is signed. Key Points on the Future Schools Agreement are set out at section 4 of this Appendix.

Save where expressly stated otherwise, this Guidance document deals with the contractual provisions in both Design and Build Contract Options.

The key commercial principles relating to the Design and Build Contracts are summarised at section 2 below.

Some direction is then given in relation to completing the forms of Design and Build Contracts and populating the Schedules at section 3 below.

Please also note that a form of Early Works Agreement has been produced for use in exceptional circumstances. The Early Works Agreement forms part of the Contractors Framework.  If an Early Works Agreement is entered into, consequential amendments, indicated by footnotes, will be required to the Design and Build Contract. The terms and conditions of the Early Works Agreement are fixed and must not be amended by the Authority or the Contractor.

Key Commercial Principles (Clause 5)

Design, Construction, Commissioning and Completion of the Works

The Contractor must carry out or procure the carrying out of the design, construction, completion, commissioning and testing of the Works so that the School is completed on or before its Date for Completion in full compliance with the Authority's Requirements and the Contractor’s Proposals, good industry practice, all necessary consents and applicable legislation.  There are further obligations regarding the Works, including the use of materials of satisfactory quality, the use of appropriately qualified staff and the maintenance of a safe and secure site.

Please note the additional design provisions which will apply where the Contractor makes use of Building Information Modelling. The Contractor will be expected to comply with the BIM protocol and co-operate at all times with the BIM Information Manager (if appropriate). The requirements relating to BIM and the mechanics of operation are set out in cause 5 and Schedule 29 of the Design and Build Contracts.

Site Conditions, Latent Defects and Asbestos (Clauses 7, 8 and 19)

The Contractor shall take responsibility for site conditions and the access to and rights over the Site. In addition the Contractor is the principal contractor for the purposes of the Site Waste Management Plans Regulations and is responsible for the site waste management plan is updated as the Works progress.

For refurbishment projects or projects where any part of an existing building is retained, a building survey and at least an Asbestos Management survey must have been carried out at the date of execution of the Design and Build Contract.  The Contractor is then responsible for any defects and asbestos to the extent that such are identified in or ought reasonably to have been identified in such surveys and, in the case of defects, such other surveys as it would have been reasonable to have expected the Contractor to have carried out.  The Authority is responsible for all other defects or asbestos.  In the context of refurbishment projects, the insurance arrangements will need to be reviewed and the Contractor should be noted on the relevant school policy.

All surveys which are procured prior to the entering into of the Design and Build Contract are appended within the relevant Schedules 23-25.

Please note that although the contractual provisions relating to asbestos remain in a familiar form when compared to previous design and build contracts there are now two options in the Lump Sum form of Design and Build Contract relating to asbestos risk and pricing that might be agreed by the Framework User at its absolute discretion.

The first option introduces the ability to use a provisional sum mechanism to deal with the removal of asbestos in existing buildings in which it has not been possible to carry out a Demolition Survey prior to the Design and Build Contract being entered into.

The second option is to be used in circumstances where the Contractor has agreed to take full risk of asbestos (cost, liability and programme implications) for a fixed sum/price on all buildings.  The Framework User will look to interrogate the price allocated to this risk in the light of all available surveys and its knowledge of the buildings to ensure that the Contractor’s offer provides value for money.

Certification of Completion of the Works (Clause 22)

Certification of the completion of the Works (or relevant part thereof) will usually be undertaken by the Authority’s Representative.  The Authority’s Representative issues a Completion Certificate for the Works (or relevant part thereof) when he is satisfied that the Works (or relevant part) are practically complete.  The Authority needs to give careful consideration to the selection of its Authority’s Representative, whether in house or an external consultant.  EFA strongly recommend that the Authority engages an external consultant with the requisite experience and professional indemnity insurance cover to carry out the role of the Authority Representative.  EFA has an existing Framework of Technical Advisers which the Authority can use.

Late Completion of the Works (Clause 24)

There are two alternative clauses relating to late completion of the Works; liquidated damages or provision of temporary accommodation by the Contractor. The individual circumstances of each project and the Authority’s requirements will determine which option is appropriate.

Payment (Clause 16)

The method and type of payment will depend upon whether the Lump Sum Option (new build) or the Target Cost Option (refurbishment) is used.  The payment profile for the Lump Sum contract is against construction milestones.  Milestone payments are made as the works progress, ie completion of foundations, completion of concrete slab etc.  A detailed Milestone Schedule must be prepared and incorporated into Schedule 9. For the Target Cost version, payments are made monthly against Actual Cost (as defined in the contract) incurred.  In both options, a fixed figure for the Contractor's Margin (profit, overheads, administration and the like) is agreed at the outset.  The Contractor's Margin is payable against an agreed profile to be set out in Schedule 9 (Payment Provisions).  In both cases, retention is withheld from payments due to the Contractor (milestone or monthly), with one half of the retention being released upon issue of the Completion Certificate and the balance upon issue of the Certificate of Completion of Making Good Defects or the Final Statement (whichever is later).  The retention percentage is 3%.

Additional optional drafting has been included in the Design and Build Contracts, at clause 16A, to allow project bank accounts to be used in certain circumstances (ie where a local authority is a counter party to the Contractor). Please note that the Contractor may be required to provide evidence that the project bank accounts are being used throughout the supply chain down to level 3 sub-contractors. The requirements of the project bank accounts and the mechanics of operation are set out in the Design and Build Contracts and cannot be amended by a Framework User or a Contractor.

Relief Events and Compensation Events (Clause 17)

The Contractor will be entitled to an extension of time and, if this option is selected, relief from its obligations (only) in the event of the occurrence of any Relief Event.  The Contractor will be entitled to seek an extension of time, relief from obligations and/or compensation on the occurrence of a Compensation Event.  Relief Events and Compensation Events are defined narrowly within the contract but depending on project specific issues the definition of Compensation Events may be expanded to cover matters such as the discovery of endangered species or Judicial Review.

Variations (Clause 15)

Upon request by the Authority, the Contractor is required to provide an Estimate in relation to the proposed Variation.  The Estimate must provide the Contractor’s opinion upon a number of issues including the impact on any Start on Site Date and/or any Date for Completion, and any Estimated Change in Project Costs.  Following further discussion between the parties, the Authority will decide whether to proceed with the Variation.

Insurance (Clause 25)

The Contractor is required to take out and maintain the Required Insurances and also to take out and maintain, and procure that its sub-contractors and design consultants take out and maintain, professional indemnity insurance (or product liability insurance where a sub-contractor carries product liability insurance in lieu of professional indemnity insurance).Authorities must carefully review their own insurance arrangements, particularly in the context of refurbishment schemes or shared sites.

Termination (Clause 31)

The Design and Build Contract provides for termination in the following circumstances:

- Voluntary termination by the Authority;

- Termination on Authority Default;

- Termination on Contractor Default (including corrupt gifts and fraud);

- Force Majeure.

The payment due to the Contractor upon termination will depend upon the reason for termination.  In the event of Contractor Default, the Contractor indemnifies the Authority against all additional costs incurred by the Authority (above those it would have paid to the Contractor had the Contractor completed the Works) in completing the Works.  In the event of Authority Default, voluntary termination or Force Majeure the Contractor shall be entitled to be paid for the Works undertaken and materials ordered at the date of termination together with cost of removal of materials and plant from the Sites and Direct Losses caused to the Contractor by the termination.

Collateral Warranties/Parent Company Guarantee (Clause 27)

The Contractor shall procure the provision of collateral warranties in favour of the Authority from all Principal Building Sub-Contractors (as defined) and the Professional Team appointed by the Contractor.  The Contractor must also provide a parent company guarantee in favour of the Authority from its parent whose identity is fixed under the Contractors Framework Agreement.  The Contractor may be required to procure a performance bond (equating to 10% of the Contract Sum) in favour of the Authority, upon execution of the Design and Build Contract though this will be determined by the Authority taking into account the cost of procuring the performance bond and the value for money this may/may not offer. The Authority should note that it will be responsible for and shall bear the cost of providing the bond and will not be permitted to rely on the capital funding envelope for the Scheme for meet the cost of the bond.

Dispute Resolution Procedure

The Design and Build Contract is a “construction contract” as defined by the Housing Grants Construction and Regeneration Act 1996 and therefore either party has the right to refer any dispute to adjudication, in which circumstances the Scheme for Construction Contracts shall apply.  The decision of an adjudicator shall be binding on the parties pending final resolution of the dispute by the English courts.

Novation

Where the Authority is procuring an Academy or a Voluntary Aided School, there is a requirement under the terms of the relevant Development Agreement to novate the Design and Build Contract to the Academy Trust or VA School Governing Body.  Novation only takes place when all financial claims have been settled by the Authority with the Contractor and the Certificate of Completion of Making Good Defects has been issued.    The form of novation is attached at Schedule 21.  In these circumstances, the Selected Panel Member is required to enter into a collateral warranty with the Framework User at the point of novation to protect the Framework User in the event of any forfeiture of the long lease to the Academy Trust or where the Framework User retains part of the site upon which the Scheme has been constructed.

Completing the Design and Build Contract

It is vital that an Authority fully and accurately compiles and completes all Schedules to a Design and Build Contract and reviews all alternative options, footnotes and text in square brackets before entering into a Design and Build Contract.  Legal advice should be sought as appropriate.

Completing the Contracts and Schedules

Each of the Design and Build Contracts are drafted in such a way that the Authority is required to populate the Schedules, where appropriate, and insert detail into clauses as indicated by the footnotes.  The footnotes show information to the Authority on key issues that need to be considered before completing any Design and Build Contract and all references to them should be deleted from the final form Design and Build Contract.  No Design and Build Contract should be entered into with a Contractor, unless an Authority has completed the contract correctly and populated all of the Schedules.

These Notes relate to (and follow the clause numbering of) the Lump Sum Option. Information on issues that are particular to Target Cost are noted below where applicable:

Parties

Ensure the correct name and registered office/principal place of business of the Authority and the Contractor are inserted here.  Ensure that the Contractor’s details are the same as the Contractor’s details under the Contractors Framework Agreement, eg that the Contractor has not entered into the Design and Build Contract using a subsidiary company.

Recital B

The Contractors Framework Agreements with each of the Contractors are dated 14 November 2013.

Recital D

Insert here a geographical description of the proposed school.

Definition “Abandons”

Authority to consider whether these periods are acceptable.

Definition “Academic Year”

Authority to consider whether these are the most appropriate start and end dates for an academic year.

Definition “Ancillary Rights”

If the Authority has a particular requirement for a third party to commission a new school (such as in relation to ICT provision or arrangements with an FM Contractor), these need to be spelt out in the Authority’s Requirements.

Definition “Asbestos Survey”

For refurbishment projects and if appropriate, projects that include demolition activities, the Authority needs to commission asbestos management surveys and attach the same to the Design and Build Contract at Schedule 23 . The Authority must ensure the surveyor enters into a collateral warranty with the Contractor, so that the Contractor can rely on the performance of the surveyor in carrying out the asbestos survey. The Authority should ensure that the surveyor’s appointment provides for the procurement of third party warranties as may be required.

Definition “Authority’s Default”

Consider whether the 20 day period is acceptable.

Definition “Authority Related Party”

Item (iv) should be included if there is a VA School or Academy being procured under a Development Agreement which will require novation of the Design and Build Contract.

Definition “Contractor’s Margin”

The Framework Agreement will set out any Contractor’s Margin which needs to be inserted at Schedule 9, together with details of the Contractor’s Margin Payment Profile which may be on a monthly or stage payment basis.  Note that the payment of the Contractor’s Margin is subject to the retention provisions, as detailed in clause 16.  (Payment will vary depending on whether the Lump Sum or Target Cost Option is used).

Definition “Decant Protocol”

Schedule 17 is available for the Authority to set out it’s decant protocol.  There is an example protocol in Schedule 17 but the Authority should draft this on a school specific basis.

Definition “Disclosed Data”

The Authority to ascertain whether or not a data room is being used and amend as appropriate. Where an electronic data room is used, details should be entered in the appropriate square brackets.

Definition “FM Contractor(s)”

The Design and Build Contracts recognise that the FM Contractor is likely to be appointed either by the Authority or the Academy Trust (where an Academy is being procured) or the Governing Body of a VA School (where a VA School is being procured) It is likely that the FM Contractor will require rights of access under clause 3.9 so details should be incorporated into the Construction Programme.

Definition “Long Stop Date”

The Authority should give consideration to the Long Stop Date but the period should be at least half the length of the anticipated construction period (calculated to the nearest month).

Definition “Principal Building Sub-Contractor”

This list should contain all those sub-contract packages in respect of which collated warranties will be required.  The footnote contains an indicative list but careful consideration should be given to the packages.

Definition “Professional Team”

The Authority needs to insert any other Consultants which may be involved and employed by the Contractor, such as fire engineers, landscape architects etc.

Definition “Term”

EFA have assumed a three term year.  Any differences must be made clear to the Contractor and included in the drafting.

Clause 2.2 - Disclosure and Barring Service

This provision can be deleted if no part of the Works qualifies as Sensitive Works.

Clause 3.1 – Authority’s Representative

The Authority’s Representative should be a technically qualified person with construction background knowledge in contract administration and consideration should be given by the Authority to engage third party consultants to carry out this role.

Clause 3.2 – Representative of the Contractor

The key contact from the Contractor should be named here.

Clause 3.4 – Rights of FM Contractors and ICT Contractors

This provision can be deleted if no rights of access are required by the Authority for those third party contractors.

Clause 4.1 – Warranty by Authority

The Authority warrants title as set out in Schedule 15.  The Authority warrants title to the Contractor and any omissions or inaccuracies will be a Compensation Event in favour of the Contractor.  If the Authority is constructing a school on behalf of a VA school, then an appropriate indemnity in relation to title needs to be sought from the VA school.

Clause 4.4 – Contractor’s Due Diligence

If a Contractor is to be given responsibility for the risk items set out in clause 4.4, adequate access for surveys must be made available.  The value of environmental warranties and indemnities should be reviewed on a project specific basis.

Clause 5.1 – Contractor’s Obligation to Carry Out the Works

The Authority should ensure that detailed testing and commissioning programmes are incorporated within the Authority’s Requirements and met by the Contractor’s Proposals.

Clause 5.6 – Consents and Planning Approval

It is entirely feasible that the Authority may be obliged to obtain consents or satisfy certain conditions within an existing planning permission that the Contractor cannot satisfy (eg because only the Authority as landowner can procure certain consents) and separate schedules should be prepared detailing those items.

It is also possible that, due to tight procurement timetables, the Works may have to commence within the judicial review period of a planning permission. Where this is the case clause 5.6B should also be included within the Design and Build Contract. The Authority should consider how long it would be possible to allow the Works to remain suspended pending any such challenge.

Clause 5.7 – Fire Folder

Only relevant to the extent that the Regulatory Reform (Fire Safety) Order 2005 (SI 2005/1541).are applicable to the works once completed.

Clause 7 – The Sites

The provisions of clause 7 need addressing to properly allocate risks.  The Authority should bear any additional costs arising out of unforeseen conditions in areas where the Contractor cannot investigate and which cannot reasonably be identified by the Contractor, these areas need to be clearly identified in the agreement including by plan to clearly show the extent to which the Authority takes the risk for such unforeseen conditions.

Clause 8.2 – Asbestos Liability

This clause will only be appropriate where buildings are being demolished or refurbished.

Clause 10.3 – Minimising Disruption

Wording in square brackets to be used on phased schools.

Clause 10.6 – Decanting

This clause is only relevant if the Contractor is carrying out the decant and if that is the case, a specifically drafted protocol should be incorporated at Schedule 17.

Clause 10.7 – Induction

This clause to be incorporated to the extent that the Contractor will provide induction seminars/workshops for teachers, staff and students.

Clause 15.1 – Variations

There are limits on the ability for the Authority to request a change.  The Authority is to consider which of the exclusions are appropriate.

Clause 15.6 – Disputes

Authorities should give consideration to the risk management of potential disputes and how such disputes are defined.

Clause 16 – Payment

Clause 16.2.3 of the Design and Build Contract – Lump Sum Option provides an option that the Authority’s Representative cannot certify a milestone is complete unless and until all preceding milestones have been completed.  This may not be the case where works are proceeding in unconnected areas at a different rate.

Clause 16.11 – Final Statement and Repayment

The Contractor must provide EFA standard costs proformas, as identified on the Education Funding Agency website in accordance with clause 16.11 of the Design and Build Contract – Lump Sum.

Clause 21 – Provision of Planned Maintenance Programme

Authority to consider whether relevant in relation to refurbishment of part of a school.

Clause 22.2 – Dates on which Completion Dates May Occur

This provision allows for the Authority to insist on handover only on given term or half term dates but these provisions may not be relevant in every case.

Clause 22.6 – Rectification of Snagging Items

There is a contractual 20 business day requirement for rectifying snagging items but the Authority may agree to waive this in relation to long lead in items.

Clause 24 – Alternative A/Alternative B – Liquidated Damages and Provision of Temporary Accommodation

There are two alternative options here for the Authority to decide on.  The Authority can decide to take liquidated damages for failure on the part of the Contractor to complete on time or alternatively, require the Contractor to make temporary accommodation available.  The liquidated damages rate should be a genuine pre estimate of the likely loss to be suffered by the school in the event of a delay in completion.  If alternative accommodation is required, then details of the relevant distance from the relevant existing school needs to be inserted at 24.4.2.

Clause 25 – Insurance

The whole of the insurance provisions in clause 25 need to be considered by reference to market availability at the relevant time.  Project specific requirements must also be dealt with here, eg shared site.

Clause 25.10 – Professional Indemnity Insurance

Guide levels of PI cover have been set.  For Schemes with a contract value of less than £10 million, PI insurance in the sum of £5 million will be required.  Where the contract value exceeds £10 million, PI insurance in the minimum sum of £10 million will be required from the Contractor.  The Authority must decide on appropriate levels of PI cover for the Professional Team and Principal Building Sub-Contractors.

Clause 26.2 – Obligations re Reinstatement and Insurance

Relevant amount to be inserted showing excess.

Clause 27 – Collateral Warranties, Performance Bond and Parent Company Guarantee

This clause sets out in detail who is required to give collateral warranties and when they must be entered into. It should be noted that the provision of such collateral warranties is a completion requirement, in accordance with Schedule 8, and as such the Contractor should produce all collateral warranties prior to the final Date for Completion. There are obligations on the Contractor to enter into collateral warranties in favour of the Authority or a third party at the Authority’s direction.  The Authority would require warranties to, for example, VA Governing Bodies and to Academy Trusts.  Warranties should be made available to these third parties, notwithstanding later novation of the Design and Build Contract. It should be noted that where collateral warranties are provided in favour of a party who will be the beneficiary of the novation of the Design and Build Contract, then such collateral warranties shall terminate once novation takes place.

The Authority will require a collateral warranty from the Contractor on novation of the Design and Build Contract to protect it in circumstances where the long lease to the VA Governing Body or Academy Trust is forfeited.

The Contractor is also required to procure collateral warranties from its Principle Building Sub-Contractors in favour of the Authority and third parties.  This is likely to relate to major design elements, such as piling steelwork, cladding, lifts etc. which should be listed in the definition.

The Contractor is required to procure collateral warranties from the Professional Team in favour of the Authority and third parties.

Clause 27 – Performance Bond

Authorities need to give consideration as to whether or not a bond is required.  If so, a decision must be taken as to the bond sum (normally 10% of the contract sum) and the date of release of the bond (usually on the completion of the works).  Authorities may also consider a reducing bond in the event that works are carried out using sectional completion.  It is not intended that the bond be “on demand”, rather that it will follow the default bond model promulgated by the Association of British Insurers.  A draft form of bond is contained at Schedule 14. The Authority should note that it will be responsible for and shall bear the cost charged by the Contractor of providing the bond and will not be permitted to rely on the capital funding envelope for the Scheme for meet the cost of the bond.

Clause 39.7.4 – Freedom of Information

The Authority needs to give consideration as to how long it requires a Contractor to retain information for disclosure.

Clause 42 – Notices

Full details of the Contractor and Authority’s name, address and fax numbers needs to be incorporated, as does that of the Contractor’s and Authority’s Representatives.

Clause 51 – Limitation on Liability

In order to reflect market conditions, each of the design build contracts contains an aggregate cap on liability which needs completing in clause 50.1.  This should be expressed as a fixed sum, equating to 150% of the Contract Sum and the Contractor’s Margin, as detailed in Schedule 9.  The Authority should note that there are certain exclusions to the cap detailed in clause 50.2.

Schedule 1 – The Authority’s Requirements

The Authority’s Requirements should be worked up with the Authority’s Representative, broadly in line with EFA standard output specification – see EFA website.

Schedule 2 – The Contractor’s Proposals

The Contractor’s Proposals should meet the Authority’s Requirements and have been thoroughly interrogated by the Authority’s Representative.

Schedule 3 – Details of School

In Part 1, the Authority should detail its Existing School premises which are the subject matter of the contract.  Part 2 details New Schools to be constructed (as defined).

Schedule 4 – The Construction Programme

To be agreed with the Contractor and incorporated here.

Schedule 5 – The Site Plan(s)

Relevant plans for the school to be incorporated here showing the Works area with details of how the Site boundaries change during a phased construction process (if relevant).

Schedule 6 – Review Procedure

This is a procedure for design development during construction.  Consideration needs to be given to the lists of reviewable design data under paragraph 7.

Schedule 7 – The Date or Dates for Completion

Parts 1 and 2 set out the dates for completion and start on site dates for the school and/or part of the Works.

Schedule 8 – Completion Requirements

This is the list of pre-conditions which must be achieved by the Contractor before completion can be certified.  Note that all testing and commissioning certificates must be provided and all collateral warranties and guarantees be in place and that the Health and Safety file is completed and provided to the Authority as part of the list of pre-conditions.  There is provision within the footnotes for dealing with completion of landscaping outside the planting season.

Schedule 9 – Payment Provisions

Here the Authority will detail the Contract Sum, the Contractor’s Margin, the Milestones for Payment (milestone value and cumulative value) for the Lump Sum version of the contract, the Interest Rate and the Payment Profile for the payment of the Contractor’s Margin.  A detailed breakdown of the Milestones against which certification will take place must be included where the Lump Sum version of the Design and Build Contract is being used.

Schedule 10 – Minimum Information to be included in the Planned Maintenance Programme

Here the Authority will detail its minimum requirements for a planned maintenance programme which the Contractor is required to provide pursuant to clause 21.  The Authority should liaise with its FM Contractor in preparing this Schedule (if FM Contractor is already appointed).

Schedule 11 – Prohibited Materials

Refer to Part 2 of the Authority’s Requirements.

Schedule 12 – Insurances

The insurance schedule presupposes a project specific policy being taken out by the Contractor although the Authority, in its absolute discretion, may permit the Contractor to use an existing group policy. It is accepted that changes required by the use of a group policy may be required but the risk to the Authority, depending on the specific details, should not increase from the position where a project specific policy is being used. All amendments should be approved by the Authority’s insurance adviser.

Schedule 13 – Forms of Collateral Warranty

There are separate forms of collateral warranty to cover the various warranties and beneficiaries detailed in clause 27.1.  Where the Authority is procuring an Academy the Authority can call for a collateral warranty from the Contractor at the point of novation of the Design and Build Contract.  Similarly where the Authority retains a proprietary interest in part of the Site of an Academy a warranty can be obtained on novation.

Schedule 14 – Performance Bond

See earlier notes on bonding.

Schedule 15 – Warranted Title Matters

This Schedule sets out the level and detail of title information that must be supplied by the Authority to the Contractor and against which the Authority gives a warranty.  The information breaks down into four parts:

Part 1 – Title warranties.

Part 2 – Disclosed title matters (official copy entries/epitome of title).

Part 3 – Replies to enquiries (based on standard pre contract enquiries).

Part 4 – Disclosed searches.

The Authority should appreciate that a high level of title information needs to be provided to the Contractor and the Authority needs to make this information available at the FS stage

Schedule 16 – Equality Requirements

These are general provisions which the parties are required to comply with

Schedule 17 – Decant Protocol

A draft template to be revised and agreed on a Scheme specific basis where the Authority wished the Contractor to carry out decant.

Schedule 18 – Commercially Sensitive Information

Here the Authority and the Contractor will list out commercially sensitive material and the period for which it should be held.

Schedule 19 – Authority’s Policies

To be inserted by the Authority but must include the OCG Fair Payment Guide.

Schedule 20 – Authority Planning Conditions

It is often the case that a number of the conditions to the planning consent for the Scheme can only be obtained, carried out or implemented by the Authority, with support from the Contractor.  This Schedule should list out those conditions by either marking up the planning consent itself or separately listing the Authority’s conditions.

Schedule 21 – Deed of Novation

This allows for the Design and Build Contract to be novated to an Academy to sit with any land transfer or leasing arrangements under the Development Agreement.  The Deed of Novation is not in substitution for collateral warranties, which should be made available to an Academy in any event.

Schedule 22 – Parent Company Guarantee

To be provided by the Contractor’s Parent as stated in the Contractors Framework Agreement between EFA and the Contractor.  Advice should be sought from EFA as to the appropriate entity pre-qualified by EFA under the Contractors Framework to provide the Parent Company Guarantee.  There may be circumstances where Panel Members do not have a Parent and EFA will advise of this.  In these circumstances, appropriate amendments need to be made to the Design and Build Contract as detailed in the footnotes.

Schedule 23 – Asbestos Survey[s]

Here the Authority will include copies of any asbestos surveys procured in relation to the Scheme.

Schedule 24 – Building Survey[s]

Here the Authority will append any building surveys procured in relation to the Scheme.

Schedule 25 – Site Surveys[s]

Here the Authority will append any site surveys procured in relation to the Scheme which should include but not be limited to Ground Investigation Surveys.

Schedule 26 – Excluded Defects

If it is agreed commercially between the Authority and the Contractor that the Authority will retain responsibility for certain defects they shall be set out in Schedule 26.

Schedule 27 – Authority Necessary Consents

In the event there are any Necessary Consents (ie wayleave agreements) which only the Authority as a matter of law can obtain they will be set out in Schedule 27 and the provisions of clause 5.6A and Schedule 27 will apply.

Schedule 28 – Project Bank Account

In the event the project bank account is required on a Scheme the parties will comply with the provisions of clause 16A and Schedule 28.

Schedule 29 – BIM Protocol

In the event the Contractor utilises BIM when carrying out the design of the Works the BIM Protocol shall be used (save for where this information is included in Schedule 1.

Schedule 30 – Key Performance Indicators

The key performance indicators which the Contractor will be expected to comply with will be set out in Schedule 30.

Future Schools Agreement – Summary of Key Points

General Comments and Background

Under the Local Competition procedure set out in the Contractors Framework, the Authority may be procuring a series of school Schemes either with each school having its own separate and defined funding envelope or all schools within an overall funding envelope.  The Local Competition is expected to provide for such Schemes to be procured using one Sample School (against which the Contractor will price and provide design with the Local Competition) with the further Schemes delivered as non-sample schemes.  The Sample School will be delivered under a separate Design and Build Contract entered into pursuant to the Contractors Framework Agreement.

Non-sample schools will be delivered using the Future Schools Agreement.  This agreement provides an option for the Authority to call for the Contractor to produce Future Schools Scheme Proposals which essentially mirror the level of design and pricing information required by the Local Competition under the Contractors Framework for the sample school.

The purpose of the Agreement is to allow the Authority to procure the non-sample schools with the Contractor selected for the Sample School but without the need for the Contractor to design and price both the sample and non-sample schools during the Local Competition. The Future Schools Agreement is expected to be executed at the same time that the Design and Build Contract for the sample school is signed.

Once the Future Schools Agreement has been entered into with the Contractor, the Authority may issue Future Schools Notices under the Future Schools Agreement at any time before the termination of the Framework Agreement.

The Authority is not obliged under the Future Schools Agreement to:

- give any exclusivity to the Contractor in respect of the non-sample schools;

- request any Future Schools Scheme Proposals;

- implement any Future Schools Scheme Proposal (whether approved or not).

The Authority has no liabilities or obligations to the Contractor at any point during the Future Schools Agreement for the costs incurred by the Contractor in preparing any Future Schools Scheme Approval documentation.  The Authority only becomes liable to the Contractor once a Design and Build Contract is entered into for the Future Schools Scheme.

The Future Schools Agreement contains a third party right mechanism to allow a secondary Framework User to operate the Approval process under Schedule 1.

Key Commercial Principles

The Authority needs to familiarise itself with the Future Schools Scheme Approval Procedure set out in Schedule 1 of the Future Schools Agreement.

In broad terms, the Contractor works (at risk) with the Local Authority to analyse and discuss accommodation requirements and decide which Future Schools Schemes the Contractor should submit ahead of the approval procedure commencing proper.

The Contractor is then obliged to submit a Future Schools Scheme Proposal within 6 weeks of receipt of a Future Schools Notice (or such other time as the parties may agree) from the Authority.

The Future Schools Agreement sets out in detail at Schedule 1 the level of information required to be provided by the Contractor within a Future Schools Scheme Proposal, which equates to the level of information submitted at invitation to tender under the Local Competition and in any event, no less than RIBA Level C+.  The Contractor must also provide a fixed price lump sum or target cost for the project, with the price built up strictly in accordance with the pricing schedule under the Contractors Framework Agreement.

The Authority then either approves or rejects the Future Schools Scheme Proposal.  If the Proposal is approved, then the Authority will submit its final business case to EFA, planning consent will be obtained and the Contractor enters into a Design and Build Contract within 14 days of a written request by the Authority.

If the Proposal is rejected, the Contractor has the opportunity to resubmit if required by the Authority.

Any Future Schools Scheme Proposal is valid for a period of one month from the date of submission by the Contractor.

EARLY WORKS AGREEMENT – SUMMARY

The fixed form of Early Works Agreement (EWA) has been developed to work with the Design Build Contracts and must be used by the Framework User where this a requirement for advance works, design or orders to be placed ahead of entering into the Design Build Contract. No other form is acceptable and in particular a letter of intent should not be used. The form of EWA is fixed and should be completed by operating the footnotes and guidance. Works procured under an EWA should be subsumed into the subsequent Design and Build Contract

.

Appendix C

Technical Requirements used during the Contractors Framework ITT conducted by EFA to establish the Contractors Framework

Please see Volume 5 of the ITT issued by EFA in July 2013

Appendix D

Information and Maps for each Sector

Introduction

The attached map provides Framework Users with an indication of the Sector in which they are located with regard to the use of the EFA Contractors Framework. There are 2 Sectors:

- Sector North (shown as Sector 1 on the map) – This comprises the North West, the North East, Yorkshire and the Humber, the East Midlands, and the West Midlands;

- Sector South (shown as Sector 2 on the map) – This comprises the East of England, the South East, the South West, and London.

In the event of any query, Framework Users are advised to contact the EFA Project Director.

The following Contractors have been appointed to the EFA Contractors Framework Panel in the respective Sectors:

| Sector North | Sector South |
| --- | --- |
| Balfour Beatty Group Plc | Balfour Beatty Group Plc |
| BAM Construction Ltd | BAM Construction Ltd |
| Bowmer & Kirkland Ltd | Bowmer & Kirkland Ltd |
| Carillion Construction Ltd | Carillion Construction Ltd |
| Galliford Try Construction Ltd | Galliford Try Construction Ltd |
| Keir | Kier |
| Sir Robert McAlpine | Sir Robert McApline |
| Thomas Vale Construction Plc | Wates Construction Ltd |
| Wates Construction Ltd | Wilmott Dixon Construction Ltd |

Education Funding Agency - Indicative list of locations by Sector / Sub-Region

Sector North

1. North West

- Cumbria

- Lancashire

- Cheshire

- Sefton

- Wirral

- Liverpool

- Knowsley

- St Helens

- Wigan

- Bolton

- Bury

- Rochdale

- Oldham

- Salford

- Trafford

- Manchester

- Stockport

- Tameside

- Blackpool

- Halton

- Warrington

- Blackburn with Darwen

2. North East

- Northumberland

- Durham

- Newcastle upon Tyne

- Gateshead

- North Tyneside

- South Tyneside

- Sunderland

- Hartlepool

- Darlington

- Stockton-on-Tees

- Middlesbrough

- Redcar & Cleveland

3. Yorkshire and The Humber

- North Yorkshire

- Leeds

- Barnsley

- York

- Doncaster

- East Riding of Yorkshire

- Bradford

- Caldergate

- Kirklees

- Sheffield

- Rotherham

- Kingston upon Hull

- North Lincolnshire

- North East Lincolnshire

4. East Midlands

- Lincolnshire

- Nottinghamshire

- Derbyshire

- Leicestershire

- Rutland

- Northamptonshire

- Derby

- Nottingham

- Leicester

5. West Midlands

- Staffordshire

- Shropshire

- Herefordshire

- Worcestershire

- Warwickshire

- Wolverhampton

- Dudley

- Walsall

- Sandwell

- Birmingham

- Solihull

- Coventry

- Stoke

- Telford and Wrekin

Sector South

6. East of England

- Norfolk

- Cambridgeshire

- Hertfordshire

- Suffolk

- Essex

- Peterborough

- Bedfordshire

- Luton

- Thurrock

- Southend on Sea

7. South East

- Oxfordshire

- Hampshire

- Buckinghamshire

- Surrey

- West Sussex

- East Sussex

- Newbury

- Reading

- Wokingham

- Bracknell & Forest

- Windsor & Maidenhead

- Slough

- Isle of Wight

- Southampton

- Portsmouth

- Brighton & Hove

- Medway Towns

- Milton Keynes

8. South West

- Gloucestershire

- Wiltshire

- Somerset

- Devon

- Dorset

- Cornwall

- South Gloucestershire

- Bristol

- Bath & NE Somerset

- North Somerset

- Plymouth

- Torbay

- Poole

- Bournemouth

- Swindon

9. London

- Barking & Dagenham

- Barnet

- Bexley

- Brent

- Bromley

- Camden

- City of London

- City of Westminster

- Croydon

- Ealing

- Enfield

- Greenwich

- Hackney

- Hammersmith & Fulham

- Haringey

- Harrow

- Having

- Hillingdon

- Hounslow

- Islington

- Kingston & Chelsea

- Kingston upon Thames

- Lambeth

- Lewisham

- Merton

- Newham

- Redbridge

- Richmond upon Thames

- Southwark

- Tower Hamlets

- Waltham Forest

- Wandsworth

# Footnotes

The website link may be subject to change.

The process for completing any “gaps” or submitting any derogations to the Design and Build Contract will vary depending on the type of programme the Scheme relates to.  Further information will be available from the EFA PD or the Commercial Manager allocated to that project (if applicable).

# Text boxes

Sector South

Sector North