## Introduction
ENVIRONMENT AGENCY (December 2014)
© Environment Agency copyright and/or database right 2014. All rights reserved |  | This document may be downloaded from gov.uk :- | Programme of flood and coastal risk management projects
Flood and Coastal Erosion Risk Management Programmes of Work for the financial year 2015 to 2016 Consented by Regional Flood & Coastal Committees
There are 12 Regional Flood & Coastal Committees (RFCCs) in England. The Environment Agency must consult with RFCCs about flood and coastal erosion risk management work in their region and take their comments into consideration. RFCCs are required to consent the programme covering their region. RFCCs are composed of a chairperson appointed by the Secretary of State and members appointed by lead local flood authorities, and by the Environment Agency.
You can download a map showing RFCC boundaries from gov.uk :- | Regional Flood and Coastal Committees map
What information is provided on the three tables?
There are three separate tables which provide information on flood and coastal erosion risk management (FCERM) projects at three different stages of development. The three stages of the programme reflect increasing levels of certainty around the development and delivery of individual schemes. The visibility that this provides will enable the construction industry to better support the Environment Agency and its partners in identifying where additional efficiencies or delivery improvements could be introduced.
Projects in the programme are at one of three stages: 1) construction programme, 2) development programme or 3) pipeline programme. Within the first two of these stages there are sub-headings in the programme which further define the status of projects.
1 - Construction programme (coloured green): a - Projects already in construction b - Fully funded projects scheduled to start construction in the coming financial year c - Projects scheduled to start construction in the coming financial year, subject to securing other funding contributions
2 - Development programme (coloured amber): a - Projects in development with full funding packages agreed, expected to start construction in future years, subject to approval of a full business case. b - Projects in development, expected to start construction in future years, subject to approval of a full business case and securing other funding contributions. Please note: in this table columns E - J show pre-construction costs and columns M - P shows indicative construction costs up to March 2021.
3 - Pipeline programme (coloured yellow): The pipeline programme lists project proposals that are likely to qualify for some government funding before 2021 and have been given an indicative allocation. However they have not yet identified sufficient contributions and/or do not have a sufficiently well-developed case to enter the development programme at this stage.
Commitments to specific allocations of central government funding (FCERM Grant in Aid - GiA) to projects will be reviewed at least annually. The amounts payable beyond the 2015 to 2016 financial year will be confirmed and allocated on a project by project basis. Local authority and internal drainage board project payments will be in line with the Department for Communities and Local Government rules for the allocation of funding. For schemes entering the construction programme an indicative funding allocation is made through to completion. Funding may be re-profiled to ensure the overall programme remains affordable and efficient. This will ensure that any unused contingency and efficiencies can be effectively applied to support accelerated delivery of the programme. These programmes are subject to change during the year and projects may be subject to delay (for example through extreme weather events) or brought forward (for example in response to additional funding). New projects not on these lists may also start during the year where for example emergency works are required.
Projects are only introduced into the development programme if they have a prima facie (at first sight appear to have a) case for government support in the construction phase. Confirmation of the timing and amount of grant in aid for the construction phase of a scheme is subject to assurance and approvals. As a general rule the maximum funding available for the development phase of a project is 20% of the eligible total grant in aid for that scheme.
Projects in the pipeline programme may move into the development, and potentially construction, programme at any time subject to meeting the normal criteria. The pipeline projects will be regularly reviewed to take full advantage of any opportunities to accelerate their delivery.
The projects listed aim to reduce the risk of flooding from rivers, sea, groundwater or surface water and/or to reduce the risks from coastal erosion. They do not include work to reduce the risks of flooding from sewers which is funded exclusively by water companies.
The projects listed are those that contain an indicative allocation of FCERM grant in aid funding within the 2015 to 2021 period. For further information around any potential projects that will be funded purely from third party funding (or projects that are planned for after 2021), please contact your local Area Flood and Coastal Risk Manager.
All cost information is provided in £k.
The project information in these programmes has been provided by the Environment Agency, local authorities, internal drainage boards, water companies and highways authorities, who all have responsibilities for flood and coastal erosion risk management in England. These programmes are made up of the programmes consented by the RFCCs at their October 2014 meetings. All information is correct as at October 2014. The published cost figures are based on the current most likely costs at 2014 prices. The final figures for costs, GiA contributions and other funding contributions will be updated as the projects progress.
How can I find out about a project near me?
The tables are ordered alphabetically by Regional Flood and Coastal Committee (RFCC), risk management authority (RMA) and then project name. The first four columns of the tables show the project name, risk management authority, RFCC name and project location. On each table, by first finding the RFCC and RMA of interest, you can then scan down the list of projects.
You can contact your local Environment Agency office for more information on any of these projects by calling 03708 506 506 or by email to: |  |  | enquiries@environment-agency.gov.uk
You can also use the interactive map on gov.uk to search for projects by location or postcode :- Interactive map of projects
Understanding the information provided
These tables are used for a wide range of purposes. A brief explanation has been provided below including links to where you can find out more information on how funding is allocated and how the outcomes of the projects are assessed.
Risk Management Authority - This column specifies which risk management authority is leading the project. They are either a local authority (LA), internal drainage board (IDB) or the Environment Agency (EA). Water companies and highways authorities are also risk management authorities and may lead projects in the programme in the future.
Outcomes and funding The numbers of households with a better level of protection are initially estimated using local engineering knowledge and experience from previous flooding. As projects progress in their development the estimate is refined using modelled data. The tables show, for each project, the number of households that are expected to have a better level of protection within the next 6 years, and from the project overall once it is complete.
Where 'other funding' is listed against projects these contributions will need to be forthcoming to enable the projects to continue to progress.
More information on how outcomes of projects are assessed and how grant in aid funding for projects is calculated can be found on gov.uk :- |  |  | Partnership Funding and Outcome measures
Reference: LIT_10059

## Construction Programme
Flood and Coastal Erosion Risk Management (FCERM) Construction Programme - England
[5 empty] | Flood and Coastal Erosion Risk Management Grant in Aid Funding |  |  | Project Total |  |  |  | Households with a better level of protection by March 2021 |  | Total households with a better level of protection when schemes are complete
Project Name | Risk Management Authority | Regional Flood and Coastal Committee (RFCC) | Location | Estimated Total Project Cost (£k) | Funding allocated for 2015/16 (£k) | INDICATIVE to 2021 (£k) | INDICATIVE from 2021 (£k) | Local Levy (£k) | Public (incl. Internal Drainage Board Precept, £k) | Private (£k) | Further Required (£k) | from flooding | from coastal erosion | from flooding | from coastal erosion | Economic benefits (Net Present Value, £k) | Other major benefits / reason for the scheme | NPN
a. Projects already in construction (started before April 2015)
Gough Way Culvert Repairs | Environment Agency | Anglian Central | Cambridge | 534 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 0 |  | ACC451E/000A/599A
Ouse Washes Habitat Creation | Environment Agency | Anglian Central | 5km strip adjacent to Ouse Washes | 17715.2785 | 1846.2 | 718.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ACC451E/000A/016A
Pix Brook flood alleviation | Bedfordshire and River Ivel Internal Drainage Board | Anglian Central | Arlesey and Stotfold, Pix Brook | 298.967 | 156 | 4 | 0 | 50 | 53.5 | 0 | 0 | 75 | 0 | 75 | 0 | 2981 |  | ACC451I/000A/207A
Cherry Hinton Estate, Cambridge, Surface Water Flood Alleviation | Cambridgeshire County Council | Anglian Central | Cherry Hinton Estate, Cambridge | 288 | 90 | 0 | 0 | 126.5 | 20 | 0 | 0 | 30 | 0 | 30 | 0 | 0.5 |  | ACC451F/000A/002A
Anglian Regional Habitat Creation Programme (ARHCP) | Environment Agency | Anglian Eastern | various | 11548.1337 | 198.47 | 2443.18 | 7400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AEO000E/000A/064A
Biodiversity Action Plan Habitat Creation | Environment Agency | Anglian Eastern | Fingringhoe | 4747.172 | 265 | 2405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3930 |  | AEO000E/000A/043A
Chelmsford Flood Alleviation | Environment Agency | Anglian Eastern | Chelmsford, Essex | 13266.721 | 1433.181 | 315 | 0 | 2535.378 | 6500 | 0 | 0 | 370 | 0 | 495 | 0 | 23640 |  | AEC505E/004A/001A
Easton Broad Flood Management | Environment Agency | Anglian Eastern | Easton Broad, Suffolk | 2431.033 | 342.18 | 1035.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AES503E/008A/001B
Eccles to Winterton Coastal Management Stage 2 | Environment Agency | Anglian Eastern | Happisburgh to Winterton, Norfolk | 24552.9 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 |  | AES502E/001A/002A
Great Yarmouth Tidal Defences 2013 to 2016 | Environment Agency | Anglian Eastern | Great Yarmouth | 27870.1235 | 8608.391 | 3945.379 | 0 | 2621.3465 | 0 | 125 | 0 | 295 | 0 | 520 | 0 | 760367 |  | AES502E/002A/002B
Hickling Reedbed Creation | Environment Agency | Anglian Eastern | Potter Heigham and Hickling | 1491.1702 | 329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AEO000E/000A/323A
Ipswich Flood Defence Management Strategy: Tidal Barrier | Environment Agency | Anglian Eastern | River Orwell, Ipswich, Suffolk | 41084.275 | 7691.199 | 8557.806 | 0 | 0 | 6600 | 1090 | 0 | 1010 | 0 | 1010 | 0 | 293964.81 |  | AES503E/006A/004A
Methwold Reedbed Creation | Environment Agency | Anglian Eastern | Methwold | 950.6787 | 158 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AEO000E/000A/357A
Needham Market flood risk management | Environment Agency | Anglian Eastern | Needham Market | 456 | 190 | 0 | 0 | 26 | 0 | 0 | 0 | 140 | 0 | 140 | 0 | 4851.426 |  | AEO000E/000A/358A
Scarhouse Dyke - Conveyance | Environment Agency | Anglian Eastern | Scarhouse Dyke, Canvey Island | 235.25 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 1796.1 |  | AEC506E/000A/007A
Tilbury Barrier - Dual Function Lock Gate | Environment Agency | Anglian Eastern | Tilbury, Essex | 15000 | 12500 | 0 | 0 | 500 | 0 | 0 | 0 | 3270 | 0 | 3270 | 0 | 185000 |  | AES504E/005A/017A
Cromer Coast Protection | North Norfolk District Council | Anglian Eastern | Cromer | 8202 | 135 | 1946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 0 |  | AES502C/000A/004A
Ipswich - Stone Lodge Park Sustainable Urban Drainage | Suffolk County Council | Anglian Eastern | Stone Lodge Park off Hawthorne Drive, Ipswich | 30 | 15 | 0 | 0 | 0 | 5 | 0 | 0 | 10 | 0 | 10 | 0 | 774 |  | AEC504F/000A/002A
Clacton Holland on Sea Management Phase 1 (Zones B and C) | Tendring District Council | Anglian Eastern | Coast | 36106 | 18615 | 0 | 0 | 75 | 8000 | 0 | 0 | 0 | 1575 | 0 | 1575 | 209559 |  | AES504C/000A/008A
Barnby North Cove Pumping Station Reorganisation | Waveney, Lower Yare & Lothingland Internal Drainage Board | Anglian Eastern | Castle, Barnby and Share Marshes near Lowestoft | 356 | 102 | 0 | 0 | 194 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AEO000E/000A/394A
Grimsby Flood Alleviation Scheme (Fluvial) | Environment Agency | Anglian Northern | Grimsby | 2705.656 | 1.053 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ANC401E/000A/018A
Horncastle Improvements | Environment Agency | Anglian Northern | Horncastle | 8265 | 601 | 0 | 0 | 3141 | 3800 | 0 | 0 | 95 | 0 | 120 | 0 | 24518.0024 |  | ANC403E/000A/058A
Humber - Donna Nook | Environment Agency | Anglian Northern | Louth | 7987 | 595 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | YOS399E/001A/006A
Humber Grimsby Docks | Environment Agency | Anglian Northern | Grimsby | 19791.414 | 1500 | 0 | 0 | 0 | 189 | 0 | 0 | 12180 | 0 | 15915 | 0 | 348872 |  | ANS399E/001A/020A
Lincshore 2010 - 2015 | Environment Agency | Anglian Northern | Mablethorpe to Skegness | 66236.9 | 6650 | 19350 | 0 | 0 | 8250 | 0 | 0 | 10930 | 0 | 31210 | 0 | 1527977.8002 |  | ANS401E/001B/001A
Louth Improvements | Environment Agency | Anglian Northern | Louth | 5823.5 | 241 | 0 | 0 | 0 | 4538.5 | 0 | 0 | 115 | 0 | 115 | 0 | 22930.8612 |  | ANC402E/000A/027A
Maud Foster Sluice Apron Refurbishment | Environment Agency | Anglian Northern | Boston, River Witham | 653 | 375 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3478 |  | ANC403E/000A/064A
Northern Area Reservoirs Statutory Obligations | Environment Agency | Anglian Northern | Northampton and other FSR's | 1355 | 400 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25215 |  | ANO000E/000A/212A
Reservoirs: Whittlesey Washes Probable Maximum Flow | Environment Agency | Anglian Northern | Whittlesey | 17411.075 | 3895 | 120 | 0 | 2573.095 | 529.66 | 0 | 0 | 0 | 0 | 0 | 0 | 142293.365 |  | ANC405E/000A/048A
Sempringham Fen Pumping Station Refurbishment | Black Sluice Internal Drainage Board | Anglian Northern | Boston | 81 | 40.5 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 1025.438 |  | ANC403I/005A/028A
Lincoln - Stamp End: Flood Risk and Drainage Improvement | Lincolnshire County Council | Anglian Northern | Lincoln | 750 | 80 | 97 | 0 | 0 | 152 | 185 | 0 | 85 | 0 | 85 | 0 | 2197.962 |  | ANC403F/000A/005A
Washingborough: Flood Risk and Drainage Improvement | Lincolnshire County Council | Anglian Northern | Washingborough | 478 | 104.1 | 0 | 0 | 0 | 248 | 0 | 0 | 40 | 0 | 40 | 0 | 1404 |  | ANC403F/000A/004A
Pyewipe Pumping Station Refurbishment | Upper Witham Internal Drainage Board | Anglian Northern | South bank Fossdyke | 118.25 | 0 | 12.8 | 0 | 0 | 27.9875 | 67 | 0 | 0 | 0 | 0 | 0 | 0 |  | ANC403I/002A/010A
Telemetry Upgrade Upper Witham | Upper Witham Internal Drainage Board | Anglian Northern | Lincoln Area and other areas | 69.6715 | 6.795 | 0 | 0 | 0 | 38.3193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ANC403I/002A/002A
Culverted Watercourse Re-lining | Welland & Deepings Internal Drainage Board | Anglian Northern | Spalding, Lincolnshire - Pennygate Drain | 500 | 100 | 300 | 0 | 0 | 100 | 0 | 0 | 40 | 0 | 40 | 0 | 9659.693 |  | ANC404I/000A/006A
Hobhole Refurbishment Programme | Witham 4th District Internal Drainage Board | Anglian Northern | Coastal Outfall | 697 | 149 | 0 | 0 | 0 | 0 | 42 | 0 | 130 | 0 | 1380 | 0 | 269864.5059 |  | ANC403I/002A/034A
Daniels Brook | Environment Agency | English Severn and Wye | Gloucester | 946 | 21.595 | 67.686 | 0 | 350.719 | 500 | 0 | 0 | 0 | 0 | 180 | 0 | 7166 |  | SNC001E/001A/018A
River Severn, Minsterworth Flood Alleviation Erosion Protection | Environment Agency | English Severn and Wye | Minsterworth | 252 | 0 | 172 | 0 | 80 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 2663 |  | SNC001E/000A/049A
The Grove, Minsterley, Shropshire, Flood Alleviation | Shropshire Council | English Severn and Wye | Minsterley, Shrewsbury | 93 | 0 | 32 | 0 | 34 | 27 | 0 | 0 | 0 | 0 | 10 | 0 | 237 |  | SNC001F/000A/028A
North East Bomere Heath, Shropshire, Flood Alleviation | Shropshire Council | English Severn and Wye | Bomere Heath | 105 | 0 | 10 | 0 | 0 | 20 | 75 | 0 | 5 | 0 | 5 | 0 | 47 |  | SNC001F/000A/032A
Barbourne Brook Culvert Improvements | Worcester City | English Severn and Wye | Perdiswell, Worcester | 475 | 95 | 0 | 0 | 315 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 1313 |  | SNC001E/000A/320A
Wick, Worcestershire, Property Level Protection | Wychavon District | English Severn and Wye | Wick, Pershore | 67 | 38 | 0 | 0 | 21 | 8 | 0 | 0 | 10 | 0 | 10 | 0 | 294 |  | SNC001F/000A/046A
Crossens Pumping Station Refurbishment | Environment Agency | North West | Banks, Southport | 4889 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 660 | 0 | 109613 |  | NWC001E/001A/005A
Croston Risk Management, River Yarrow | Environment Agency | North West | Croston, Lancashire | 7309 | 2650 | 0 | 0 | 0 | 3350 | 0 | 0 | 345 | 0 | 345 | 0 | 57695 |  | NWC003E/001A/002A
Dallam Brook, Warrington | Environment Agency | North West | Dallam, Warrington | 1463 | 0 | 1395 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 6773 |  | NWC008E/002A/006A
Fisher Beck, Ambleside | Environment Agency | North West | Ambleside, Cumbria | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 640 |  | NWC006E/000A/014A
Jacks Key Reservoir Improvements, Darwen | Environment Agency | North West | Darwen , Lancashire | 1388 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 1015 | 0 | 1015 | 0 | 78965 |  | NWC009E/000A/017A
Kendal, River Kent | Environment Agency | North West | Kendal, Cumbria. | 3950 | 0 | 250 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 15065 |  | NWC006E/000A/001A
Keswick flood Defences Post Construction | Environment Agency | North West | River Greta Keswick | 5851 | 0 | 5 | 10 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 38157 |  | NWC002E/001A/001A
Leigh East Flood Risk Managment | Environment Agency | North West | Bedford Bk, Greater Manchester | 2857 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 65439 |  | NWC008E/003A/003A
Mill Brook, Tattenhall | Environment Agency | North West | Chester, England | 63 | 10 | 35 | 0 | 18 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 188 |  | NWC014E/000A/003A
Northwich Town Centre | Environment Agency | North West | Northwich, Cheshire | 7029 | 3814 | 77 | 0 | 0 | 500 | 0 | 0 | 290 | 0 | 290 | 0 | 46072 |  | NWC012E/002A/001A
Property Level Protection Programme | Environment Agency | North West | Various sites across Greater Manchester & Cheshire | 289 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 2775 |  | NWO001E/000A/006A
River Douglas, Wigan Flood Alleviation | Environment Agency | North West | River Douglas, Wigan, Greater Manchester | 11605 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60055 |  | NWC003E/001A/001A
River Mersey Warrington Flood Risk Management | Environment Agency | North West | Warrington, Cheshire | 23473 | 1300 | 1400 | 0 | 0 | 1800 | 2600 | 0 | 825 | 0 | 2325 | 0 | 112527 |  | NWC008E/002A/001A
Salford Flood Alleviation Improvements | Environment Agency | North West | Kersal/Broughton, Manchester | 8766 | 2078 | 588 | 0 | 0 | 2000 | 0 | 0 | 1800 | 0 | 1800 | 0 | 104800 |  | NWC005E/003A/001A
Sankey Bridges, Warrington Flood Risk Management | Environment Agency | North West | Sankey Bridges & Dallam areas of Warrington | 3645 | 0 | 3260 | 0 | 359 | 0 | 0 | 0 | 475 | 0 | 475 | 0 | 24300 |  | NWC008E/002A/003A
Skirting Beck, Egremont | Environment Agency | North West | Egremont, Cumbria | 3898 | 2400 | 200 | 0 | 120 | 600 | 400 | 0 | 295 | 0 | 295 | 0 | 58475 |  | NWC010E/000A/003A
Ulverston Flood Risk Management | Environment Agency | North West | Ulverston, Cumbria. | 4793 | 2000 | 0 | 0 | 80 | 0 | 0 | 0 | 505 | 0 | 505 | 0 | 60317 |  | NWC006E/000A/002A
Upper & Middle Wyre Flood Risk Management Assets | Environment Agency | North West | St Michaels on Wyre, Lancashire | 941 | 0 | 870 | 0 | 50 | 0 | 0 | 0 | 310 | 0 | 310 | 0 | 17400 |  | NWC013E/000A/009A
Waterfall, Blackburn Flood Risk Management | Environment Agency | North West | Darwen, Lancashire | 2825 | 1844 | 0 | 0 | 510 | 0 | 0 | 0 | 55 | 0 | 55 | 0 | 14133 |  | NWC009E/002A/003A
Anchorsholme Coast Protection | Blackpool Council | North West | Blackpool | 22757 | 6063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4415 | 400 | 209587 |  | NWS002C/000A/002B
A530 Bradfield Green, Crewe | Cheshire East Council | North West | Crewe, Cheshire | 300 | 135 | 0 | 0 | 140 | 25 | 0 | 0 | 15 | 0 | 15 | 0 | 1032 |  | NWC012F/000A/027A
Tinkers Clough, Princess Street, Bollington | Cheshire East Council | North West | Bollington, Cheshire | 250 | 80 | 0 | 0 | 170 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 55 |  | NWC012F/000A/025A
Morecambe Wave Reflection Wall Phases 1 - 3 | Lancaster City Council | North West | Morecambe, Lancashire | 8635 | 820 | 6955 | 0 | 0 | 0 | 0 | 0 | 8125 | 0 | 8125 | 0 | 124063 |  | NWC007F/000A/001A
Hidden Watercourses Appraisal | Manchester City Council | North West | Manchester | 911 | 125 | 250 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 3533.662 |  | NWC005F/000A/016A
Crosby Marine Lake to Formby Point Strategy Delivery Programme | Sefton Council | North West | Waterloo, Crosby, Blundellsands,Hightown, Sefton Coast SSSI, SPA, RAMSAR,SAC | 2724 | 0 | 60 | 1444 | 0 | 1000 | 0 | 0 | 0 | 0 | 200 | 0 | 2850 |  | NWS001C/000A/008B
Warrington Road/ Mill Lane, St Helens | St Helens Council | North West | St Helens | 54 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 127.701 |  | NWC008F/000A/086A
West End Road, St Helens | St Helens Council | North West | St Helens, Blackbrook | 212 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 308 |  | NWC008F/000A/087A
Rossall Coastal Defence Improvement | Wyre Borough Council | North West | Fylde coast Lancashire, Rossall Hospital to Fleetwood Golf Course | 94165 | 18750 | 28782 | 30865 | 0 | 100 | 25 | 0 | 5625 | 0 | 7495 | 0 | 996751 |  | NWC013F/000A/001A
Browns Bridge (Lustrum Beck) | Environment Agency | Northumbria | Stockton on Tees: Hartburn, Oxbridge, Newton | 3009.875 | 828 | 480.802 | 0 | 872.975 | 460 | 0 | 0 | 130 | 0 | 150 | 0 | 3905 |  | NOC306E/000A/031A
Brunton Park, Ouseburn Flood Alleviation | Environment Agency | Northumbria | Brunton Park, Ouseburn | 1118.2 | 153.2 | 0 | 0 | 540 | 0 | 100 | 0 | 75 | 0 | 75 | 0 | 6247.5 |  | NOC304E/000A/021A
Greatham North | Environment Agency | Northumbria | Hartlepool | 6053.0935 | 51.7491 | 191.1814 | 39.521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NOC306E/001A/003A
Neasham Village Flood Protection & Reservoir Safety | Environment Agency | Northumbria | Neasham, nr Darlington, River Tees | 3748.185 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 838 |  | NOC306E/000A/009A
Port Clarence and Greatham South Flood Alleviation | Environment Agency | Northumbria | Middlesborough | 15333.843 | 5000 | 3069.54 | 0 | 0 | 0 | 0 | 5930 | 350 | 0 | 350 | 0 | 504277.603 |  | NOC306E/001A/001A
Spring Gardens Urgent Works | Environment Agency | Northumbria | Spring Gardens, nr West Auckland, River Gaunless | 1315.549 | 20 | 10.712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 13562 |  | NOC305E/000A/016A
Witton Gilbert Flood Alleviation | Durham County Council | Northumbria | Witton Gilbert | 1028 | 143 | 0 | 0 | 357.718 | 200 | 50 | 0 | 50 | 0 | 50 | 0 | 475 |  | NOC305F/000A/006A
Saltwell Road South | Gateshead Council | Northumbria | Chowdene, Gateshead | 85 | 0 | 42 | 0 | 23 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 710 |  | NOC304F/000A/045A
Headland Walls and Blocksands, Hartlepool | Hartlepool Borough Council | Northumbria | Hartlepool Headland | 9116.616 | 4758.598 | 1032.902 | 0 | 300 | 1935 | 425 | 0 | 0 | 195 | 0 | 195 | 39442.084 |  | NOS302F/000A/004A
Shiremoor, Appraisal, Design and Construction | North Tyneside Council | Northumbria | Shiremoor | 842.9 | 212.9 | 350 | 0 | 0 | 115 | 115 | 0 | 60 | 0 | 60 | 0 | 16970.865 |  | NOC303F/000A/011A
Chathill Surface Water Flood Alleviation | Northumberland County Council | Northumbria | Chathill, Northumberland | 164.1 | 5.1 | 0 | 0 | 63.742 | 40 | 34 | 0 | 5 | 0 | 5 | 0 | 40.067 |  | NOC301F/000A/005A
Ovingham Surface Water Flood Alleviation | Northumberland County Council | Northumbria | Ovingham, Northumberland | 195 | 51.5 | 0 | 0 | 45.317 | 72 | 4 | 0 | 10 | 0 | 10 | 0 | 260.068 |  | NOC304F/000A/033A
Skinningrove Coastal Protection | Redcar and Cleveland Borough Council | Northumbria | Skinningrove | 3097.8 | 2450.8 | 0 | 0 | 0 | 139 | 0 | 0 | 0 | 175 | 0 | 175 | 3909 |  | NOS302C/000A/006A
Fellgate Estate - Appraisal, Design and Construction | South Tyneside Council | Northumbria | Jarrow, South Tyneside | 1012.2 | 85.6 | 0 | 0 | 300 | 550 | 0 | 0 | 45 | 0 | 45 | 0 | 0 |  | NOC304F/000A/020A
CCTV installation of Devon and Cornwall Flood Risk Management assets | Environment Agency | South West | various | 400 | 40 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 |  | SWO004E/000A/052A
Dawlish Warren and Exmouth Beach Management | Environment Agency | South West | Dawlish Warren & Exmouth | 8770.5 | 398 | 7069 | 0 | 150 | 100 | 0 | 0 | 2880 | 0 | 2880 | 0 | 77837 |  | SWC013E/000A/082A
Devon and Cornwall Floods 2012 | Environment Agency | South West | Various Locations across Devon and Cornwall | 4305 | 445 | 445 | 0 | 2000 | 0 | 60 | 0 | 250 | 0 | 355 | 0 | 49613.789 |  | SWO007E/000A/025A
Exeter Flood Defence | Environment Agency | South West | Exeter | 30928 | 2500 | 14431 | 0 | 0 | 6000 | 1470 | 0 | 4150 | 0 | 4150 | 0 | 229940 |  | SWC013E/000A/016A
Rolle Quay Flood Defence Repairs | Environment Agency | South West | Bideford | 260.831 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8453 |  | SWC014E/000A/039A
Stoke Canon Flood Defence Improvements | Environment Agency | South West | Stoke Canon | 2361.34 | 5 | 0 | 0 | 0 | 23.2 | 0 | 0 | 0 | 0 | 155 | 0 | 8391.1 |  | SWC013E/000A/044A
Porth Mellon Dune Management Plan, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 50 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 20 | 0 | 20 | 0 | 0 |  | SWS005C/000A/051A
Stoggy Lane, Plympton, Plymouth improvements | Plymouth city council | South West | Plymouth | 123 | 64 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 96 |  | SWS006F/000A/061A
Seaford Beach Shingle Recycling 2018/19 - 2022/23 | Environment Agency | Southern | Seaford, East Sussex | 1500 | 0 | 900 | 600 | 0 | 0 | 0 | 0 | 360 | 0 | 600 | 0 | 0 |  | SOS004C/000A/0010A
Broomhill Sands Coastal Defence | Environment Agency | Southern | Camber to Jury's Gap | 25314.684 | 9709.841 | 50 | 0 | 0 | 0 | 0 | 0 | 830 | 0 | 830 | 0 | 706415.629 |  | SOS003E/001A/014A
Bulverhythe Capital Maintenance 2013/14-2017/18 | Environment Agency | Southern | Between Bexhill and Hastings | 1200 | 300 | 600 | 0 | 0 | 0 | 0 | 0 | 465 | 0 | 620 | 0 | 175992 |  | SOS003E/002A/005A
Bulverhythe Capital Maintenance 2018/19-2022/23 | Environment Agency | Southern | Bulverhythe, East Sussex | 1500 | 0 | 900 | 600 | 0 | 0 | 0 | 0 | 465 | 0 | 775 | 0 | 175992 |  | SOS003E/000A/016A
Chalkmead Sluice Refurbishment | Environment Agency | Southern | River Lesser Teise, Collier Street, Kent | 180 | 0 | 150 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOO001E/000A/418A
Cheveney Sluice Refurbishment | Environment Agency | Southern | Upstream of Yalding on the River Beult SSSI | 180 | 120 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOO001E/000A/419A
Great Bells Farm - Habitat Creation | Environment Agency | Southern | Isle of Sheppey | 419.667 | 26 | 127.6 | 50.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOO004E/000A/083A
Greggs Wood Stream Culvert Renovation | Environment Agency | Southern | North Farm Industrial Estate Tunbridge Wells | 540 | 0 | 300 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 10150 |  | SOO001E/000A/416A
Littlehampton Arun Tidal Defences East Bank | Environment Agency | Southern | Littlehampton, coast to 500m north of A259 | 16068.324 | 800 | 0 | 0 | 0 | 1770 | 0 | 0 | 0 | 0 | 750 | 0 | 173334 |  | SOS004E/002B/007A
Lower Tidal River Arun Strategy Implementation Phase 1 | Environment Agency | Southern | Arundel | 90 | 30 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOO002E/000A/300A
Marshlands Tidal Basin Improvements | Environment Agency | Southern | Dymchurch | 150 | 0 | 110 | 0 | 40 | 0 | 0 | 0 | 55 | 0 | 55 | 0 | 459 |  | SOS003E/000A/014A
Medmerry Managed Realignment | Environment Agency | Southern | Medmerry Nr Selsey | 21058.019 | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 71866 |  | SOS005E/009A/001A
Medmerry monitoring | Environment Agency | Southern | Medmerry Nr Selsey | 400 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOS005C/009A/010A
Nore Farm Stream, Emsworth Flood Alleviation | Environment Agency | Southern | Bridge Road, Emsworth | 822.824 | 10 | 0 | 0 | 121 | 100 | 0 | 0 | 0 | 0 | 55 | 0 | 3365 |  | SOO002E/000A/020A
Pagham Harbour Inland Banks Flood Alleviation | Environment Agency | Southern | Pagham Harbour, West Sussex | 1229.93 | 150 | 25 | 0 | 0 | 0 | 700 | 0 | 85 | 0 | 85 | 0 | 6950 |  | SOS005C/009A/009A
Pett Shingle Renourishment Phase 2-6 | Environment Agency | Southern | Pett Levels | 3876 | 554 | 1662 | 0 | 0 | 0 | 0 | 0 | 1825 | 0 | 3190 | 0 | 945 |  | SOS003E/001A/006A
Pevensey Bay Sea Defences | Environment Agency | Southern | Pevensey, East Sussex | 49235.953 | 1552.463 | 8489.506 | 7755.283 | 0 | 0 | 5336 | 0 | 18605 | 0 | 34110 | 0 | 89560 |  | SOS003E/002A/003A
Sandwich Bay Sea Defences (Deal) | Environment Agency | Southern | Deal, Kent | 8424.116 | 158.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420 | 0 | 469443 |  | SOS001E/006A/016A
Sandwich Town Tidal Defences | Environment Agency | Southern | Sandwich, Kent | 20968.36 | 3072.5 | 0 | 0 | 0 | 3612 | 6310.07 | 0 | 0 | 0 | 485 | 0 | 201393 |  | SOS001E/006A/015A
Seaford Beach Shingle Recycling 2013/14 - 2017/18 | Environment Agency | Southern | Seaford | 1569 | 300 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOS004E/001A/012A
Southease Parish and Southease to A27 Tidal Embankment | Environment Agency | Southern | East Sussex | 2271.986 | 259 | 1212 | 563 | 0 | 0 | 0 | 0 | 25 | 0 | 40 | 0 | 4304 |  | SOS004E/001A/008A
Warnham Mill Reservoir | Environment Agency | Southern | Horsham, West Sussex | 1166.182 | 3 | 0 | 0 | 0 | 412.5 | 0 | 0 | 0 | 0 | 80 | 0 | 2200 |  | SOO004E/000A/148A
Herne Bay Sea Defence | Canterbury City Council | Southern | Herne Bay, Kent | 5458 | 0 | 182.8 | 4368.2 | 0 | 80 | 0 | 0 | 0 | 0 | 190 | 450 | 90000 |  | SOS002F/005A/03AA
Hambledon Groundwater Flood Alleviation | Hampshire CC | Southern | West Street/East Street Hambledon | 3743 | 0 | 1599 | 0 | 0 | 2144 | 0 | 0 | 125 | 0 | 125 | 0 | 35296 |  | SOC009F/000A/001A
South Hayling Island Beach Management Activities | Havant BC | Southern | Hayling Island Southern Frontage | 7143 | 288 | 1553 | 4606 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 1500 | 63841 |  | SOS005F/001A/006A
Hurst Spit Beach Management Plan 2013/14 to 2016/17 | New Forest DC | Southern | Southeast England | 100 | 24 | 33 | 0 | 0 | 10 | 0 | 0 | 450 | 0 | 450 | 0 | 97193.1707 |  | SOS005C/011A/013A
North Portsea Island Coastal Flood and Erosion Risk Management | Portsmouth City Council | Southern | Portsea Island, Portsmouth | 36767.603 | 6010 | 18350 | 11586.3 | 0 | 0 | 11.303 | 0 | 1905 | 0 | 1905 | 0 | 531069 |  | SOS005F/004A/006A
Aberford Road Health and Safety Improvements | Environment Agency | Thames | Aberford Road, Borehamwood, Herts. Borehamwood Brook. | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607 |  | THC017E/000A/023A
Banbury Flood Alleviation | Environment Agency | Thames | Banbury | 18555.849 | 5.579 | 6 | 0 | 1540.802 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 |  | THC001E/002A/001A
Beddington Park | Environment Agency | Thames | Beddington Park | 170 | 0 | 110.5 | 0 | 59.5 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 312 |  | THC032E/000A/010A
Chesham Culvert | Environment Agency | Thames | Chesham, Vale Brook | 502.759 | 10 | 0 | 0 | 105 | 150 | 0 | 0 | 10 | 0 | 10 | 0 | 0 |  | THC100E/001A/027A
Eastbury Flood Alleviation | Environment Agency | Thames | Eastbury, West Berkshire | 539.931 | 10 | 0 | 0 | 441.311 | 0 | 48.879 | 0 | 0 | 0 | 10 | 0 | 2312 |  | THC007E/000A/005A
Haydon Wick Flood Alleviation | Environment Agency | Thames | Haydon Wick | 7148.407 | 1 | 0 | 0 | 0 | 765 | 0 | 0 | 0 | 0 | 120 | 0 | 0 |  | THC001A/000E/005A
Hillman Cottages Flood Alleviation | Environment Agency | Thames | Essex | 1125.54 | 5 | 0 | 0 | 599.504 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | THC029E/000A/002A
Ifield Flood Alleviation | Environment Agency | Thames | Ifield, near Crawley | 170.25 | 70.25 | 0 | 0 | 100 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 1102 |  | THC009E/000A/002A
Newbury Flood Alleviation | Environment Agency | Thames | Newbury | 2949.114 | 3 | 0 | 0 | 0 | 1252.499 | 5 | 0 | 0 | 0 | 360 | 0 | 0 |  | THC007E/001A/002A
Paddle Rymer Package 2 | Environment Agency | Thames | Thames RFDC | 4367.778 | 8.674 | 29.422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | THC000E/003A/057B
Paddle and Rymer Health and Safety | Environment Agency | Thames | N/A | 8097.014 | 4 | 9.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | THC000E/003A/057A
Penton Hook Restoration | Environment Agency | Thames | Chertsey / Staines | 5795.52 | 1387.836 | 275.178 | 1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | THC038E/000A/006A
Redhill Flood Alleviation | Environment Agency | Thames | Redhill, Surrey | 875 | 0 | 450.5 | 0 | 424.5 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 3622.701 |  | THC009E/000A/001A
River Thames - Property Level Protection | Environment Agency | Thames | Lower Thames - Sunbury & Weybridge | 7473.821 | 1030 | 848 | 0 | 5085.791 | 510.03 | 0 | 0 | 380 | 0 | 560 | 0 | 0 |  | THC038E/001A/003A
River Wey Weir Refurbishment | Environment Agency | Thames | Wey Catchment Tilford to Thames | 3894.394 | 1763.647 | 1365.419 | 0 | 279.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | THC014E/001A/005A
Salmons Brook Flood Alleviation | Environment Agency | Thames | Enfield, London | 14508.156 | 900 | 0 | 0 | 4126 | 0 | 0 | 0 | 0 | 0 | 1355 | 0 | 0 |  | THC036E/001A/008A
Thames Barrier Drive Equipment | Environment Agency | Thames | Thames Barrier, Woolwich | 27693.8166 | 5937.675 | 16041.173 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 2500 | 0 | 1973086.1398 |  | THE001E/001A/025A
Thames Tidal Frontages Programme 1 | Environment Agency | Thames | Various | 8414.384 | 10 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 4140 | 0 | 2016467 |  | THE001E/000A/013A
Thames Weirs High Priority Programme Package 1 | Environment Agency | Thames | Romney Weir Molesey weir | 6277.906 | 10 | 0 | 0 | 3980.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | THC000E/000A/101B
Upper Mole Flood Alleviation | Environment Agency | Thames | Crawley & Horley, Gatwick Airport | 19872.466 | 3174.541 | 739.335 | 0 | 0 | 0 | 3821.603 | 0 | 280 | 0 | 1465 | 0 | 0 |  | THC009E/001A/002A
Northway & Marston Flood Risk Alleviation | Oxford City Council | Thames | Oxford, Peasmore Brook | 1487 | 981.35 | 0 | 0 | 505.65 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 8331.6023 |  | THC002E/000A/033A
Chobham Flood Alleviation | Surrey Heath BC | Thames | Chobham | 141 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 5451 |  | THO999F/017A/009A
Cheney Manor Flood Mitigation | Swindon Borough Council | Thames | Trib of R. Ray, Rodbourne, Swindon | 4028 | 1528 | 0 | 0 | 100 | 1300 | 0 | 0 | 0 | 0 | 180 | 0 | 47656 |  | THO999F/006A/015C
Tull Way Flood Alleviation | West Berkshire Council | Thames | Thatcham | 225 | 100 | 0 | 75 | 50 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 9020 |  | THO999F/011A/018A
Winterbourne Flood Alleviation | West Berkshire Council | Thames | Winterbourne | 250 | 0 | 37.348 | 0 | 132.652 | 20 | 15 | 0 | 15 | 0 | 15 | 0 | 1063 |  | TH0999F/11A/017A
Great Bedwyn Surface Water Drainage Improvements | Wiltshire Council | Thames | Great Bedwyn, Wiltshire, SN8 | 260 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 0 |  | THC007E/001A/013A
Isle of Axholme, Bull Hassocks Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 231 | 0 | 33.5 | 81 | 116.5 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 596 |  | TRC002E/000A/005A
Leicester Risk Management - conveyance | Environment Agency | Trent | Leicester | 7466 | 4600 | 950 | 0 | 0 | 700 | 0 | 0 | 1775 | 0 | 1775 | 0 | 16934 |  | TRC000E/000A/531A
Lower Derwent Package | Environment Agency | Trent | River Derwent | 80956 | 14315 | 14596 | 0 | 469 | 300 | 45043 | 0 | 1465 | 0 | 1465 | 0 | 180.212 |  | TRC003E/028A/001A
Lower Dove Flood Alleviation | Environment Agency | Trent | Scropton to the Trent. Derbyshire/Staffordshire | 7402.501 | 42.09 | 84.18 | 0 | 0 | 8.4 | 0 | 0 | 0 | 0 | 1620 | 0 | 314446 |  | TRC003E/005A/001A
Lower Tame - Whitacre Heath, Tamworth and Fazeley | Environment Agency | Trent | West Midlands | 15220.697 | 344.459 | 106.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 939805 |  | TRC003E/007A/001A
Middle Tame - Perry Barr and Witton | Environment Agency | Trent | River Tame Catchment, Witton, Birmingham | 25511.718 | 4047.637 | 15620.181 | 0 | 1559.8 | 1495 | 0 | 0 | 715 | 0 | 715 | 0 | 318500 |  | TRC003E/000A/533A
Nottingham Trent Left Bank | Environment Agency | Trent | Nottingham, River Trent | 5768.265 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16380 | 0 | 375.8 |  | TRC003E/008A/001A
River Idle, West Stockwith, Tidal/Idle Flood Gate Repair | Environment Agency | Trent | West Stockwith | 522 | 0 | 31 | 0 | 314.7 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 4.96 |  | TRC003E/000A/018A
Spondon Sluices Decommissioning | Environment Agency | Trent | River Derwent, Spondon | 1034.985 | 0 | 550 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.222 |  | TRC003E/000A/076A
Upper Tame - Titford Culvert | Environment Agency | Trent | River Tame Catchment, Oldbury, Birmingham | 284.311 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 27078 |  | TRC003E/000A/529A
Walkeringham - Flood Alleviation | Bassetlaw District | Trent | Walkeringham (Walkeringham Beck) | 598 | 293 | 0 | 0 | 105 | 150 | 0 | 0 | 45 | 0 | 45 | 0 | 1.924 |  | TRC003F/000A/002A
Ock Brook, Ockbrook, Flood Alleviation Study | Erewash District (B) | Trent | Ockbrook, Ock Brook | 83 | 0 | 38.5 | 0 | 25 | 17.5 | 2 | 0 | 0 | 0 | 15 | 0 | 0.36 |  | TRC003F/000A/039A
Kelfield Sewer, Kelfield Pumped Catchment | Isle of Axholme and North Notts Water Level MB | Trent | Kelfield, Doncaster | 446 | 0 | 70 | 0 | 30 | 346 | 0 | 0 | 45 | 0 | 45 | 0 | 3.377 |  | TRC002I/000A/005A
River Trent, Amcotts, Crowle Pumped Catchments | Isle of Axholme and North Notts Water Level MB | Trent | Amcotts, Scunthorpe | 1175 | 522 | 0 | 0 | 0 | 467 | 0 | 0 | 170 | 0 | 300 | 0 | 27.98 |  | TRC003I/000A/187A
River Soar, Leicester Northfields Flood Alleviation | Leicester City Council | Trent | Leicester | 435 | 0 | 435 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 85 | 0 | 2.087 |  | TRC003F/000A/009A
Thimblemill Brook, Smethwick, Flood Alleviation | Sandwell Metropolitan District | Trent | Smethwick, West Midlands | 900 | 0 | 750 | 0 | 150 | 0 | 0 | 0 | 255 | 0 | 255 | 0 | 1981 |  | TRC003F/000A/382A
Foston Brook, Scropton, Flood Alleviation Study | South Derbyshire District | Trent | Foston Brook, Scropton | 146 | 0 | 79 | 0 | 16 | 39 | 12 | 0 | 25 | 0 | 25 | 0 | 0.643 |  | TRC003F/000A/040A
Huntington, Cannock, Surface Water Flood Alleviation | Staffordshire County Council | Trent | Huntingdon, South Staffs | 240 | 0 | 180 | 0 | 50 | 10 | 0 | 0 | 30 | 0 | 30 | 0 | 433 |  | TRC003F/000A/030A
Knoll Brook, Barton-under-Needwood, Flood Alleviation | Staffordshire County Council | Trent | Barton-under-Needwood | 107 | 0 | 43 | 0 | 52 | 12 | 0 | 0 | 15 | 0 | 15 | 0 | 253 |  | TRC003F/000A/055A
Perton, Surface Water Flood Alleviation | Staffordshire County Council | Trent | Perton, Staffordshire | 250 | 30 | 120 | 0 | 50 | 5 | 5 | 0 | 220 | 0 | 220 | 0 | 3002 |  | TRC003F/000A/026A
Beckingham Drain, Beckingham Pumping Station Refurbishment | Trent Valley IDB | Trent | Beckingham | 1300 | 250 | 0 | 0 | 300 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 21.511 |  | TRC003I/000A/117A
Lowfield Drain, Lowfield Pumping Staion Refurbishment | Trent Valley IDB | Trent | Balderton, Newark | 106 | 0 | 90 | 0 | 0 | 16 | 0 | 0 | 55 | 0 | 55 | 0 | 1.05 |  | TRC003I/000A/007A
Bruton Reservoir Section 10 Improvements | Environment Agency | Wessex | Bruton , Somerset | 256.5 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC006E/000A/155A
Coombend Culvert and Stream Improvements | Environment Agency | Wessex | Somerset | 1336.0336 | 10 | 0 | 0 | 1009.496 | 50 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | WXC005E/000A/103A
Cribbs Causeway Reservoir Section 10 Improvements | Environment Agency | Wessex | Carbrain, Bristol. Trym. | 254 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC005E/000A/147A
Curry Moor Reservoir Section 10 Improvements | Environment Agency | Wessex | East Lyng, River Tone | 717 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC007E/000A/219A
French Weir Remedials, River Tone | Environment Agency | Wessex | River Tone, Taunton, Somerset | 186.8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC007E/000A/208A
Somerset Levels and Moors 20 Year Flood Action Plan implementation | Environment Agency | Wessex | Somerset Levels and Moors - Parrett, Tone, Brue and Axe Rivers | 55161.476 | 30 | 134.815 | 16378.664 | 50 | 4000 | 0 | 24567.997 | 0 | 0 | 0 | 0 | 125850 |  | WXO004E/000A/102A
Steart Coastal Management | Environment Agency | Wessex | Steart, Somerset | 20179 | 237 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXS004E/001A/001A
Swanage Flood Storage Reservoirs | Environment Agency | Wessex | Swanage/River Swan | 790 | 243.692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC001E/000A/033A
Tubbs Bottom Washland Improvements | Environment Agency | Wessex | Iron Acton, Bristol Frome. | 264 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC005E/000A/148A
Wareham Coastal Change | Environment Agency | Wessex | Wareham | 9760 | 1000 | 2579.2 | 4376.8 | 0 | 0 | 1375 | 0 | 0 | 0 | 3000 | 0 | 261416 |  | WXC001E/000A/025A
Wessex Property Level Protection | Environment Agency | Wessex | Various | 4121.007 | 403.665 | 904.285 | 0 | 2080.208 | 0 | 85 | 0 | 395 | 0 | 595 | 0 | 21822.922 |  | WXO004E/000A/060A_1
Westford Reservoir Section 10 Improvements | Environment Agency | Wessex | Westford village, Nr Wellington. | 233.5 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC007E/000A/220A
Lower Axe - Health and Safety improvements to structures (Phase 2) | Axe Brue Internal Drainage Board | Wessex | Ex Lower Axe DDB area | 442.5822 | 28 | 56 | 0 | 0 | 243.4202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC006I/000A/02CA
Lower Axe Urban Drainage Improvements - Brent Knoll and East Brent | Axe Brue Internal Drainage Board | Wessex | East Brent | 200 | 25 | 125 | 0 | 0 | 50 | 0 | 0 | 20 | 0 | 20 | 0 | 3589 |  | WXC006I/000a/03CA
Lower Brue Health and Safety Improvements to Structures (Phase 2) | Axe Brue Internal Drainage Board | Wessex | Ex Lower Brue DDB area | 453.8489 | 30 | 60 | 0 | 0 | 249.6169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC006I/000A/05CA
Lower Brue Urban Drainage Improvements - West Huntspill and Alstone | Axe Brue Internal Drainage Board | Wessex | West Huntspill and Alstone | 184.4444 | 45 | 0 | 0 | 0 | 101.4444 | 0 | 0 | 30 | 0 | 30 | 0 | 72 |  | WXC006I/000A/081A
Poole Dolphin Haven | Borough of Poole | Wessex | Poole | 2000 | 200 | 400 | 0 | 0 | 0 | 1200 | 0 | 75 | 0 | 75 | 0 | 38428 |  | WXS001C/000A/039A
Bournemouth Beach Management Phase 1 (18% Version) | Bournemouth Borough Council | Wessex | Bournemouth | 14739.3 | 4614.233 | 7271.513 | 0 | 1000 | 1273.554 | 350 | 0 | 0 | 2595 | 0 | 2595 | 469060.486 |  | WXS001C/000A/027A
Weston Bay beach recycling | North Somerset Council | Wessex | Weston-super-Mare, Knightstone to Uphill | 100 | 15 | 45 | 0 | 0 | 25 | 0 | 0 | 895 | 0 | 1115 | 0 | 86906.5 |  | WXC006C/000A/152A
Wrington Flood Relief | North Somerset Council | Wessex | Wrington, North Somerset | 670 | 20 | 0 | 0 | 80 | 100 | 182 | 0 | 25 | 0 | 80 | 0 | 3410 |  | WXC006F/000A/109A
Minehead Urban Drainage Improvements | Parrett Internal Drainage Board | Wessex | Minehead | 646.6667 | 152 | 114 | 0 | 0 | 355.6667 | 0 | 0 | 180 | 0 | 180 | 0 | 24143 |  | WXS004I/001A/051A
Parrett Health and Safety Improvements to Structures | Parrett Internal Drainage Board | Wessex | Parret IDB area | 815.1711 | 50 | 50 | 0 | 0 | 448.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC007I/000A/01CA
Flood alleviation at Croscombe, Somerset | Somerset County Council | Wessex | Old Street Lane, Croscombe | 90 | 0 | 42 | 0 | 0 | 48 | 0 | 0 | 10 | 0 | 10 | 0 | 129.475 |  | WXS004F/001A/047A
Lyme Regis Coast Protection Beach Management | West Dorset DC | Wessex | Lyme Regis | 274.6 | 65.3 | 65.3 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 135 | 2421.5 |  | WXS002C/000A/036A
Lyme Regis Coast Protection Phase IV | West Dorset DC | Wessex | Lyme Regis | 17141.844 | 100 | 100 | 0 | 0 | 4270.844 | 0 | 0 | 0 | 480 | 0 | 480 | 72038 |  | WXS002C/000A/03CA
Ringstead Beach Management | West Dorset DC | Wessex | Ringstead | 200 | 0 | 157 | 18 | 20 | 5 | 0 | 0 | 0 | 10 | 0 | 10 | 2200 |  | WXS002C/000A/025A
West Bay Coast Protection Works Beach Management | West Dorset DC | Wessex | West Bay | 266.1 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 105 | 35 | 260 | 90 | 9556 |  | WXS002C/000A/034A
Avenue Flood Balancing Reservoir, Chesterfield | Environment Agency | Yorkshire | River Rother, Chesterfield | 2712 | 620 | 60 | 0 | 795 | 400 | 240 | 0 | 90 | 0 | 90 | 0 | 5833 |  | YOC356E/003A/901A
Catterick Flood Alleviation | Environment Agency | Yorkshire | Catterick, River Swale | 4830 | 500 | 0 | 0 | 330 | 3500 | 0 | 0 | 55 | 0 | 55 | 0 | 7873 |  | YOC353E/000A/916A
Humber: Erosion Protection | Environment Agency | Yorkshire | Humber Estuary | 20326 | 750 | 7550 | 11000 | 0 | 0 | 0 | 0 | 2585 | 0 | 7215 | 0 | 28296 |  | YOS399E/001A/046B
Humber: Estuary-wide Monitoring | Environment Agency | Yorkshire | Humber Estuary | 2100 | 250 | 850 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | YOS399E/001A/037A
Ings Beck Flood Alleviation | Environment Agency | Yorkshire | Wakefield | 16531.319 | 12.221 | 6.505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715 | 0 | 117000 |  | YOC355E/000A/002A
Mill Beck Reservoir, Market Weighton | Environment Agency | Yorkshire | Market Weighton, Mill Beck Reservoir | 3781.415 | 10 | 12.5 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 65 | 0 | 0 |  | YOC357E/000A/013A
Northallerton (Sun and Turker Becks) Flood Alleviation | Environment Agency | Yorkshire | Northallerton | 2791.125 | 23.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 82589 |  | YOC353E/000A/006A
Package 2 - Yorkshire - inc Reedness, Goole and Airmyn | Environment Agency | Yorkshire | Reedness, Goole | 4600 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | YOC353E/000A/094A
Skipton Flood Alleviation | Environment Agency | Yorkshire | Skipton, Eller Beck, Waller Hill Beck and Ings Beck | 13780 | 2800 | 1207 | 0 | 300 | 1650 | 250 | 1254 | 365 | 0 | 365 | 0 | 43499 |  | YOC354E/000A/016A
Snaith Ings Reservoir Repairs | Environment Agency | Yorkshire | Snaith, lower River Aire | 3196.5 | 371.5 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 55 | 0 | 0 |  | YOC354E/000A/025A
Water End Flood Alleviation, York | Environment Agency | Yorkshire | York | 4612 | 2.5 | 7.5 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 380 | 0 | 39627 |  | YOC353E/001A/002A
Low Valley Flood Alleviation, Wombwell, Barnsley | Barnsley MBC | Yorkshire | Barnsley | 1200 | 65.625 | 0 | 0 | 0 | 0 | 600 | 0 | 160 | 0 | 160 | 0 | 6800 |  | YOC356F/000A/032A
Pocklington Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Pocklington | 2000 | 315 | 0 | 0 | 100 | 85 | 1500 | 0 | 260 | 0 | 260 | 0 | 6889.709 |  | YOC353F/000A/013A
Willerby and Derringham Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Willerby | 17677.539 | 2625.113 | 0 | 4059.583 | 37.5 | 6626.155 | 0 | 0 | 8085 | 0 | 8085 | 0 | 525454.323 |  | YOC357F/000A/022A
Leeds City Flood Alleviation | Leeds City Council | Yorkshire | River Aire, Leeds | 45572 | 0 | 8510 | 0 | 0 | 13362 | 0 | 0 | 70 | 0 | 70 | 0 | 88615 |  | YOC354E/001A/001A
Sandsend Coast Protection | North Yorkshire County Council | Yorkshire | Sandsend | 12541 | 1611 | 1402 | 0 | 0 | 6126 | 0 | 0 | 0 | 10 | 0 | 10 | 75476 |  | YOS351F/000A/012A
Eastrington & Laxton Flood Management | Ouse & Humber Drainage Board | Yorkshire | Eastrington & Laxton | 904 | 297 | 0 | 0 | 0 | 310 | 0 | 0 | 270 | 0 | 270 | 0 | 2162 |  | YOC357I/000A/012A
Gilberdyke & Blacktoft Flood Management | Ouse & Humber Drainage Board | Yorkshire | Gilberdyke & Blacktoft | 1164.6754 | 450.0389 | 0 | 0 | 0 | 115.598 | 0 | 0 | 570 | 0 | 570 | 0 | 3959 |  | YOC357I/000A/011A
Sheffield Lower Don Valley Flood Protection | Sheffield City Council | Yorkshire | Sheffield Lower Don Valley - Rover Don, Sheffield S1 and S9 | 15304.0901 | 5635 | 2359 | 0 | 98 | 0 | 500 | 0 | 35 | 0 | 35 | 0 | 285840 |  | YOC356F/000A/019A
b. Projects scheduled to start construction by 31 March 2016 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
King's Lynn Fisher Fleet - Refurbishment of Floodgates | Environment Agency | Anglian Central | King's Lynn, Tidal River Great Ouse and The Wash | 1449.76 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 12000 |  | ACC451E/000A/586A
Ouse Washes Reservoir Section 10 | Environment Agency | Anglian Central | River Great Ouse | 36475 | 100 | 36300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory Requirement | ACC451E/000A/615a
Swavesey Flood Risk Management | Environment Agency | Anglian Central | Swavesey, Cambridgeshire, in River Ouse | 675.224 | 0 | 387 | 0 | 287 | 0 | 0 | 0 | 135 | 0 | 135 | 0 | 3062.626 |  | ACC451E/000A/611A
Norwich Flood Protection | Environment Agency | Anglian Eastern | Norwich, Norfolk | 550 | 40 | 390 | 0 | 120 | 0 | 0 | 0 | 55 | 0 | 55 | 0 | 7233.957 |  | AEC503E/000A/008A
Sandford Mill Cottages Defence Repairs Pump Installation | Environment Agency | Anglian Eastern | Chelmsford | 65 | 20 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.971 |  | AEC506E/000A/021A
Bourne Eau Health and Safety | Environment Agency | Anglian Northern | Boune Eau | 412.868 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11894 | Health & Safety | ANC404E/000A/001A
Bewdley Property Level Protection | Environment Agency | English Severn and Wye | Bewdley | 422 | 0 | 115 | 0 | 307 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 598 |  | SNC001F/000A/047A
Mushroom Green Dam, Dudley, Mousesweet Brook, Flood Alleviation | Dudley Metropolitan Borough Council | English Severn and Wye | Mushroom Green | 1400 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 94 |  | SNC001F/000A/059A
Astley Brook, Leigh | Environment Agency | North West | Astley Bk, Tyldesley, Greater Manchester | 1235 | 0 | 50 | 1185 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 8514 |  | NWC008E/003A/004A
Broadgate & Lower Penwortham Defences | Environment Agency | North West | Preston, Lancashire | 20330 | 0 | 500 | 19500 | 0 | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 47000 |  | NWC009E/005A/003A
Gategill Beck, Threlkeld | Environment Agency | North West | Keswick, Cumbria | 1050 | 100 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 142 |  | NWC002E/000A/012A
Hindley Group | Environment Agency | North West | Hindley, Greater Manchester | 1346 | 0 | 50 | 1296 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0 | 17614 |  | NWC008E/003A/006A
River Irwell, Bury South | Environment Agency | North West | Bury, Greater Manchester | 4967 | 640 | 4000 | 0 | 0 | 0 | 0 | 0 | 825 | 0 | 825 | 0 | 25366 |  | NWC005E/005A/009A
The Wrangling, Blackburn | Environment Agency | North West | Blackburn, Lancashire | 3707 | 2549 | 1037 | 0 | 122 | 0 | 0 | 0 | 135 | 0 | 135 | 0 | 33133 |  | NWC009E/002A/002A
Blackley New Road Residential Area Flooding | Manchester City Council | North West | Higher Blackley residential area adjacent to King William IV Fishing Lake | 587 | 450 | 0 | 0 | 137 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 2672.419 |  | NWC005F/000A/019A
Four Acres, Maghull Asset Management Plan | Sefton Council | North West | Maghull, Merseyside | 35 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 65 |  | NWC001F/000A/047A
13/14 Combined Flood Event Repairs | Environment Agency | South West | Various Locations | 1000 | 444.658 | 555.342 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 105 | 0 | 14649.817 |  | SWO007E/000A/069A
Exe Estuary Habitat Delivery | Environment Agency | South West | Exe Estuary | 3565.498 | 244 | 2974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2581.745 | Statutory Requirement | SWC013E/000A/045A
Helston Flood Alleviation | Environment Agency | South West | Helston | 1875.633 | 689 | 653 | 0 | 455.296 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 19825 |  | SWC010E/000A/096A
Laira Avenue, Laira, Plymouth, highways drainage and culverts | Plymouth city council | South West | Plymouth | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 63 |  | SWS006F/000A/058A
Teignmouth Point Coastal Defence Wall Replacement | Teignbridge District Council | South West | The Point Teignmouth | 623.5 | 94.5 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 195 | 17115.82 |  | SWC015C/000A/046A
Thames Estuary Phase 1 Programme | Environment Agency | Southern | Thames Estuary | 860686.7329 | 846.7708 | 90443.0686 | 769396.8935 | 0 | 0 | 0 | 0 | 2000 | 0 | 15320 | 0 | 1834485.3808 |  | THE001E/000A/012A_3
Abingdon River Stert Flood Alleviation | Environment Agency | Thames | Abingdon, Oxfordshire | 140.9 | 0 | 53.3 | 0 | 87.6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 1187.497 |  | THC041E/000A/006A
Guildford Flood Alleviation | Environment Agency | Thames | Guildford | 3155 | 0 | 1084.55 | 0 | 2070.45 | 0 | 0 | 0 | 255 | 0 | 255 | 0 | 716.91 |  | THC011E/000A/002A
Lower Mole Safety Booms | Environment Agency | Thames | Molesey, Elmbridge | 500 | 87 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Health & Safety | THC013E/000A/009A
Manor Farm Containment Cell Sump Repair | Environment Agency | Thames | Jubilee River | 110 | 10 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Legal Agreement | THC039E/000A/039A
Slough Flood Alleviation | Environment Agency | Thames | Slough | 2863.186 | 0 | 1068 | 0 | 1661 | 0 | 0 | 0 | 400 | 0 | 400 | 0 | 1419 |  | THC039E/000A/035A
Thames Estuary 2100 Habitat Creation | Environment Agency | Thames | Thames Estuary | 23000 | 1000 | 11000 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory Requirement | THE001E/000A/019A
Thames Estuary Phase 1 Programme | Environment Agency | Thames | Thames Estuary | 889904.3893 | 6762.0724 | 36351.6029 | 842928.452 | 0 | 0 | 0 | 0 | 8220 | 0 | 168900 | 0 | 103716804.5758 |  | THE001E/000A/012A_1
London Colney Surface Water and Watercourse Study | Hertfordshire CC | Thames | London Colney Hertfordshire | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2627.5464 |  | THC018E/000A/017A
Welcomes Road and Kenley Station surface water flood alleviation | London Borough of Croydon | Thames | Kenley, Croydon | 327 | 50 | 232 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 125 | 0 | 17550 |  | THO999F/035A/002A
Cossington Sluices | Environment Agency | Trent | Cossington | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 579 |  | _A
Isle of Axholme, Goodcop Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 617 | 0 | 135 | 0 | 482 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 1.446 |  | TRC002E/000A/008A
Congresbury Yeo Tidal Banks | Environment Agency | Wessex | Congresbury Yeo Tidal Banks (Tutshill to Wick) | 3407.657 | 2457.818 | 120 | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 4100 | 0 | 620192 |  | WXS004E/001A/009A
Burstwick New Clough | Environment Agency | Yorkshire | Saltend, Hull | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 360 | 0 | 4382.372 |  | YOC357E/000A/061A
Catcliffe, Canklow, Meadowgate and Woodhouse Mill Defence Improvements | Environment Agency | Yorkshire | Catcliffe, Canklow and Beighton, River Rother | 1000 | 700 | 300 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 515 | 0 | 9515.2265 |  | YOC356E/000A/068A
Newport Floodwalls | Environment Agency | Yorkshire | Newport, Market Weighton | 312 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 0 | 270 | 0 | 3698.779 |  | YOC357E/000A/050A
Yorkshire Culverts | Environment Agency | Yorkshire | Area-wide | 6550 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | YOO000E/000A/100A
Withernsea Groyne Field Improvements | East Riding of Yorkshire Council | Yorkshire | Withernsea | 1000 | 500 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 743.344 |  | YOS352C/000A/007A
c. Projects scheduled to start construction by 31 March 2016, subject to securing other funding contributions |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yelden & Upper Dean Flood Risk Management Scheme | Bedford Borough Council | Anglian Central | Yelden | 57.4 | 0 | 0.4 | 0 | 51 | 6 | 0 | 0 | 10 | 0 | 10 | 0 | 0 |  | ACC451F/000A/025A
Ledburn Flood Risk Management | Buckingham and River Ouzel Internal Drainage Board | Anglian Central | Ledburn | 428 | 147 | 0 | 0 | 80 | 172 | 0 | 0 | 25 | 0 | 25 | 0 | 0 |  | ACC451I/000A/001A
A1101 Wash Road Welney Improvement Scheme | Norfolk CC | Anglian Central | Wash Road, The Hundred Foot Washes, Old Bedford River | 1150 | 0 | 50 | 0 | 50 | 400 | 0 | 650 | 0 | 0 | 0 | 0 | 3623.196 | Time Constrained Contribution | ACC451E/000A/624A
Snape | Environment Agency | Anglian Eastern | Tidal River Alde | 425 | 350 | 0 | 0 | 0 | 0 | 75 | 0 | 35 | 0 | 35 | 0 | 0 |  | AES503E/000A/027A
Thames Estuary Phase 1 Programme | Environment Agency | Anglian Eastern | Thames Estuary | 119403.2616 | 47.4042 | 62097.9071 | 47942.3388 | 0 | 0 | 0 | 9315.6115 | 2555 | 0 | 22255 | 0 | 0 |  | THE001E/000A/012A_2
Thorpeness erosion response 2015 | Suffolk Coastal District Council | Anglian Eastern | Thorpeness | 527 | 200 | 0 | 0 | 0 | 27 | 0 | 300 | 0 | 15 | 0 | 15 | 0 |  | AES503E/003A/003A
Askews Pump Replacement, Haddiscoe | Waveney, Lower Yare & Lothingland Internal Drainage Board | Anglian Eastern | Haddiscoe Island | 108 | 32 | 0 | 0 | 0 | 76 | 0 | 0 | 2 | 0 | 2 | 0 | 0 |  | AEO000E/000A/393A
Brook Drain Flood Risk Management Peterborough | Environment Agency | Anglian Northern | Brook Drain | 550 | 0 | 40 | 0 | 0 | 0 | 0 | 510 | 0 | 0 | 0 | 0 | 594.344 | Time Constrained Contribution | ANC405E/000A/102A
Welland & Nene Property Level Protection | Environment Agency | Anglian Northern | Welland & Nene Catchment | 276.73 | 123.75 | 0 | 0 | 118 | 0 | 34.98 | 0 | 40 | 0 | 40 | 0 | 0 |  | ANO000E/000A/380A
Digby - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Digby | 300 | 40 | 45 | 0 | 20 | 50 | 145 | 0 | 20 | 0 | 20 | 0 | 0 |  | ANC403F/000A/021A
Horncastle - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Horncastle | 435 | 0 | 106.25 | 0 | 30 | 100 | 198.75 | 0 | 25 | 0 | 25 | 0 | 0 |  | ANC403F/000A/026A
Withybrook, Warwickshire Flood Alleviation | Severn Trent Water | English Severn and Wye | Withybrook | 459 | 10 | 30 | 0 | 100 | 5 | 314 | 0 | 5 | 0 | 5 | 0 | 0 |  | SNC001F/000A/060A
Shyte Brook, Much Wenlock, Flood Alleviation | Shropshire Council | English Severn and Wye | Much Wenlock | 1337 | 0 | 712 | 0 | 500 | 75 | 0 | 0 | 170 | 0 | 170 | 0 | 9734 |  | SNC001F/000A/396A
Cherington, Shipston-on-Stour, Flood Alleviation | Warwickshire CC | English Severn and Wye | Cherington | 271.4 | 0 | 67.5 | 67.5 | 100 | 36.4 | 0 | 0 | 20 | 0 | 20 | 0 | 323 |  | SNC001F/000A/057A
Fenny Compton, Flood Alleviation | Warwickshire CC | English Severn and Wye | Warwickhire CC | 371 | 0 | 70 | 0 | 30 | 271 | 0 | 0 | 20 | 0 | 20 | 0 | 0 |  | SNC003F/000A/025A
Kites Hardwick, Rugby, River Leam, Property Level Protection | Warwickshire CC | English Severn and Wye | Kites Hardwick | 59 | 0 | 20 | 0 | 10 | 29 | 0 | 0 | 5 | 0 | 5 | 0 | 0 |  | SNC001F/000A/051A
Darwen Surface Water Management Plan | Blackburn with Darwen Borough Council | North West | Darwen, Lancashire | 1135 | 200 | 800 | 0 | 90 | 45 | 0 | 0 | 260 | 0 | 260 | 0 | 2.339 |  | NWC009F/000A/013A
Elliot Park, Keswick | Cumbria CC | North West | Keswick, Cumbria | 649 | 319 | 0 | 0 | 300 | 0 | 30 | 0 | 35 | 0 | 35 | 0 | 0 |  | NWC002F/001A/002A
Manchester Restoration of Open Channels of Ordinary Watercourses | Manchester City Council | North West | Manchester | 350 | 100 | 100 | 0 | 0 | 150 | 0 | 0 | 70 | 0 | 100 | 0 | 0 |  | NWC005F/000A/018A
Calder Avenue, Littleborough Flood Alleviation | Rochdale MBC | North West | Calder Avenue, Littleborough | 609 | 119 | 110 | 0 | 150 | 150 | 0 | 0 | 65 | 0 | 65 | 0 | 0 |  | NWC005F/000A/001A
Coffin Lane Brook, Ashton, Wigan | Wigan Council | North West | Wigan, Greater Manchester | 99.61 | 89.61 | 0 | 0 | 0 | 10 | 0 | 0 | 35 | 0 | 35 | 0 | 0 | Health & Safety | NWC003F/000A/010A
West Kirby Flood Alleviation | Wirral MBC | North West | West Kirby, Merseyside | 1764.287 | 1057.752 | 0 | 0 | 0 | 570 | 0 | 136.535 | 140 | 0 | 140 | 0 | 0 | Time Constrained Contribution | NWC008F/000A/002C
Lanchester Surface Water | Durham County Council | Northumbria | Lanchester | 1265.9 | 92.427 | 170.9 | 0 | 582.573 | 420 | 0 | 0 | 45 | 0 | 45 | 0 | 0 |  | NOC305F/000A/005A
Newcastle Culvert Repairs and Access Improvements | Newcastle City Council | Northumbria | Various | 739.2 | 160.7 | 133.5 | 0 | 135 | 310 | 0 | 0 | 20 | 0 | 20 | 0 | 4250 |  | NOC304F/000A/029A
Newcastle Local Flood Alleviations | Newcastle City Council | Northumbria | Various | 824.6 | 0 | 544.6 | 0 | 140 | 140 | 0 | 0 | 110 | 0 | 110 | 0 | 0 |  | NOC304F/000A/030A
Anchorwood Barnstaple Flood Defence Improvements | Environment Agency | South West | Barnstaple Devon River Taw | 1100 | 50 | 50 | 0 | 0 | 0 | 1000 | 0 | 90 | 0 | 90 | 0 | 0 |  | SWC014E/000A/065A
Par Moor Diversion culvert | Environment Agency | South West | Par | 1106 | 243 | 213 | 0 | 20 | 530 | 100 | 0 | 5 | 0 | 5 | 0 | 0 |  | SWC010E/000A/074A
Perranporth (Bolingey River) Flood Defence | Environment Agency | South West | Perranporth | 847.662 | 367 | 0 | 0 | 221.196 | 0 | 125 | 0 | 215 | 0 | 215 | 0 | 0 |  | SWC010E/000A/046A
Whimple Flood Defence Improvements | Environment Agency | South West | Whimple | 1506 | 237 | 132 | 0 | 416 | 50 | 140 | 531 | 40 | 0 | 40 | 0 | 0 |  | SWC013E/000A/036A
Coverack sea walls refurbishment | Cornwall Council | South West | Coverack | 310 | 155 | 0 | 0 | 0 | 155 | 0 | 0 | 0 | 10 | 0 | 10 | 0 |  | SWC010C/000A/048A
Axminster Millbrook | Devon County Council | South West | Axminster | 135 | 50 | 0 | 0 | 50 | 35 | 0 | 0 | 100 | 0 | 100 | 0 | 2759.902 |  | SWC012F/000A/062A
Braunton Flood Improvements | Devon County Council | South West | Braunton | 560 | 200 | 200 | 0 | 30 | 100 | 30 | 0 | 70 | 0 | 70 | 0 | 0 |  | SWC014F/000A/070A
Modbury Flood Improvements | Devon County Council | South West | Modbury | 460 | 150 | 150 | 0 | 50 | 80 | 30 | 0 | 60 | 0 | 60 | 0 | 0 |  | SWC015F/000A/057A
Stibbs Lane Ivybridge | Devon County Council | South West | Stibbs Lane Ivybridge | 175 | 40 | 40 | 0 | 30 | 45 | 20 | 0 | 25 | 0 | 25 | 0 | 0 |  | SWC015F/000A/055A
Honicknowle Lane, Plymouth, new trash screen and headwall | Plymouth city council | South West | Plymouth | 68 | 58 | 0 | 0 | 0 | 10 | 0 | 0 | 15 | 0 | 15 | 0 | 0 |  | SWS006F/000A/056A
Stokeinteignhead - Remedial Works | Teignbridge District Council | South West | Stokeinteignhead | 100 | 90 | 0 | 0 | 5 | 5 | 0 | 0 | 70 | 0 | 70 | 0 | 1165.8885 |  | SWC015F/000A/054A
Angmering Fluvial and Surface Water Flood Improvement | Environment Agency | Southern | Angmering | 750.5 | 200 | 338 | 0 | 47.5 | 90 | 75 | 0 | 70 | 0 | 70 | 0 | 0 | Time Constrained Contribution | SOO002E/000A/299A
Highfield Close (Waterlooville) Trash Screen Replacement | Environment Agency | Southern | Waterlooville | 162 | 50 | 0 | 0 | 0 | 0 | 0 | 112 | 30 | 0 | 30 | 0 | 0 | Health & Safety | SOC009E/000A/005A
River Ouse, Newhaven to Seaford Flood Alleviation | Environment Agency | Southern | Newhaven and Seaford | 9319.057 | 0 | 5700 | 0 | 0 | 3000 | 250 | 0 | 1060 | 215 | 1060 | 215 | 0 |  | SOS004E/001A/009A
Shoreham Adur Tidal Walls | Environment Agency | Southern | Shoreham | 25846.583 | 134.1 | 16479 | 0 | 901.239 | 6400 | 800 | 0 | 2215 | 0 | 2215 | 0 | 0 |  | SOS004E/002A/002A
Eastbourne Beach Management - (2015/16 - 2020/21) | Eastbourne Borough Council | Southern | Eastbourne Sea Front | 2400 | 300 | 1500 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOS003C/004A/07AA
Ramsgate Main Beach - Timber Groyne Installation | Thanet District Council | Southern | Ramsgate, Kent | 705 | 0 | 442 | 0 | 0 | 263 | 0 | 0 | 30 | 0 | 30 | 0 | 0 |  | SOS002C/000A/015A
West Ilsley | West Berkshire Council | Thames | West Ilsley, West Berkshire | 282 | 0 | 191.941 | 0 | 47.759 | 42.3 | 0 | 0 | 40 | 0 | 40 | 0 | 0 |  | THC007E/000A/006A
Oakerthorpe Brook, Derwent Grove, Alfreton, Flood Alleviation Study | Amber Valley District (B) | Trent | Alfreton, Oakerthorpe Brook | 110 | 0 | 50 | 0 | 0 | 40 | 20 | 0 | 15 | 0 | 15 | 0 | 0 |  | TRC003F/000A/035A
Paper Mill Dyke Flood Defence Wall | Doncaster MBC | Trent | Tickhill | 83 | 7 | 0 | 0 | 38 | 14 | 24 | 0 | 10 | 0 | 10 | 0 | 0 | Time Constrained Contribution | TRC003F/000A/075A
Hucknall Town Centre Flood Alleviation | Nottinghamshire CC | Trent | Hucknall, Baker Lane Brook | 836.25 | 180 | 56.25 | 0 | 100 | 425 | 75 | 0 | 35 | 0 | 35 | 0 | 0 |  | TRC003F/000A/072A
Cannington Flood Defence | Environment Agency | Wessex | Cannington | 3851.292 | 883.5 | 0 | 0 | 1750 | 89 | 740 | 0 | 115 | 0 | 115 | 0 | 0 |  | WXC007E/000A/194A
Charminster | Environment Agency | Wessex | Charminster | 591.664 | 37.795 | 0 | 0 | 453.869 | 100 | 0 | 0 | 10 | 0 | 10 | 0 | 1746.338 |  | WXC001E/000A/004A
Frome Improvements - Wallbridge | Environment Agency | Wessex | Somerset River Frome at Wallbridge, Frome | 515 | 0 | 151 | 0 | 0 | 0 | 364 | 0 | 20 | 0 | 20 | 0 | 0 |  | WXC005E/000A/137A
Bath Flood Risk Management Project | Bath and North East Somerset Council | Wessex | Bath, River Avon (Main River) | 5100 | 540 | 0 | 0 | 510 | 3980 | 0 | 0 | 60 | 0 | 60 | 0 | 15075 |  | WXC005F/000A/150A
Dorset Property Level Protection | Dorset County Council | Wessex | Weymouth, Bradford Peverell, Sixpenny Handley and Rural Dorset South Winterbourne, Winterbourne Abbas, Winterbourne Steepton and Martinstown | 642 | 0 | 232 | 0 | 350 | 60 | 0 | 0 | 95 | 0 | 95 | 0 | 0 |  | WXC001F/000A/034A
Anlaby and East Ella Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Anlaby | 19922.399 | 1500 | 11210.399 | 35 | 100 | 7000 | 0 | 0 | 12780 | 0 | 12780 | 0 | 0 |  | YOC357F/000A/067A
Cottingham and Orchard Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Cottingham | 22213.414 | 150 | 11912.615 | 282.625 | 37.5 | 9250 | 0 | 0 | 4255 | 0 | 4255 | 0 | 0 |  | YOC357F/000A/023A
Hull and Holderness Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Humber Estuary | 30100 | 1500 | 25500 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | YOC357F/000A/115A
Skidby Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Skidby | 318 | 29 | 200 | 0 | 0 | 78 | 0 | 0 | 90 | 0 | 90 | 0 | 0 |  | YOC357F/000A/007A
Works Arising from River Hull Integrated Catchment Strategy | East Riding of Yorkshire Council | Yorkshire | Beverley | 43095 | 150 | 34200 | 0 | 0 | 8745 | 0 | 0 | 0 | 0 | 22830 | 0 | 0 |  | YOC357F/000A/116A
River Wiske Flood Risk Management Plan (Unit 05) | North Yorkshire County Council | Yorkshire | River Wiske | 1817.2 | 0 | 1458.907 | 228.293 | 65 | 65 | 0 | 1.1642e-13 | 0 | 0 | 190 | 0 | 0 |  | YOC353F/000A/019A
Whitby Harbour Works (Units 17 & 18) | Scarborough Borough Council | Yorkshire | Whitby, North Yorkshire, YO21 | 8522 | 2214 | 2303.125 | 0 | 0 | 3710 | 0 | 0 | 15 | 360 | 15 | 360 | 0 |  | YOS351C/000A/086A

## Development Programme
Flood and Coastal Erosion Risk Management (FCERM) Development Programme - England
|  |  |  | Pre-Construction FCERM GIA |  |  | Pre-Construction Other funding |  |  |  |  | Estimated funding for construction by March 2021 dependent on full business case approval and securing required contributions |  |  |  | Households with a better level of protection by March 2021 |  | Total households with a better level of protection when schemes are complete
Project Name | Risk Management Authority | Regional Flood and Coastal Committee (RFCC) | Location | Allocated in 2015/16 (£k) | Indicative upto 2021 (£k) | Indicative from 2021 (£k) | RFCC Local levy (£k) | Public/Private identified (incl. Internal Drainage Board Precept, £k) | Further Required (£k) | Estimated Total Project Cost (£k) | Estimated earliest construction start | GiA (£k) | RFCC local levy (£k) | Public/Private (incl. Internal Drainage Board Precept, £k) | Other funding contributions Required (£k) | from flooding | from coastal erosion | from flooding | from coastal erosion | Economic benefits (Net Present Value, £k) | Other benefits / reason for the scheme including estimate of householders better protected | NPN
a. Projects in development, expected to start construction in future years, subject to approval of a full business case.
St Neots Brook Street Flood Risk Management | Environment Agency | Anglian Central | St Neots - Brook Street | 0 | 0 | 0 | 0 | 0 | 0 | 340 | 2021 on | 300 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 2669.4 |  | ACC451E/000A/603A
Tidal river erosion protection | Environment Agency | Anglian Central | Denver, Norfolk | 100 | 0 | 0 | 0 | 0 | 0 | 600 | 2016 to 2018 | 500 | 0 | 0 | 0 | 660 | 0 | 660 | 0 | 4730.027 |  | ACC451E/001A/001F
Godmanchester Surface Water Flood Alleviation | Cambridgeshire County Council | Anglian Central | Huntingdon | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 2016 to 2018 | 110 | 35 | 0 | 0 | 15 | 0 | 15 | 0 | 236.547 |  | ACC451F/000A/015A
Brundall Flood risk management | Environment Agency | Anglian Eastern | Brundall | 0 | 10 | 0 | 0 | 0 | 0 | 260 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 1025.6752 |  | AEC503E/000A/014A
Bungay Flood Alleviation | Environment Agency | Anglian Eastern | Bungay | 0 | 30 | 0 | 0 | 0 | 0 | 480 | 2018 to 2021 | 290 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 7494.317 |  | AEC503E/001A/005A
Cavendish - Communities at Risk | Environment Agency | Anglian Eastern | Cavendish | 0 | 20 | 0 | 0 | 0 | 0 | 450 | 2018 to 2021 | 430 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 9627.073 |  | AEC505E/000A/027A
Debenham Flood Alleviation | Environment Agency | Anglian Eastern | Central Suffolk & North Ipswich | 0 | 0 | 0 | 0 | 0 | 0 | 860.468 | 2016 to 2018 | 640 | 30 | 0 | 0 | 50 | 0 | 50 | 0 | 14202.284 |  | AEC504E/000A/006A
Eastwood Brook - Southend Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Southend-on-Sea | 50 | 0 | 0 | 0 | 0 | 0 | 400 | 2016 to 2018 | 350 | 0 | 0 | 0 | 180 | 0 | 180 | 0 | 97553.831 |  | AEO000E/000A/409A
Great Dunmow Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Great Dunmow, River Chelmer | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 2021 on | 7.6 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 266.66 |  | AEC505E/000A/038A
Great Yeldham Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Great Yeldham, River Colne | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 2021 on | 21.8 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 748.178 |  | AEC505E/000A/040A
Halstead Mill Bypass Gates - Townsford Mill | Environment Agency | Anglian Eastern | Halstead, Essex | 75 | 0 | 0 | 0 | 0 | 0 | 462.1 | 2016 to 2018 | 350 | 0 | 0 | 0 | 190 | 0 | 190 | 0 | 5302.65 |  | AEO000E/002A/192A
Heybridge (near Ingatestone) Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Heybridge (near Ingatestone) , Ingatestone Brook. | 0 | 0 | 0 | 0 | 0 | 0 | 109 | TBC | 21.8 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 |  | AEC506E/000A/034A
Hoveton and Wroxham - Flood Risk Management | Environment Agency | Anglian Eastern | Hoveton, Wroxham on River Bure, Norfolk | 0 | 50 | 0 | 0 | 0 | 0 | 600 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 2086.029 |  | AEC503E/000A/013A
Jaywick Beach Recharge | Environment Agency | Anglian Eastern | Jaywick | 0 | 0 | 0 | 0 | 0 | 0 | 9560 | 2016 to 2018 | 4500 | 0 | 0 | 0 | 2475 | 0 | 2475 | 0 | 77366.762 |  | AES504E/007A/006A
Little Waltham Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Little Waltham, River Chelmer | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2021 on | 8.4 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 228.134 |  | AEC505E/000A/042A
Old Wickford Road, South Woodham Ferrers Property Level Protection | Environment Agency | Anglian Eastern | South Woodham Ferrers, River Crouch | 0 | 0 | 0 | 0 | 0 | 0 | 33 | TBC | 30 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 648.68 |  | AEC506E/000A/044A
Potter Heigham, Bastwick, Martham Ferry and Repps | Environment Agency | Anglian Eastern | Potter Heigham, Bastwick, Martham Ferry and Repps | 0 | 30 | 0 | 0 | 0 | 0 | 450 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 1615.802 |  | AEC503E/000A/012A
Rawreth and Rawreth Shot Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Wickford, River Crouch | 0 | 0 | 0 | 0 | 0 | 0 | 27 | TBC | 5.4 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 457.692 |  | AEC506E/000A/041A
South Creake - Flood Alleviation | Environment Agency | Anglian Eastern | South Creake | 0 | 10 | 0 | 0 | 0 | 0 | 350 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 914.2772 |  | AEC501E/001A/005A
West Clacton to Jaywick Sea defences | Environment Agency | Anglian Eastern | Coast | 70 | 1105 | 0 | 0 | 0 | 0 | 6000 | 2016 to 2018 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77000 |  | AES504E/000A/030A
Weybourne - Flood Alleviation | Environment Agency | Anglian Eastern | Weybourne | 0 | 15 | 0 | 0 | 0 | 0 | 245 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 1100.266 |  | AEC501E/001A/006A
Witham Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Witham, River Brain | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 2021 on | 51.2 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 963.4211 |  | AEC505E/000A/051A
Sudbourne Pumping Station Refurbishment | East Suffolk Internal Drainage Board | Anglian Eastern | Sudbourne, Boulge Hall and Town Maeshes | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 2016 to 2018 | 140 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 4019.7079 |  | AEC504I/001A/013A
Basildon (North West Billericay) Surface Water | Essex County Council | Anglian Eastern | Basildon | 32 | 0 | 0 | 0 | 0 | 0 | 362 | 2016 to 2018 | 300 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 |  | AEO000F/000A/001A
Castle Point- New Thundersley | Essex County Council | Anglian Eastern | Castle Point | 30 | 0 | 0 | 0 | 0 | 0 | 417 | 2016 to 2018 | 359 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 |  | AEO000F/000A/004A
Rochford - Hockley - Surface Water | Essex County Council | Anglian Eastern | Rochford | 0 | 0 | 0 | 0 | 0 | 0 | 140 | TBC | 112 | 0 | 0 | 0 | 130 | 0 | 130 | 0 | 0 |  | AEO000F/000A/006A
Gorleston Coast Protection | Great Yarmouth Borough Council | Anglian Eastern | Coastline of Gorleston Great Yarmouth south of harbour | 0 | 1600 | 0 | 0 | 0 | 0 | 11489 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 500 | 96800 |  | AES502C/002A/001A
Cromer Sustainable Urban Drainage Retrofit | Norfolk CC | Anglian Eastern | Cromer | 0 | 16 | 0 | 10 | 0 | 0 | 825 | 2016 to 2018 | 750 | 40 | 0 | 0 | 350 | 0 | 350 | 0 | 4723.165 |  | AEC501F/000A/005A
Hemsby Flood Risk Mitigation | Norfolk CC | Anglian Eastern | Hemsby, NR29 4NH | 0 | 0 | 0 | 50 | 0 | 0 | 275 | 2016 to 2018 | 185 | 40 | 0 | 0 | 90 | 0 | 90 | 0 | 1129.662 |  | AEC501E/000A/010A
North Walsham Sustainable Urban Drainage Retrofit | Norfolk CC | Anglian Eastern | North Walsham | 0 | 0 | 0 | 50 | 0 | 0 | 525 | 2016 to 2018 | 365 | 81 | 0 | 0 | 220 | 0 | 220 | 0 | 2992.548 |  | AEC501F/000A/004A
Boxford Flood Risk Management | Suffolk County Council | Anglian Eastern | Boxford, Suffolk - ordinary water course | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2016 to 2018 | 70 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 1462.848 |  | AEO000E/000A/593A
Sudbury Great Cornard flood risk management | Suffolk County Council | Anglian Eastern | Sudbury & Great Cornard | 0 | 40 | 0 | 20 | 0 | 0 | 1060 | 2018 to 2021 | 500 | 0 | 0 | 0 | 0 | 0 | 390 | 0 | 9081.585 |  | AEC503F/000A/003A
Stanford-le-Hope Surface Water Flood Alleviation | Thurrock Borough Council | Anglian Eastern | Stanford-le-Hope | 75 | 0 | 0 | 0 | 0 | 0 | 1160 | 2016 to 2018 | 1050 | 0 | 0 | 0 | 1145 | 0 | 1145 | 0 | 9567 |  | AEO000E/000A/410A
Fossbank Floodwall works, Lincoln | Environment Agency | Anglian Northern | Lincoln | 25 | 0 | 0 | 0 | 0 | 0 | 300 | 2016 to 2018 | 225 | 0 | 0 | 0 | 345 | 0 | 345 | 0 | 2025.0491 |  | ANC403E/000A/074A
Greatford Flood Alleviation | Environment Agency | Anglian Northern | Greatford | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2018 to 2021 | 100 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 240 |  | ANC404E/000A/055A
Humber - Immingham to Freshney sea defence improvements | Environment Agency | Anglian Northern | Immingham to Grimsby | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 2021 on | 2500 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 206816.6035 |  | ANS399E/001A/021A
Humber - Cleethorpes & Humberston | Environment Agency | Anglian Northern | Cleethorpes, Humberston and Tetney | 0 | 110 | 0 | 0 | 0 | 0 | 4510 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 45365 |  | ANS399E/001A/012A
Humber - Halton and Killingholme Marshes | Environment Agency | Anglian Northern | East Halton & Killingholme | 300 | 0 | 0 | 0 | 0 | 0 | 12400 | 2016 to 2018 | 6600 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 542687 |  | ANS399E/001A/016A
South Ferriby Pointing Doors | Environment Agency | Anglian Northern | South Ferriby | 770 | 0 | 0 | 0 | 0 | 0 | 770 | 2018 to 2021 | 0 | 0 | 0 | 0 | 170 | 0 | 170 | 0 | 23239.5631 |  | ANS399E/001A/027A
Wainfleet Relief Channel | Environment Agency | Anglian Northern | Wainfleet | 5 | 0 | 0 | 0 | 0 | 0 | 1840 | 2016 to 2018 | 611.648 | 1138.352 | 0 | 0 | 65 | 0 | 65 | 0 | 8799 |  | ANC402E/000A/018A
Works Arising from Upper Witham Strategy Review | Environment Agency | Anglian Northern | Upper Witham | 0 | 150 | 0 | 0 | 0 | 0 | 900 | 2016 to 2018 | 700 | 0 | 0 | 0 | 0 | 0 | 390 | 0 | 4896.4303 |  | ANC403E/002A/003A
Works Arising from Witham Opportunity Study - Lower | Environment Agency | Anglian Northern | River Witham, Lincs | 0 | 100 | 0 | 0 | 0 | 0 | 750 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 0 | 6721.6247 |  | ANC403E/003C/001A
Sutton St James Pumping Station Refurbishment | South Holland Internal Drainage Board | Anglian Northern | PUMPING STATION ON SOUTH SIDE OF SOUTH HOLLAND MAIN DRAIN BETWEEN CLIFTONS BRIDGE AND REDHOUSE BRIDGE NEAR SUTTON ST JAMES | 0 | 30 | 0 | 0 | 0 | 0 | 490 | 2018 to 2021 | 460 | 0 | 0 | 0 | 135 | 0 | 135 | 0 | 29814.9325 |  | ANC405I/001A/050A
Aubourn Pumping Station Refurbishment | Upper Witham Internal Drainage Board | Anglian Northern | EA Brant Washland Site | 0 | 9 | 11 | 0 | 0 | 0 | 146 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8600.767 |  | ANC403I/002A/003A
Sand Syke Pumping Station Refurbishment | Upper Witham Internal Drainage Board | Anglian Northern | Bassingham | 0 | 20 | 0 | 0 | 0 | 0 | 138 | 2021 on | 27 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5965.6641 |  | ANC403I/002A/023A
Thorpe Pumping Station Environmental/Efficiency | Upper Witham Internal Drainage Board | Anglian Northern | Saxilby | 0 | 2 | 0 | 0 | 0 | 0 | 27 | 2018 to 2021 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.91 |  | ANC403I/002A/038A
Billinghay Pumping Station Refurbishment | Witham 1st Internal Drainage Board | Anglian Northern | Tattershall Bridge, Lincolnshire | 0 | 9 | 11 | 0 | 0 | 0 | 116 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 3157.0015 |  | ANC403I/002A/041A
Metheringham Pumping Station Refurbishment | Witham 1st Internal Drainage Board | Anglian Northern | Sots Hole, Lincolnshire | 0 | 10 | 0 | 0 | 0 | 0 | 143 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 2954.7074 |  | ANC403I/002A/046A
North Kyme Pumping Station Refurbishment | Witham 1st Internal Drainage Board | Anglian Northern | North Kyme, Lincolnshire | 0 | 9 | 0 | 0 | 0 | 0 | 71 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 2870.4133 |  | ANC403I/002A/048A
Culverted Watercourse Lining | Witham 4th District Internal Drainage Board | Anglian Northern | Town | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 2016 to 2018 | 135 | 0 | 0 | 0 | 100 | 0 | 135 | 0 | 1710.278 |  | ANC403I/002A/032A
Alney Island Improvements, River Severn | Environment Agency | English Severn and Wye | Pool Meadow Alney Island Gloucester. East channel river Severn | 0 | 0 | 0 | 50 | 0 | 0 | 400 | 2021 on | 50 | 280 | 0 | 0 | 0 | 0 | 60 | 0 | 92 |  | SNC001E/000A141A
Badsey Brook Flood Risk (Wickhamford) | Environment Agency | English Severn and Wye | Wickhamford | 0 | 0 | 0 | 50 | 0 | 0 | 750 | 2021 on | 84 | 591 | 0 | 0 | 0 | 0 | 20 | 0 | 166 |  | SNC001E/001A/016A
Bishops Frome, Herefordshire Property Level Protection | Environment Agency | English Severn and Wye | Bishops Frome Herefordshire | 0 | 0 | 0 | 8 | 0 | 0 | 65.99 | 2018 to 2021 | 14 | 30.1 | 0 | 0 | 0 | 0 | 10 | 0 | 264 |  | SNC001E/000A158A
Canley, Canley Brook Flood Alleviation | Environment Agency | English Severn and Wye | Coventry, Canley Brook | 0 | 27 | 0 | 48 | 0 | 0 | 500 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 407.357 |  | SNC001E/000A134A
Cleobury Mortimer Pudding Brook Flood Alleviation | Environment Agency | English Severn and Wye | Cleobury Mortimer | 0 | 0 | 0 | 29 | 0 | 0 | 329 | 2018 to 2021 | 179 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 279 |  | SNC001E/000A/050A
Diglis, Worcs Property Level Protection, River Severn | Environment Agency | English Severn and Wye | Diglis,Worcester, River Severn | 0 | 0 | 0 | 10 | 0 | 0 | 120 | 2018 to 2021 | 76 | 17.5 | 0 | 0 | 15 | 0 | 20 | 0 | 480 |  | SNC001E/000A149A
Dog Lane Pumping Station refurbishment | Environment Agency | English Severn and Wye | Bewdley, River Severn | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 2016 to 2018 | 120 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 946.719 |  | SNC001E/000A126A
Evesham Property Level Protection, River Avon | Environment Agency | English Severn and Wye | Evesham | 0 | 0 | 0 | 120 | 0 | 0 | 852 | 2016 to 2018 | 67 | 265 | 0 | 0 | 0 | 0 | 110 | 0 | 3408 |  | SNC001E/000A151A
Ewyas Harold | Environment Agency | English Severn and Wye | Ewyas Harold, Herefordshire on the Dulas book | 0 | 35 | 20 | 55 | 0 | 0 | 710 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 |  | SNC001E/000A143A
Himbleton, Bow Brook, Property Level Protection | Environment Agency | English Severn and Wye | Himbleton | 0 | 0 | 0 | 29 | 0 | 0 | 199 | 2018 to 2021 | 60 | 50 | 0 | 0 | 0 | 0 | 25 | 0 | 550 |  | SNC001E/000A/052A
Hunters Way, Droitwich Property Level Protection, Elmbridge Brook | Environment Agency | English Severn and Wye | Droitwich, Elmbridge Brook | 0 | 0 | 0 | 11 | 0 | 0 | 176 | 2018 to 2021 | 43 | 39 | 0 | 0 | 10 | 0 | 20 | 0 | 484 |  | SNC001E/000A153A
Kenilworth, Finham Brook, Property Level Protection | Environment Agency | English Severn and Wye | Kenilworth | 0 | 20 | 0 | 0 | 0 | 0 | 132 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 940 |  | SNC001E/000A/055A
River Lugg, Leominster Flood Alleviation Improvements | Environment Agency | English Severn and Wye | Leominster, Herefordshire | 0 | 55 | 0 | 150 | 0 | 0 | 2589 | 2016 to 2018 | 1924 | 400 | 0 | 0 | 830 | 0 | 830 | 0 | 7424 |  | SNC001E/000A/054A
Severn Stoke Flood Alleviation, River Severn | Environment Agency | English Severn and Wye | Severn Stoke, Worcs | 0 | 46 | 45 | 20 | 0 | 0 | 940 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 470 |  | SNC001E/000A139A
Shrewsbury, River Severn Property Level Protection | Environment Agency | English Severn and Wye | Shrewsbury, River Severn | 0 | 0 | 0 | 12.5 | 0 | 0 | 150 | 2018 to 2021 | 72.5 | 47.5 | 0 | 0 | 0 | 0 | 25 | 0 | 600 |  | SNC001E/000A152A
Slow the Flow - Shropshire Rivers | Environment Agency | English Severn and Wye | Shropshire/Herefordshire. | 0 | 70 | 0 | 0 | 0 | 0 | 470 | 2016 to 2018 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 |  | SNK002E/000A001A
Warwick, St Johns Brook, Flood Alleviation | Environment Agency | English Severn and Wye | St Johns Brook, Warwick | 0 | 92 | 0 | 92 | 0 | 0 | 1150 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 0 | 4046.01 |  | SNC001E/000A132A
Worcester Property Level Protection, River Severn | Environment Agency | English Severn and Wye | Worcester, River Severn | 0 | 0 | 0 | 17 | 0 | 0 | 204 | 2018 to 2021 | 130 | 20 | 0 | 0 | 30 | 0 | 35 | 0 | 816 |  | SNC001E/000A148A
Gosford Brook, Brimfield, Flood Alleviation | Herefordshire Council | English Severn and Wye | Brimfield, Herefordshire | 0 | 0 | 0 | 0 | 0 | 0 | 121.3 | 2021 on | 17 | 25 | 0 | 0 | 0 | 0 | 30 | 0 | 411 |  | SNC001F/000A/014A
Wesley Brook, Shifnal, Flood Alleviation | Shropshire Council | English Severn and Wye | Shifnal | 0 | 0 | 0 | 0 | 0 | 0 | 532 | 2018 to 2021 | 272 | 250 | 0 | 0 | 85 | 0 | 85 | 0 | 2058 |  | SNC001F/000A/031A
Coal Brook, Coalbrookdale, Flood Relief | Telford and Wrekin Unitary Authority | English Severn and Wye | Coalbrookdale, R Severn | 0 | 0 | 0 | 0 | 0 | 0 | 241 | 2018 to 2021 | 201 | 30 | 0 | 0 | 40 | 0 | 40 | 0 | 1085 |  | SNC001F/000A/044A
Ironbridge Gorge Indvidual Property Protection | Telford and Wrekin Unitary Authority | English Severn and Wye | Ironbridge | 0 | 0 | 0 | 20 | 0 | 0 | 292 | 2018 to 2021 | 25 | 147 | 0 | 0 | 40 | 0 | 40 | 0 | 848 |  | SNC001F/000A/043A
Appleby Flood Gate Replacement | Environment Agency | North West | Appleby, Cumbria | 0 | 50 | 0 | 0 | 0 | 0 | 400 | 2018 to 2021 | 350 | 0 | 0 | 0 | 180 | 0 | 180 | 0 | 5005 |  | NWC004E/000A/017A
Arnside Embankment | Environment Agency | North West | Arnside, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 2016 to 2018 | 300 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 3291 |  | NWS003E/000A/010A
Astley Bridge, Bolton | Environment Agency | North West | Bolton, Greater Manchester | 0 | 70 | 100 | 0 | 0 | 0 | 1070 | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 0 | 6430 |  | NWC005E/005A/010A
Braithwaite Embankment Refurbishment | Environment Agency | North West | Braithwaite, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 2018 to 2021 | 250 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 625 |  | NWC002E/000A/015A
Clarington Brook Culvert, Wigan | Environment Agency | North West | Wigan, Greater Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2018 to 2021 | 500 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 715 |  | NWC003E/001A/005A
Common Lane Bk, Leigh | Environment Agency | North West | Common Lane Bk, Leigh Greater Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 300 | TBC | 213 | 87 | 0 | 0 | 45 | 0 | 45 | 0 | 3546 |  | NWC008E/003A/002C
Cringle Bk, Ladybarn | Environment Agency | North West | Ladybarn, Withington, Greater Manchester | 0 | 225 | 0 | 0 | 0 | 0 | 2025 | 2016 to 2018 | 1800 | 0 | 0 | 0 | 265 | 0 | 265 | 0 | 5875 |  | NWC011E/003A/014A
Downholland Bk, Formby | Environment Agency | North West | Formby, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 100 | 0 | 0 | 0 | 130 | 0 | 130 | 0 | 1364 |  | NWC001E/001A/012A
Eastford Road, Warrington | Environment Agency | North West | Lower Walton, Warrington | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 2018 to 2021 | 75 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 795 |  | NWC008E/002A/009A
Gosling Sike, Carlisle | Environment Agency | North West | Carlisle, Cumbria | 0 | 25 | 0 | 0 | 0 | 0 | 515 | TBC | 490 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 2735 |  | NWC004E/000A/019A
Grasmere, River Rothay | Environment Agency | North West | Grasmere, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 150 | TBC | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 634 |  | NWC006E/000A/008A
Hillylaid Pool, Thornton | Environment Agency | North West | Thornton, Wyre | 0 | 100 | 0 | 0 | 0 | 0 | 1852 | 2016 to 2018 | 1530 | 0 | 0 | 0 | 1905 | 0 | 1905 | 0 | 131300 |  | NWC013E/000A/003A
Keckwick Brook, Wharford Farm, Runcorn | Environment Agency | North West | Runcorn, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 2018 to 2021 | 35 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 232 |  | NWC012E/000A/007A
Mill Beck, Barrow in Furness | Environment Agency | North West | Barrow-in-Furness, Cumbria | 0 | 50 | 0 | 0 | 0 | 0 | 650 | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 2030 |  | NWC010E/000A/012A
River Darwen, Darwen | Environment Agency | North West | Darwen, Lancashire | 240 | 0 | 0 | 0 | 0 | 0 | 2050 | 2016 to 2018 | 1760 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 15637 |  | NWC009E/002A/001A
River Roch, Rochdale & Littleborough | Environment Agency | North West | Rochdale, River Roch, Greater Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 3919 | 2016 to 2018 | 3680 | 0 | 0 | 0 | 155 | 0 | 155 | 0 | 54221 |  | NWC005E/002A/008A
Thelwall, Warrington | Environment Agency | North West | Thelwall, Warrington | 0 | 0 | 0 | 0 | 0 | 0 | 50 | TBC | 50 | 0 | 0 | 0 | 0 | 0 | 190 | 0 | 4900 |  | NWC008E/002A/007A
Ulverston, Dragley Beck Rydal Road | Environment Agency | North West | Ulverston,Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 500 | TBC | 500 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 2414 |  | NWO006E/000A/003A
Maryport Flood and Coastal Protection | Allerdale BC | North West | Maryport, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2016 to 2018 | 30 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 10307.325 |  | NWS004C/000A/014A
A6 Market Street, Danebank | Cheshire East Council | North West | Disley, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2021 on | 20 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 455.583 |  | NWC012F/000A/039A
Blakelow Road, Macclesfield | Cheshire East Council | North West | Macclesfield, Cheshire | 0 | 20 | 0 | 0 | 0 | 0 | 120 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 805.971 |  | NWC011F/008A/018A
Cheshire Asset Inspection/CCTV Survey | Cheshire East Council | North West | Cheshire East | 0 | 0 | 0 | 0 | 0 | 0 | 250 | TBC | 100 | 0 | 0 | 0 | 100 | 0 | 400 | 0 | 4565.051 |  | NWC012F/000A/028A
Cheshire East ordinary waterourse capital maintenance | Cheshire East Council | North West | Cheshire East | 0 | 50 | 0 | 0 | 0 | 0 | 300 | TBC | 100 | 0 | 0 | 0 | 90 | 0 | 175 | 0 | 2940.9 |  | NWC012F/000A/048A
Excalibur Brook, Alsager | Cheshire East Council | North West | Alsager, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 2016 to 2018 | 1000 | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 7839.325 |  | NWC012F/000A/037A
Pearl Street, Prestbury | Cheshire East Council | North West | Presbury, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2018 to 2021 | 50 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 207.791 |  | NWC011F/008A/020A
Tributaries of Poynton Brook, Poynton | Cheshire East Council | North West | Poynton, Cheshire | 0 | 50 | 0 | 0 | 0 | 0 | 300 | 2018 to 2021 | 250 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 2477.914 |  | NWC012F/000A/042A
St Bees Coastal Erosion Protection | Copeland BC | North West | St Bees, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2021 on | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 1068.985 |  | NWS004C/000A/009A
Whitehaven Coastal Erosion and Flooding Protection | Copeland BC | North West | Whitehaven, Cumbria | 0 | 50 | 0 | 0 | 0 | 0 | 300 | 2018 to 2021 | 250 | 0 | 0 | 0 | 105 | 0 | 105 | 0 | 5784.167 |  | NWS004C/000A/011A
Carrus Green, Kendal | Cumbria CC | North West | Carrus Green , Kendal | 0 | 0 | 0 | 0 | 0 | 0 | 65 | TBC | 20 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 293 |  | NWC006F/000A/002A
Fairways, Seascale Attenuation | Cumbria CC | North West | Seascale, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 2021 on | 215 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 357.541 |  | NWS004C/000A/017A
Gamblesby, River Eden | Cumbria CC | North West | Gamblesby, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 2018 to 2021 | 75 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 458.786 |  | NWC004F/000A/004A
Gosforth, West Cumbria | Cumbria CC | North West | Gosforth, West Cumbria | 0 | 70 | 0 | 0 | 0 | 0 | 610 | 2016 to 2018 | 540 | 0 | 0 | 0 | 190 | 0 | 190 | 0 | 1149.341 |  | NWC010F/000A/004A
Low Beckside, Kirkby in Furness | Cumbria CC | North West | Low Beckside, Kirkby in Furness | 0 | 10 | 0 | 0 | 0 | 0 | 77 | TBC | 67 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 456 |  | NWC010F/000A/003A
Moresby Watercourse investigation | Cumbria CC | North West | Moresby parks | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2021 on | 30 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 716.721 |  | NWC002F/001A/004A
Parton fluvial and surface water flooding | Cumbria CC | North West | Parton, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 537.541 |  | NWC002F/001A/005A
Penrith Road, Keswick | Cumbria CC | North West | Keswick, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 2018 to 2021 | 210 | 0 | 0 | 0 | 95 | 0 | 95 | 0 | 2156 |  | NWC002F/001A/001A
Railway Tce, Seascale | Cumbria CC | North West | Seascale, Cumbria | 0 | 20 | 0 | 0 | 0 | 0 | 250 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 337.541 |  | NWS004C/000A/018A
Ravenglass, Cumbria | Cumbria CC | North West | Ravenglass, Cumbria | 0 | 30 | 0 | 0 | 0 | 0 | 165 | TBC | 135 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 910 |  | NWC010F/000A/002A
Ulverston Urban Drainage | Cumbria CC | North West | Ulverston, Cumbria | 0 | 100 | 0 | 0 | 0 | 0 | 615 | 2021 on | 515 | 0 | 0 | 0 | 205 | 0 | 205 | 0 | 6659.715 |  | NWC006F/000A/003A
Bacup Old Brook, Higher Clough | Lancashire County Council | North West | Higher Clough, Upper Irwell | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2016 to 2018 | 8 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 172 |  | NWC009F/000A/023A
Boundary Edge Brook, Rossendale | Lancashire County Council | North West | Edenfield, Rossendale | 0 | 0 | 0 | 0 | 0 | 0 | 11.6 | 2018 to 2021 | 11.6 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 108.4 |  | NWC009F/000A/021A
Burnley Ordinary Watercourse Study | Lancashire County Council | North West | Burnley, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 2016 to 2018 | 15.5 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 2780.5 |  | NWC009F/000A/029A
Burnley Road East, Rossendale | Lancashire County Council | North West | Rossendale, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 2016 to 2018 | 25 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 575 |  | NWC009F/000A/027A
Chorley Level 2 Surface Water Management Plan | Lancashire County Council | North West | Chorley, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 840 |  | NWC009F/000A/037A
Cribden Clough, Clough End, Haslingden | Lancashire County Council | North West | Haslingden, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2018 to 2021 | 10 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 110 |  | NWC009F/000A/026A
Lancaster Ordinary Watercourse Study | Lancashire County Council | North West | Lancaster | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 2016 to 2018 | 16 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 1714 |  | NWC009F/000A/031A
Pendle Ordinary Watercourse Study | Lancashire County Council | North West | Pendle, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 2018 to 2021 | 13 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 1013 |  | NWC009F/000A/033A
South Ribble Ordinary Watercourse Study | Lancashire County Council | North West | South Ribble | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 2016 to 2018 | 15.5 | 0 | 0 | 0 | 75 | 0 | 75 | 0 | 2180.5 |  | NWC009F/000A/034A
West Lancashire Ordinary Watercourse Study | Lancashire County Council | North West | West Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2018 to 2021 | 10 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 1346 |  | NWC009F/000A/035A
Wyre Ordinary Watercourse Study | Lancashire County Council | North West | Wyre | 0 | 0 | 0 | 0 | 0 | 0 | 18.5 | 2016 to 2018 | 18.5 | 0 | 0 | 0 | 175 | 0 | 175 | 0 | 5129.5 |  | NWC009F/000A/036A
Cote Beck, Halton Flow Control | Lancaster City Council | North West | Halton, Lancaster | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 2018 to 2021 | 26 | 39 | 0 | 0 | 5 | 0 | 5 | 0 | 115 |  | NWC007F/000A/006C
Calve Croft, Sharston, Manchester | Manchester City Council | North West | Sharston, Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 2016 to 2018 | 265 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 4179.662 |  | NWC011F/008A/022A
Manchester Trash Screen and Culvert Rehabilitation | Manchester City Council | North West | Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 2016 to 2018 | 300 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 4144.662 |  | NWC005F/000A/017A
Rusholme and Moss Side Surface Water Management | Manchester City Council | North West | Rusholme and Moss Side - Dog Kennel Brook and Rush Brook | 0 | 100 | 0 | 0 | 0 | 0 | 600 | 2016 to 2018 | 500 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 3844.662 |  | NWC011F/008A/021A
Shaw, Cringle, Ley and Willow Brook | Manchester City Council | North West | Withington, Greater Manchester | 0 | 100 | 0 | 0 | 0 | 0 | 600 | 2016 to 2018 | 500 | 0 | 0 | 0 | 115 | 0 | 115 | 0 | 3844.662 |  | NWC011F/008A/009A
Sumner Street, Shaw, Oldham | Oldham Council | North West | Shaw, Oldham | 0 | 15 | 0 | 0 | 0 | 0 | 135 | 2018 to 2021 | 120 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 525 |  | NWC005F/000A/042A
Gore Avenue Groundwater, Salford | Salford City Council | North West | Weaste, Salford | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2018 to 2021 | 125 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 1075 |  | NWC005F/000A/037A
Groundwater Study - Castlewood Road, Kersal | Salford City Council | North West | Castlewood Road, Kersal | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 1230 |  | NWC005F/000A/035A
Trevor Road, Winton, Salford | Salford City Council | North West | Winton, Salford | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2016 to 2018 | 70 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 380 |  | NWC005F/000A/036A
Merseyside Strategic Groundwater Flood Risk Pilot Strategy | Sefton Council | North West | Merseyside, Sefton, Liverpool, Wirral, Knowsley | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 2016 to 2018 | 264 | 0 | 0 | 0 | 85 | 0 | 100 | 0 | 616 |  | NWC001F/000A/044A
Sefton Flood Storage and Wet Habitat Creation Programme | Sefton Council | North West | Sefton, Southport, Ainsdale, Formby, Crosby, Hightown, Bootle | 0 | 15 | 0 | 0 | 0 | 0 | 105 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 |  | NWC001F/000A/045A
Sefton Strategic Surface Water Management Plan Delivery Programme | Sefton Council | North West | Sefton, Southport, Ainsdale, Formby, Crosby, Hightown, Bootle | 0 | 290 | 0 | 0 | 0 | 0 | 2040 | 2018 to 2021 | 250 | 0 | 0 | 0 | 75 | 0 | 340 | 0 | 30790 |  | NWC001F/000A/043A
Grappenhall, Warrington | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 15 | 0 | 0 | 0 | 0 | 315 | 2018 to 2021 | 300 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 1811.442 |  | NWC008F/000A/065A
Heath Lane, Croft, Warrington | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 10 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 80 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 585.061 |  | NWC008F/000A/064A
Hillfoot Crescent, Stockton Heath, Warrington | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2018 to 2021 | 20 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 123.344 |  | NWC008F/000A/082A
Orford, Warrington | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 40 | 0 | 0 | 0 | 0 | 390 | 2018 to 2021 | 350 | 0 | 0 | 0 | 75 | 0 | 75 | 0 | 960 |  | NWC008F/000A/066A
Padgate Lane, Padgate, Warrington | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2018 to 2021 | 50 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 308.36 |  | NWC008F/000A/083A
Stocks Lane, Penketh, Warrington | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 15 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 92.508 |  | NWC008F/000A/084A
Abbey Brook (The Pines Estate), Ormskirk | West Lancashire Borough Council | North West | Abbey Brook, Ormskirk | 0 | 0 | 0 | 0 | 0 | 0 | 640 | TBC | 567 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 8950 |  | NWC001F/000A/002A
Wyre Dune and Beach Management | Wyre Borough Council | North West | Fylde Coast Lancashire, Cleveleys to Fleetwood Ferry Dock | 0 | 4293 | 0 | 0 | 0 | 0 | 40448 | 2016 to 2018 | 5380 | 0 | 0 | 0 | 1915 | 0 | 1915 | 0 | 126897 |  | NWS003C/000A/002S
Acomb (Red Burn) Flood Alleviation | Environment Agency | Northumbria | Acomb, Red Burn, | 76.6 | 0 | 0 | 0 | 0 | 0 | 631.25 | 2018 to 2021 | 220.7 | 293.95 | 0 | 0 | 45 | 0 | 45 | 0 | 881 |  | NOC304E/000A/036A
Blackhall Mill Asset Replacement | Environment Agency | Northumbria | Blackhall Mill, River Derwent, Gateshead, Tyne & Wear | 0 | 25.9 | 0 | 0 | 0 | 0 | 572.2 | 2018 to 2021 | 546.3 | 0 | 0 | 0 | 75 | 0 | 75 | 0 | 3.622 |  | NOC304E/000A/042A
Chester-le-Street Deculvert | Environment Agency | Northumbria | Chester-le-Street | 0 | 0 | 0 | 0 | 0 | 0 | 563.1 | 2018 to 2021 | 38.1 | 455 | 0 | 0 | 25 | 0 | 25 | 0 | 23.2 |  | NOC305E/000A/029A
Croft (downstream of bridge) | Environment Agency | Northumbria | Croft-on-Tees, River Tees | 0 | 0 | 0 | 35 | 0 | 0 | 367.6 | 2018 to 2021 | 332.6 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 675 |  | NOC306E/000A/055A
Guisborough Flood Alleviation | Environment Agency | Northumbria | Guisborough, Skelton Beck/Chapel Beck | 0 | 0 | 0 | 130 | 0 | 0 | 1209 | 2016 to 2018 | 209 | 200 | 0 | 0 | 95 | 0 | 95 | 0 | 3834 |  | NOC306E/000A/020A
Hurworth Place | Environment Agency | Northumbria | Hurworth Place, River Tees | 0 | 0 | 0 | 60 | 0 | 0 | 305.85 | 2018 to 2021 | 75.85 | 170 | 0 | 0 | 15 | 0 | 15 | 0 | 19.5 |  | NOC306E/000A/058A
Lanchester | Environment Agency | Northumbria | Lanchester | 0 | 0 | 0 | 0 | 0 | 0 | 541.216 | 2018 to 2021 | 38.716 | 502.5 | 0 | 0 | 15 | 0 | 15 | 0 | 302.5 |  | NOC305E/000A/052A
Marton West Beck - Middlesbrough | Environment Agency | Northumbria | Middlesbrough, Marton West Beck, d/s of Albert Park | 0 | 0 | 0 | 0 | 0 | 0 | 253.215 | 2018 to 2021 | 73.215 | 180 | 0 | 0 | 55 | 0 | 55 | 0 | 1.861 |  | NOC306E/001A/009A
Oxney Flatts Floodbank | Environment Agency | Northumbria | Oxney Flatts, River Tees | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 2018 to 2021 | 170 | 0 | 0 | 0 | 70 | 0 | 70 | 0 | 221.304 |  | NOC306E/000A/043A
Staindrop Flood Alleviation | Environment Agency | Northumbria | Staindrop, Langley Beck/Sudburn Beck/Moor Beck | 0 | 0 | 0 | 0 | 0 | 0 | 501 | 2016 to 2018 | 188 | 263 | 0 | 0 | 35 | 0 | 35 | 0 | 142.656 |  | NOC306E/000A/025A
Stokesley Flood Alleviation | Environment Agency | Northumbria | Stokesley, River leven | 0 | 105.93 | 0 | 100 | 0 | 0 | 1058.16 | 2016 to 2018 | 612.23 | 240 | 0 | 0 | 260 | 0 | 260 | 0 | 1714 |  | NOC306E/000A/026A
Wooler Water Defence Replacement and Reallignment | Environment Agency | Northumbria | Wooler, Northumberland. River : Wooler Water | 0 | 25 | 0 | 60 | 0 | 0 | 1261 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 18905 |  | NOC302E/000A/004A
Yarm Flood Gate replacement | Environment Agency | Northumbria | Yarm on the River Tees | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 2016 to 2018 | 220 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 27.523 |  | NOC306E/000A/052A
Cherry Banks, Chester le Street | Durham County Council | Northumbria | 5 Cherry Banks, Chester le Street | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 2018 to 2021 | 4.8 | 0.6 | 0 | 0 | 1 | 0 | 1 | 0 | 25 |  | NOC305F/000A/023A
Craigland Villas, Sacriston | Durham County Council | Northumbria | Rear of 1-10, Craigland Villas, Sacriston | 0 | 0 | 0 | 0 | 0 | 0 | 46.6 | 2018 to 2021 | 46.6 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 280 |  | NOC305F/000A/025A
Dene Crescent, Sacriston | Durham County Council | Northumbria | Rear of 1-8 Dene Crescent, Sacriston | 0 | 0 | 0 | 0 | 0 | 0 | 46.6 | 2016 to 2018 | 46.6 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 190 |  | NOC305F/000A/026A
Dipton Surface Water Flood Management | Durham County Council | Northumbria | Dipton | 0 | 0 | 0 | 0 | 0 | 0 | 42.5 | 2018 to 2021 | 37.5 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 107.5 |  | NOC304F/000A/017A
Dunelm Walk, Leadgate | Durham County Council | Northumbria | 83 - 91 Dunelm Walk, Leadgate | 0 | 0 | 0 | 0 | 0 | 0 | 32.1 | 2018 to 2021 | 20.1 | 12 | 0 | 0 | 5 | 0 | 5 | 0 | 115 |  | NOC305F/000A/027A
Kingfisher Close, Esh Winning | Durham County Council | Northumbria | Esh Winning - Hedleyhope Burn | 0 | 0 | 0 | 0 | 0 | 0 | 155.2 | 2018 to 2021 | 67.2 | 88 | 0 | 0 | 10 | 0 | 10 | 0 | 175 |  | NOC305F/000A/032A
Hartlepool Marina Study and Construction (North Pier) | Hartlepool Borough Council | Northumbria | Hartlepool Marina | 0 | 0 | 0 | 0 | 0 | 0 | 3618 | 2018 to 2021 | 1171.156 | 0 | 0 | 0 | 0 | 360 | 0 | 360 | 25986 |  | NOS306C/000A/001A
Jesmond Gardens | Hartlepool Borough Council | Northumbria | Hartlepool | 0 | 0 | 0 | 0 | 0 | 0 | 644.2 | 2016 to 2018 | 579.2 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 9330 |  | NOC306F/000A/028A
Riverston Close | Hartlepool Borough Council | Northumbria | Hartlepool | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 2016 to 2018 | 195 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 5885 |  | NOC306F/000A/029A
Tynebrook Avenue | Hartlepool Borough Council | Northumbria | Hartlepool | 0 | 0 | 0 | 0 | 0 | 0 | 233.6 | 2016 to 2018 | 218.6 | 15 | 0 | 0 | 25 | 0 | 25 | 0 | 3282.5 |  | NOC306F/000A/030A
Little Shore Improvement | Northumberland County Council | Northumbria | Amble | 0 | 22.2 | 0 | 20 | 0 | 0 | 240 | 2018 to 2021 | 197.8 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 1788.339 |  | NOS301C/000A/065A
Rothbury Surface Water Flood Alleviation | Northumberland County Council | Northumbria | Rothbury, Northumberland | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 2016 to 2018 | 25 | 15 | 0 | 0 | 10 | 0 | 10 | 0 | 207.695 |  | NOC301F/000A/006A
Warkworth Harbour North Pier Geophysical and Ground Investigations | Northumberland County Council | Northumbria | Warkworth Harbour, Amble, Northumberland | 0 | 53.6 | 57.4 | 0 | 0 | 0 | 645.4 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 3400 |  | NOS301C/000A/020A
North Skelton Inland Flood Alleviation | Redcar and Cleveland Borough Council | Northumbria | North Skelton | 0 | 0 | 0 | 10 | 0 | 0 | 165.3 | 2018 to 2021 | 155.3 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 230 |  | NOC352F/000A/001A
Property Level Protection - Don View and Newcastle Road | South Tyneside Council | Northumbria | South Shields | 0 | 8.3 | 0 | 0 | 0 | 0 | 42.6 | 2016 to 2018 | 34.3 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 200 |  | NOC304F/000A/034A
Property Level Protection - Elberfeld Court, Jarrow | South Tyneside Council | Northumbria | South Shields | 0 | 24 | 0 | 0 | 0 | 0 | 126.8 | 2016 to 2018 | 102.8 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 600 |  | NOC304F/000A/049A
Halidon Way, Billingham | Stockton-on-Tees Borough Council | Northumbria | Halidon Way, Billingham | 0 | 0 | 0 | 0 | 0 | 0 | 51.7 | 2016 to 2018 | 41 | 10.7 | 0 | 0 | 10 | 0 | 10 | 0 | 49 |  | NOC306F/000A/023A
Ings lane | Stockton-on-Tees Borough Council | Northumbria | Ings Lane, Yarm | 0 | 0 | 0 | 0 | 0 | 0 | 6.2 | 2018 to 2021 | 0.8 | 5.4 | 0 | 0 | 1 | 0 | 1 | 0 | 24 |  | NOC306F/000A/024A
Borrowdale Street - surface water flooding | Sunderland City Council | Northumbria | Sunderland | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 2016 to 2018 | 130 | 50 | 0 | 0 | 10 | 0 | 10 | 0 | 243.719 |  | NOC305F/000A/020A
Hendon Burn Culvert | Sunderland City Council | Northumbria | Sunderland | 0 | 0 | 0 | 10 | 0 | 0 | 160 | 2016 to 2018 | 75 | 75 | 0 | 0 | 20 | 0 | 20 | 0 | 620.257 |  | NOC305F/000A/012A
Hendon Burn Watercourse | Sunderland City Council | Northumbria | Sunderland | 0 | 0 | 0 | 10 | 0 | 0 | 77 | 2016 to 2018 | 7 | 60 | 0 | 0 | 10 | 0 | 10 | 0 | 103.476 |  | NOC305F/000A/029A
Holley Park | Sunderland City Council | Northumbria | Lambton, Washington | 0 | 0 | 0 | 20 | 0 | 0 | 120 | 2016 to 2018 | 20 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 83.6752 |  | NOC305F/000A/031A
Springwell Village - surface water flooding | Sunderland City Council | Northumbria | Sunderland | 0 | 0 | 0 | 50 | 0 | 0 | 259.9 | 2016 to 2018 | 209.9 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 969.644 |  | NOC305F/000A/017A
Bampton Upstream Improvements | Environment Agency | South West | Bampton, Devon | 0 | 50 | 0 | 0 | 0 | 0 | 603 | 2018 to 2021 | 453 | 100 | 0 | 0 | 45 | 0 | 45 | 0 | 5622 |  | SWC013E/000A/076A
Bodmin Town Leat culvert repairs | Environment Agency | South West | Bodmin | 0 | 35 | 0 | 0 | 0 | 0 | 292.2 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2809.347 |  | SWC009E/000A/085A
Chaddlewood screen upgrade | Environment Agency | South West | Plympton | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 2018 to 2021 | 53 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 5006.979 |  | SWS006E/000A/063A
Drakewalls stream culvert inlet screen refurbishments | Environment Agency | South West | Body's Court, Gunnislake | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 2018 to 2021 | 37 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 1113.19 |  | SWC011E/000A/107A
Falmouth tidal | Environment Agency | South West | Falmouth | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 2018 to 2021 | 95 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 1509.315 |  | SWS005E/000A/014A
Ilfracombe Sea | Environment Agency | South West | Ilfracombe | 0 | 50 | 0 | 0 | 0 | 0 | 327 | 2018 to 2021 | 277 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 1353.836 |  | SWC014E/000A/066A
Kenwith Operational Improvements | Environment Agency | South West | River Kenwith, Bideford, Devon. | 0 | 0 | 0 | 0 | 0 | 0 | 575 | 2016 to 2018 | 575 | 0 | 0 | 0 | 665 | 0 | 665 | 0 | 6997.222 |  | SWC014E/000A/069A
Kenwith, Bideford | Environment Agency | South West | Bideford | 0 | 75 | 0 | 0 | 0 | 0 | 1275 | 2018 to 2021 | 1200 | 0 | 0 | 0 | 700 | 0 | 700 | 0 | 2361.702 |  | SWC014E/000A/067A
Latchbrook Impoundment dam refurbishment | Environment Agency | South West | Latchbrook, Saltash | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 2018 to 2021 | 97 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 574.963 |  | SWC011E/000A/109A
Longbrook culvert desilts/ repairs | Environment Agency | South West | Plympton | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 2018 to 2021 | 33 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 716.856 |  | SWC011E/000A/110A
Lympstone Strand Trash Screen Refurbishment | Environment Agency | South West | Wotton Brook, Lympstone | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2016 to 2018 | 244 | 0 | 0 | 0 | 165 | 0 | 165 | 0 | 5881.918 |  | SWC013E/000A/088A
Metcombe | Environment Agency | South West | Tipton St John | 0 | 0 | 0 | 10 | 0 | 0 | 75 | 2018 to 2021 | 21 | 5 | 0 | 0 | 0 | 0 | 10 | 0 | 678.408 |  | SWC012E/000A/050A
Otter Reach Improvements, Newton Poppleford | Environment Agency | South West | Newton Poppleford | 0 | 20 | 0 | 0 | 0 | 0 | 153 | 2018 to 2021 | 133 | 0 | 0 | 0 | 85 | 0 | 85 | 0 | 1184.051 |  | SWC012E/000A/056A
Padstow Gate Refurbishment | Environment Agency | South West | Padstow | 0 | 0 | 0 | 0 | 0 | 0 | 430 | 2016 to 2018 | 380 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 22448.85 |  | SWC010E/000A/097A
Padstow Town Stream Harbour refurbishment | Environment Agency | South West | Padstow Harbour | 0 | 0 | 0 | 0 | 0 | 0 | 296.57 | 2018 to 2021 | 296.57 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 22848.567 |  | SWC010E/000A/108A
Paignton Green Culvert and Pump Refurbishment | Environment Agency | South West | Victoria Stream, Paignton, Devon | 0 | 0 | 0 | 0 | 0 | 0 | 1140 | 2016 to 2018 | 1140 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 12403.532 |  | SWC015E/000A/075A
Paignton Seafront | Environment Agency | South West | Paignton Seafront | 0 | 333 | 0 | 0 | 0 | 0 | 1733 | 2018 to 2021 | 900 | 500 | 0 | 0 | 605 | 0 | 605 | 0 | 7566.561 |  | SWC015E/000A/076A
Palmers Dam Reservoir Safety Measures | Environment Agency | South West | River Harbourne, Palmers Dam, Devon | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2016 to 2018 | 250 | 0 | 0 | 0 | 145 | 0 | 145 | 0 | 5065.455 |  | SWC015E/000A/056A
Paul Stream channel/culvert refurbishments | Environment Agency | South West | Mousehole | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 2018 to 2021 | 83 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 522.973 |  | SWC010E/000A/109A
Polperro trash screen improvements | Environment Agency | South West | Polperro | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 2018 to 2021 | 177 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 0 |  | SWS005E/000A/073A
Portreath Flood Alleviation | Environment Agency | South West | Portreath | 0 | 175 | 0 | 0 | 0 | 0 | 962 | 2018 to 2021 | 382 | 405 | 0 | 0 | 135 | 0 | 135 | 0 | 5441 |  | SWC010E/000A/076A
Portreath Tunnel patch repairs | Environment Agency | South West | Portreath | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 100 | 0 | 0 | 0 | 85 | 0 | 85 | 0 | 9666.649 |  | SWC010E/000A/107A
St Blazey Stream Desilt | Environment Agency | South West | St Blazey, Par | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 2018 to 2021 | 117 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 3074.734 |  | SWC009E/000A/084A
Starcross and Cockwood Tidal Defence | Environment Agency | South West | Starcross and Cockwood | 0 | 275 | 0 | 0 | 0 | 0 | 1875 | 2018 to 2021 | 1600 | 0 | 0 | 0 | 660 | 0 | 660 | 0 | 78442.86 |  | SWC013E/000A/086A
Tamerton Foliot Stream Screen refurbishment | Environment Agency | South West | Tamerton Foliot | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 2018 to 2021 | 42 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 1467.322 |  | SWC011E/000A/104A
Tinhay refurbishment | Environment Agency | South West | Tinhay, Lifton | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 2018 to 2021 | 62 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 241.852 |  | SWC014E/000A/063A
Tiverton Flood Defence Improvements | Environment Agency | South West | Tiverton, Devon | 100 | 0 | 0 | 0 | 0 | 0 | 1250 | 2016 to 2018 | 1150 | 0 | 0 | 0 | 880 | 0 | 880 | 0 | 10862.39 |  | SWC013E/000A/057A
Tory Brook desilt | Environment Agency | South West | Plympton | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 2018 to 2021 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013.649 |  | SWC011E/000A/092A
Totnes Steamer Quay Wall Repairs | Environment Agency | South West | Totnes, Steamer Quay, River Dart | 0 | 0 | 0 | 0 | 0 | 0 | 435 | 2016 to 2018 | 320 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 7037.822 |  | SWC015E/000A/048A
Tywardreath Stream Culvert repairs | Environment Agency | South West | Par | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 105 | 0 | 105 | 0 | 3197.803 |  | SWO004E/000A/080A
Withycombe and Bapton Wall Refurfishments | Environment Agency | South West | Withycombe and Bapton Brook, Exmouth, Devon | 0 | 30 | 0 | 0 | 0 | 0 | 230 | 2018 to 2021 | 200 | 0 | 0 | 0 | 0 | 0 | 855 | 0 | 31473.929 |  | SWC013E/000A/096A
Wooda screen inlet refurbishment | Environment Agency | South West | Wooda screen inlet screen, Wooda Lane, Launceston | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2021 on | 40 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 720.026 |  | SWC011E/000A/103A
Bude Breakwater Refurbishment | Cornwall Council | South West | Bude | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 2018 to 2021 | 175 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 2994.792 |  | SWC009C/000A/055A
Keveral Gardens, Seaton Culvert Improvements | Cornwall Council | South West | Seaton | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2018 to 2021 | 165 | 85 | 0 | 0 | 25 | 0 | 25 | 0 | 848 |  | SWO007F/000A/050A
Kingsand Coast Protection | Cornwall Council | South West | Kingsand | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2018 to 2021 | 125 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 1191.07 |  | SWC011C/000A/056A
Porthleven Harbour Walls Refurbishment | Cornwall Council | South West | Porthleven | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 2018 to 2021 | 300 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 6938.567 |  | SWC010C/000A/058A
Church Sea Wall Repairs, Old Town, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 2018 to 2021 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1425 |  | SWS005C/000A/044A
Dune Management Plan and Works, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 |  | SWS005C/000A/074A
Great Pool Sea Defence Repairs, St Agnes | Council of the Isles of Scilly | South West | St Agnes | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 |  | SWS005C/000A/075A
Hell Bay Sea Defence Repairs, Bryher | Council of the Isles of Scilly | South West | Bryher | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 |  | SWS005C/000A/076A
Lower Moors Catchment Management, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 2713 |  | SWS005C/000A/077A
Mermaid Sea Wall Repairs, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 1647 |  | SWS005C/000A/078A
Porthminick Revetment Repairs, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 |  | SWS005C/000A/079A
Town Beach Flood Defence, St Mary's | Council of the Isles of Scilly | South West | St Mary's | 0 | 38.43 | 0 | 0 | 0 | 0 | 400.02 | 2018 to 2021 | 161.59 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 2718 |  | SWS005C/000A/080A
Seaton Beach and Axmouth Harbour - Beach Management Plan | East Devon District Council | South West | Seaton | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 2018 to 2021 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9610 |  | SWC012C/000A/044A_2
Alexandra Close, Plymstock, surface water flood protection | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 2018 to 2021 | 49 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 109.6 |  | SWS006F/000A/038A
Bernice Terrace, Lipson Vale, surface water capacity improvements | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 2018 to 2021 | 60 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 178 |  | SWS006F/000A/037A
Chaddlewood Stream, Plympton, Plymouth, capacity improvements | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 296.6 |  | SWC011F/000A/083A
Cobb Lane, Plymstock, additional highway drainage | Plymouth city council | South West | Plymouth | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 2018 to 2021 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 89 |  | SWS006F/000A/020A
Drunken Bridge Hill, Plympton, addional highway drainage | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2018 to 2021 | 20 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 79 |  | SWS006F/000A/027A
Embankment Road adj Haywoods, pumping and attenuation improvements | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 2018 to 2021 | 37 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 62 |  | SWC011F/000A/091A_2
Marshall Road Culvert renewal/relining | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 14.477 | 2018 to 2021 | 14.477 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 44.523 |  | SWS006F/000A/025A
Norossisick Way Culvert Trash Screen | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2018 to 2021 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SWC011F/000A/119A
Plymouth, Cattewater, Oreston Quay, sea wall, refurbishment | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 2018 to 2021 | 136 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 121 |  | SWC011F/000A/060A
Plymouth, Stonehouse and Durnford Street, Tidal flood alleviation | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 1126 | 2018 to 2021 | 1126 | 0 | 0 | 0 | 140 | 0 | 140 | 0 | 566.4 |  | SWC011F/000A/063A
Plymouth, Sutton Harbour, Coxside, Lock Gate climate change assessment | Plymouth city council | South West | Plymouth | 0 | 60 | 0 | 0 | 0 | 0 | 310 | 2018 to 2021 | 0 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 125 |  | SWS006F/000A/033A
Plymouth, The Cattewater, Teats Hill slipway, refurbishment | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2018 to 2021 | 8 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 51 |  | SWC011F/000A/066A
Saltash Road, Keyham, surface water capacity improvments | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2018 to 2021 | 11 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 407 |  | SWS006F/000A/024A
Shearwood Close, Plympton, additional highway drainage | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2018 to 2021 | 10 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 132 |  | SWS006F/000A/026A
Stenlake Terrace, Plymouth, surface water capacity improvements | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 2018 to 2021 | 60 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 436 |  | SWS006F/000A/039A
Tidal flap replacement. Stonehouse, Plymouth | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 2018 to 2021 | 65 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 317 |  | SWC011F/000A/120A
Wolseley Road, Camels Head, carriageway reprofiling | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 2018 to 2021 | 11 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 182.8889 |  | SWS006F/000A/023A
Adelphi Road Flood Alleviation (Property Level Protection) | Torbay Council | South West | Paignton | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2018 to 2021 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436.817 |  | SWC015F/000A/078A
Aylesford Stream Flood Alleviation, Ashford | Environment Agency | Southern | Ashford, Kent | 0 | 100 | 0 | 0 | 0 | 0 | 544 | 2018 to 2021 | 444 | 0 | 0 | 0 | 300 | 0 | 300 | 0 | 296 |  | SOC002E/000A/014B
Bartley (New Forest) Fluvial Flood Alleviation | Environment Agency | Southern | nr The New Forest SSSI, Bartley Water, Bartley Village, New Forest | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2021 on | 45 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 588 |  | SOC011E/001A/006A
Barton's Point Shingle Recycling | Environment Agency | Southern | Sheerness | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2021 on | 150 | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 6122 |  | SOS002E/002A/005A
Crayford Town Centre | Environment Agency | Southern | Crayford Town Centre | 0 | 50 | 0 | 0 | 0 | 0 | 1000 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 934.691 |  | SOC001E/000A/099A
Dartford Flood Alleviation | Environment Agency | Southern | Dartford Town Centre, Dartford | 0 | 50 | 0 | 0 | 0 | 0 | 1000 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 0 | 1045.074 |  | SOC001E/001A/010A
Denge Beach Management 2011-15 | Environment Agency | Southern | Jury’s Gap, Kent | 600 | 0 | 0 | 0 | 0 | 0 | 3000 | 2018 to 2021 | 0 | 0 | 0 | 0 | 580 | 0 | 2900 | 0 | 8683 |  | SOS003E/001A/024A
Denge Secondary Defence | Environment Agency | Southern | Denge, near Dungeness, Kent | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 2016 to 2018 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47850 |  | SOO001E/000A/431A
East Peckham Flood Alleviation | Environment Agency | Southern | East Peckham | 0 | 0 | 0 | 0 | 0 | 0 | 470.59 | 2016 to 2018 | 416 | 0 | 0 | 0 | 315 | 0 | 315 | 0 | 8620 |  | SOC003E/001A/005A
East Wittering Fluvial and Surface Water Improvements | Environment Agency | Southern | East Wittering | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 2021 on | 75 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 2800 |  | SOO002E/000A/291A
Ebbsfleet Culvert Refurbishment/Replacement | Environment Agency | Southern | Ebbsfleet and Gravesham | 0 | 20 | 0 | 0 | 0 | 0 | 520 | 2018 to 2021 | 500 | 0 | 0 | 0 | 95 | 0 | 95 | 0 | 16628.646 |  | SOC001E/000A/106A
Elmley Managed Realignment and Habitat Creation | Environment Agency | Southern | Isle of Sheppey | 80 | 0 | 0 | 0 | 0 | 0 | 1930 | 2016 to 2018 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SOS001E/000A/009A
Farlington Marsh Tidal Defence Improvements & Realignment | Environment Agency | Southern | Farlington Marsh | 0 | 525 | 100 | 0 | 0 | 0 | 4948.846 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | 36948.583 |  | SOS005E/005A/006A
Gorrell Stream Culvert | Environment Agency | Southern | Whitstable | 0 | 25 | 0 | 0 | 0 | 0 | 325 | 2018 to 2021 | 300 | 0 | 0 | 0 | 115 | 0 | 115 | 0 | 6985.945 |  | SOC002E/000A/030A
Great Stour Flood Alleviations | Environment Agency | Southern | Great Stour between Wye (TR04824650) and Fordwich (TR18666014) | 0 | 500 | 0 | 0 | 0 | 0 | 7772 | 2018 to 2021 | 7122 | 0 | 0 | 0 | 1365 | 0 | 1365 | 0 | 12370.441 |  | SOC002E-000A-017A
Gunville Stream (Isle of Wight) Flood Alleviation | Environment Agency | Southern | Gunville IOW | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2021 on | 25 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 841.4033 |  | SOS006E/000A/007A
Hailsham Flood Alleviation and River Restoration | Environment Agency | Southern | Knockhatch Stream Extension, Hailsham | 0 | 25 | 0 | 0 | 0 | 0 | 175 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 0 | 207.491 |  | SOC005E/000A/008A
Hall Place Flood Storage Reservoir Improvement | Environment Agency | Southern | Hall Place, Bourne Rd, Bexley | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2018 to 2021 | 301.384 | 198.616 | 0 | 0 | 35 | 0 | 35 | 0 | 3514.52 |  | SOC001E/000A/105A
Horsham Warnham Mill Reservoir Sluice Replacement | Environment Agency | Southern | Horsham, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2021 on | 50 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 2954.101 |  | SOC007E/000A/017A
Hythe Coastal Flood Allevation | Environment Agency | Southern | Hythe, Hampshire | 0 | 25 | 0 | 0 | 0 | 0 | 415 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 7188.047 |  | SOC011E/000A/006A
Jury's Gap Refurbishment | Environment Agency | Southern | Jury's Gap (Camber) | 500 | 0 | 0 | 0 | 0 | 0 | 605.386 | 2016 to 2018 | 0 | 0 | 0 | 0 | 405 | 0 | 405 | 0 | 92 |  | SOO001E/000A/093A
Kite Farm Diversion Channel | Environment Agency | Southern | Whistable | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 2016 to 2018 | 210.5 | 19.5 | 0 | 0 | 60 | 0 | 60 | 0 | 1121.001 |  | SOS002E/007A/001A
Lamorbey Park Flood Storage Reservoir Improvement | Environment Agency | Southern | Burnt Oak Lane, Sidcup | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 200 | 0 | 0 | 0 | 220 | 0 | 220 | 0 | 2240.834 |  | SOC001E/000A/104A
Lukely Brook (Isle of Wight) Flood Alleviation | Environment Agency | Southern | Lukely Brook - Carisbrooke/Newport IOW | 0 | 0 | 0 | 64.09 | 0 | 0 | 535 | 2021 on | 321.91 | 149 | 0 | 0 | 95 | 0 | 95 | 0 | 2723.2085 |  | SOC012E/000A/0010A
Monktonmead Brook pumping station and outfall improvements | Environment Agency | Southern | Ryde, Isle of Wight | 1610 | 0 | 0 | 0 | 0 | 0 | 2513.102 | 2016 to 2018 | 705 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 56400 |  | SOC012E/000A/007A
Oare Flood Alleviation | Environment Agency | Southern | Oare, Kent | 0 | 20 | 0 | 0 | 0 | 0 | 820 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 287.413 |  | SOC004E/000A/018A
Pett Shingle Nourishment Phase 7 - 11 | Environment Agency | Southern | Pett Level, Winchelsea Beach | 0 | 0 | 0 | 0 | 0 | 0 | 3844 | 2018 to 2021 | 2653 | 0 | 0 | 0 | 570 | 0 | 570 | 0 | 945 |  | SOS003E/001A/027A
Plenty Brook Culvert | Environment Agency | Southern | Herne Bay | 0 | 25 | 0 | 0 | 0 | 0 | 304.208 | 2018 to 2021 | 279.208 | 0 | 0 | 0 | 140 | 0 | 140 | 0 | 6630.934 |  | SOC002E/008A/002A
Polegate Flood Alleviation | Environment Agency | Southern | Wannock Mill Stream, Polegate | 0 | 0 | 0 | 45 | 0 | 0 | 295 | 2018 to 2021 | 24 | 96 | 0 | 0 | 0 | 0 | 40 | 0 | 178.739 |  | SOC005E/000A/0013A
Queenborough Creek Barrier upgrade and refurb. | Environment Agency | Southern | North Kent | 0 | 0 | 0 | 0 | 0 | 0 | 1505 | 2016 to 2018 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17800 |  | SOO001E/000A/375A
Ringmer Flood Alleviation | Environment Agency | Southern | Ringmer, East Sussex | 0 | 5 | 0 | 0 | 0 | 0 | 30 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 189.344 |  | SOC006E/000A/0015A
Romney Main Conveyance Improvements | Environment Agency | Southern | New Romney | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 100 | 0 | 0 | 0 | 90 | 0 | 90 | 0 | 151 |  | SOC004E/000A/005A
Ruxley Gravel Pits Storage Improvement | Environment Agency | Southern | Ruxley Gravel Pits, Edgington Way, Foot's Cray | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2021 on | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 3216.393 |  | SOC001E/000A/102A
Shoreham and Lancing Coastal Defences Beach Management Plan | Environment Agency | Southern | Shoreham, West Sussex | 130 | 0 | 0 | 0 | 0 | 0 | 650 | 2016 to 2018 | 520 | 0 | 0 | 0 | 720 | 0 | 900 | 0 | 3250 |  | SOS004C/000A/020A
Sidlesham - Pagham harbour inland banks improvements | Environment Agency | Southern | Sidlesham, West Sussex | 300 | 0 | 0 | 0 | 0 | 0 | 2047.5 | 2018 to 2021 | 1700 | 0 | 0 | 0 | 145 | 0 | 145 | 0 | 59200 |  | SOS005E/009A/014A
Swanscombe Peninsula Defence Improvements and Land raising | Environment Agency | Southern | Swanscombe penninsula at Dartford - DA119BB | 0 | 50 | 0 | 0 | 0 | 0 | 350 | 2021 on | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 |  | SOO001E/000A/443A
Tanyard Stream (Steyning) Culvert Improvements | Environment Agency | Southern | Three sites on the Tanyard Stream | 0 | 10 | 0 | 0 | 0 | 0 | 110 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 890 |  | SOC008E/000A/017A
Tidal Flood Defence Improvements, Wallington Shore Road, Fareham | Environment Agency | Southern | Old Wallington Village, Shore Road | 322.045 | 0 | 0 | 0 | 0 | 0 | 3016.776 | 2016 to 2018 | 2406.17 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 42100.25 |  | SOO002E/000A/215A
Tillingham sluice replacement | Environment Agency | Southern | Rye | 0 | 75 | 0 | 0 | 0 | 0 | 550 | 2018 to 2021 | 475 | 0 | 0 | 0 | 725 | 0 | 725 | 0 | 1332 |  | SOC004E/000A/011A
Upper Westerham Flood Alleviation | Environment Agency | Southern | River Darent from Squerry's Court to Long Pond, Westerham | 0 | 9 | 0 | 0 | 0 | 0 | 137 | 2016 to 2018 | 128 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 1007.149 |  | SOC001E/000A/097A
Warden Bay Outfall Refurbishment | Environment Agency | Southern | Warden Bay | 0 | 0 | 0 | 0 | 0 | 0 | 872 | 2018 to 2021 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25042 |  | SOS001E/000A/007A
West Brook South Flood Alleviation Emsworth | Environment Agency | Southern | Emsworth West Brook | 0 | 0 | 0 | 0 | 0 | 0 | 685.2 | 2021 on | 200 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 5229.7724 |  | SOC009E/000A/003A
Winchester Fluvial Flood Alleviation | Environment Agency | Southern | Winchester - River Itchen | 0 | 0 | 0 | 50 | 0 | 0 | 750 | 2021 on | 93.5 | 56.5 | 0 | 0 | 0 | 0 | 140 | 0 | 5096.2141 |  | SOC010E/000A/011A
Winterbourne Stream (Lewes) Outfall Tidal Doors Replacement | Environment Agency | Southern | Ouse Catchment | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2018 to 2021 | 194.475 | 55.525 | 0 | 0 | 105 | 0 | 105 | 0 | 1237.851 |  | SOC006E/000A/0010A
Goring-by-sea - replacement groynes | Adur and Worthing Councils | Southern | Goring-by-Sea | 0 | 500 | 0 | 0 | 0 | 0 | 2750 | 2018 to 2021 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105526 |  | SOS004C/002A/014A
Worthing replacement groynes | Adur and Worthing Councils | Southern | Worthing | 0 | 0 | 0 | 0 | 0 | 0 | 1352 | 2016 to 2018 | 1200 | 0 | 0 | 0 | 255 | 0 | 255 | 0 | 27885 |  | SOS004C/002A/012A
Aldwick Groyne Replacement Phase 10 | Arun DC | Southern | Aldwick, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 380 | 2021 on | 227 | 153 | 0 | 0 | 0 | 10 | 0 | 10 | 1878 |  | SOS004C/003A/008A
Capital Recycling West of River Arun | Arun DC | Southern | Aldwick, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 2016 to 2018 | 124 | 0 | 0 | 0 | 0 | 60 | 0 | 60 | 1283 |  | SOS004C/003A/014A
Land Drainage Outfall Improvement (Rustington and East Preston) | Arun DC | Southern | Rustington, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 2018 to 2021 | 168 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 342 |  | SOS004C/003A/019A
Middleton On Sea Risk Management | Arun DC | Southern | Middleton, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2016 to 2018 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 |  | SOS004C/003A/021A
Pagham Beach Erosion Management Option | Arun DC | Southern | Pagham, West Sussex | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662 |  | SOS004C/003A/022A
Herne Bay Sea Defence (Beach Management) | Canterbury City Council | Southern | Herne Bay | 0 | 0 | 0 | 0 | 0 | 0 | 457 | 2018 to 2021 | 182.8 | 0 | 0 | 0 | 75 | 0 | 190 | 0 | 2964.96 |  | SOS002F/005A/003B
Deal Beach management 2015-2020 | Dover DC | Southern | Deal Castle to Sandown Castle | 50 | 0 | 0 | 0 | 0 | 0 | 1800 | 2016 to 2018 | 1750 | 0 | 0 | 0 | 4700 | 0 | 7830 | 0 | 17632.287 |  | SOS001C/006A/029A
Kingsdown Beach Management 2015/16-20/21 | Dover DC | Southern | Kingsdown, Kent | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 2018 to 2021 | 450 | 0 | 0 | 0 | 535 | 0 | 890 | 0 | 39787 |  | SOS001C/006A/028A
Fareham Quay Coastal Flood & Erosion Risk Management | Fareham BC | Southern | Fareham Creek. Fareham | 0 | 40 | 0 | 0 | 0 | 0 | 380 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 5236.794 |  | SOS005C/000A/009A
Hill Head to Portsmouth Harbour Entrance Beach Management Plan | Fareham BC | Southern | Gosport and Fareham Open Coast | 0 | 0 | 0 | 0 | 0 | 0 | 142.62 | 2021 on | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 257.38 |  | SOS005C/016A/003A
Forton Lake (Gosport) Coastal Flood and Erosion Risk Management | Gosport BC | Southern | Forton Lake. Gosport | 0 | 40 | 0 | 0 | 0 | 0 | 300 | 2018 to 2021 | 155 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 3253.425 |  | SOS005F/000A/09AA
Seafield & Alverstoke Coastal Flood & Erosion Risk Management | Gosport BC | Southern | Haslar Lake and Workhouse Lake . Gosport | 0 | 120 | 0 | 0 | 0 | 0 | 1320 | 2018 to 2021 | 1200 | 0 | 0 | 0 | 215 | 0 | 215 | 0 | 19608.639 |  | SOS005F/000A/11AA
Hastings Coastal Defence - Stage 3 | Hastings Borough Council | Southern | Hastings, Pier to SW Outfall | 0 | 150 | 110 | 0 | 0 | 0 | 22505 | 2016 to 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38415 |  | SOS003F/006A/03AA
Eastoke Drainage Improvements | Havant BC | Southern | Hayling Island | 0 | 100 | 0 | 0 | 0 | 0 | 3500 | TBC | 3400 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 63841 |  | SOS005C/000A/0011A
Schemes arising from South Wight Coastal Strategy | Isle of Wight Council | Southern | Anticipated to be in Sandown Bay (and the Ventnor Undercliff, to follow) | 0 | 600 | 0 | 0 | 0 | 0 | 7482 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 773754 |  | SOS006C/000B/002A
Schemes arising from West Wight Coastal Strategy | Isle of Wight Council | Southern | Anticipated to be Yarmouth, Freshwater, Gurnard-Cowes, Cowes, East Cowes, Newport, Totland&Colwell | 0 | 600 | 0 | 0 | 0 | 0 | 15302.4 | 2018 to 2021 | 2648.4 | 0 | 0 | 0 | 50 | 85 | 555 | 485 | 961651.6 |  | SOS006C/000B/001A
Wyncham Stream Catchment | London Borough of Bexley | Southern | Sidcup, Wyncham Stream | 60 | 0 | 0 | 0 | 0 | 0 | 710 | 2018 to 2021 | 650 | 0 | 0 | 0 | 490 | 0 | 490 | 0 | 14312.593 |  | THO999F/049A/001A
Christchurch Bay Beach Management Plan 2018/19 to 2022/23 | New Forest DC | Southern | Southeast England | 0 | 80 | 0 | 0 | 0 | 0 | 4380 | 2018 to 2021 | 4100 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 136326.5016 |  | SOS005C/010A/008A
Hurst Spit Beach Management Plan 2016/17 to 2020/21 | New Forest DC | Southern | Southeast England | 0 | 0 | 0 | 0 | 0 | 0 | 7243 | 2018 to 2021 | 7243 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 97193.1707 |  | SOS005C/011A/021A
Old Portsmouth Tidal Risk Management | Portsmouth City Council | Southern | Old Portsmouth, Portsmouth | 0 | 0 | 0 | 0 | 0 | 0 | 124.447 | 2018 to 2021 | 70.641 | 0 | 0 | 0 | 215 | 0 | 215 | 0 | 7734.133 |  | SOS005C/000A/0015A
Portsea Island: Eastney Lake Coastal Flood and Erosion Risk Management | Portsmouth City Council | Southern | Eastney & Milton, Portsmouth | 0 | 21.049 | 0 | 0 | 0 | 0 | 1639.993 | 2018 to 2021 | 853.362 | 0 | 0 | 0 | 330 | 0 | 330 | 0 | 9943.264 |  | SOS005F/004A/005A
Portsea Island: Southsea Coastal Flood and Erosion Risk Management | Portsmouth City Council | Southern | Southsea, Portsmouth | 0 | 7631.92 | 0 | 0 | 0 | 0 | 41803.629 | 2018 to 2021 | 4883.558 | 0 | 0 | 0 | 0 | 70 | 2310 | 100 | 543079.068 |  | SOS005F/004A/002A
Hythe to Folkestone Beach Management 2015 - 2020 | Shepway District Council | Southern | East of Hythe Ranges to Sandgate. The Folkestone to Cliff End Flood & Erosion Risk Strategy refers to this frontage as Hythe to Folkestone Harbour Frontage A which is the most easten frontage in Coastal Cell 2. | 250 | 0 | 0 | 0 | 0 | 0 | 1520 | 2016 to 2018 | 1050 | 0 | 0 | 0 | 0 | 1750 | 0 | 1750 | 48631 |  | SOS003F/005A/06AA
Hythe to Folkestone Beach Management 2020 - 2025 | Shepway District Council | Southern | East of Hythe Ranges to Sandgate. The Folkestone to Cliff End Flood & Erosion Risk Strategy refers to this frontage as Hythe to Folkestone Harbour Frontage A which is the most easten frontage in Coastal Cell 2. | 0 | 25 | 0 | 0 | 0 | 0 | 1333 | 2018 to 2021 | 252 | 0 | 0 | 0 | 0 | 875 | 0 | 2630 | 48366 |  | SOS003F/005A/10CA
Hythe to Folkestone Beach Recharge | Shepway District Council | Southern | Hythe to Folkestone | 0 | 30 | 0 | 0 | 0 | 0 | 5035 | 2018 to 2021 | 5005 | 0 | 0 | 0 | 0 | 2190 | 0 | 2190 | 44916 |  | SOS003F/005A/18CA
Old Redbridge Lane (Southampton) Property Level Protection | Southampton City Council | Southern | Old Redbridge lane, Redbridge, Southampton (River Test) | 0 | 5 | 0 | 0 | 0 | 0 | 31.5 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 344.431 |  | SOO004C/000A/060A
Priory Road (Southampton) Property Level Protection | Southampton City Council | Southern | Priory Road, St Denys, Southampton (River Itchen) | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 2018 to 2021 | 235 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 1795.653 |  | SOC010F/000A/0010A
Minster Sheppey Coast Protection | Swale Borough Council | Southern | Minster, Isle of Sheppey | 0 | 0 | 0 | 0 | 0 | 0 | 718 | 2018 to 2021 | 259 | 0 | 0 | 0 | 0 | 55 | 0 | 55 | 4526 |  | SOS002C/000A/013A
Thanet Groyne Reconstruction/Refurbishment | Thanet District Council | Southern | Thanet District | 0 | 0 | 0 | 0 | 0 | 0 | 388 | 2018 to 2021 | 293.5 | 69.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5095 |  | SOS003C/000A/16CA
Westgate - St Mildred's Bay - Coping/Berm Slab Replacement | Thanet District Council | Southern | Westgate on Sea, Kent | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 2018 to 2021 | 86.23 | 1.77 | 0 | 0 | 5 | 5 | 5 | 5 | 715 |  | SOS003C/000A/15CA
Billingshurst Surface Water Management Plan and Actions | West Sussex CC | Southern | Billinshurst, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2021 on | 75 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 477.7 |  | SOC008E/000A/019A
Hassocks Surface Water Management Plan and Actions | West Sussex CC | Southern | Hassocks, West Sussex | 0 | 75 | 0 | 0 | 0 | 0 | 425 | 2018 to 2021 | 350 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 1273.4 |  | SOC007E/000A/015A
Lancing Surface Water Management Plan and Actions | West Sussex CC | Southern | Lancing, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 2016 to 2018 | 180 | 0 | 0 | 0 | 90 | 0 | 90 | 0 | 1470 |  | SOC007E/000A/016A
Manhood Peninsula Surface Water Management Plan and Actions | West Sussex CC | Southern | Manhood Peninsula, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 2016 to 2018 | 180 | 0 | 0 | 0 | 215 | 0 | 215 | 0 | 2230 |  | SOC008E/000A/020A
Abingdon River Ock Flood Storage Area | Environment Agency | Thames | Abingdon, Oxfordshire | 0 | 0 | 0 | 280 | 0 | 0 | 3417 | 2016 to 2018 | 1496 | 1591 | 0 | 0 | 240 | 0 | 240 | 0 | 7527.009 |  | THC041E/000A/005A
Abingdon St. Helen's Wharf Flood Alleviation | Environment Agency | Thames | St. Helen's Mill, Abingdon, Oxfordshire | 0 | 0 | 0 | 46.8 | 0 | 0 | 571 | 2016 to 2018 | 86.15 | 438.05 | 0 | 0 | 10 | 0 | 10 | 0 | 216 |  | THC041E/000A/007A
Alton Attenuation And Flood Study | Environment Agency | Thames | Alton | 0 | 30 | 0 | 0 | 0 | 0 | 445 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 3109 |  | THC014E/000A/010A
Bagshot Flood Alleviation | Environment Agency | Thames | Bagshot | 0 | 47.586 | 0 | 7.414 | 0 | 0 | 730 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 3518 |  | THC008E/000A/007A
Bicester Town Centre Trash Screen Investigation | Environment Agency | Thames | Bicester Town Centre, Oxfordshire | 0 | 5 | 0 | 0 | 0 | 0 | 35 | 2018 to 2021 | 30 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 1018 |  | THC002E/000A/030A
Bisham - Flood Alleviation | Environment Agency | Thames | Bisham | 0 | 0 | 0 | 112.153 | 0 | 0 | 825.275 | 2016 to 2018 | 462.848 | 208.274 | 0 | 0 | 95 | 0 | 95 | 0 | 2014 |  | THC000E/000A/209A
Bloxham Flood Alleviation | Environment Agency | Thames | Brookside Way, Bloxham near Banbury | 0 | 0 | 0 | 60 | 0 | 0 | 340.8 | 2018 to 2021 | 92.55 | 116.25 | 0 | 0 | 15 | 0 | 15 | 0 | 714.577 |  | THC002E/000A/028A
Boundary Brook Catchment (Florence Park) Flood Alleviation | Environment Agency | Thames | Florence Park, Iffley, Oxford | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 2016 to 2018 | 246.65 | 168.35 | 0 | 0 | 75 | 0 | 75 | 0 | 746.582 |  | THC040E/001A/005A
Bourton on the Water Flood Alleviation Remediation | Environment Agency | Thames | Bourton on the Water, Gloucestershire | 0 | 0 | 0 | 25 | 0 | 0 | 343.5 | 2018 to 2021 | 143.7 | 174.8 | 0 | 0 | 50 | 0 | 50 | 0 | 434.43 |  | THC002E/000A/032A
Charvil Flood Alleviation | Environment Agency | Thames | CHARVIL | 0 | 0 | 0 | 0 | 0 | 0 | 119.861 | 2016 to 2018 | 75.945 | 16.355 | 0 | 0 | 35 | 0 | 35 | 0 | 743.47 |  | THC000E/000A/208A
Chesham Flood Alleviation Vale Brook Culvert | Environment Agency | Thames | Chesham Town Centre | 0 | 53.088 | 0 | 96.912 | 0 | 0 | 4305 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 17530 |  | THC017E/000A/018A
Colnbrook - County Ditch & Colne Brook | Environment Agency | Thames | Slough/ Poyle and Colnbrook/ Colnbrook, County Ditch, Hawthorn Ditch | 0 | 0 | 0 | 100 | 0 | 0 | 600 | 2016 to 2018 | 294.2 | 205.8 | 0 | 0 | 245 | 0 | 245 | 0 | 954.007 |  | THC017E/000A/021A
Crayford Marshes Earth Tidal Flood Embankment | Environment Agency | Thames | Darent Industrail Park and Crayford Marshes, Slade Green, Kent - DA8 2AF | 0 | 55 | 100 | 0 | 0 | 0 | 5055 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 11698.657 |  | THC000E/000A/248A
Culvert Capacity and Trash Screen Effectiveness | Environment Agency | Thames | Westhorne Avenue, Eltham, Greenwich, London | 150 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 4514.364 |  | THC022E/000A/032A
Culvert Capacity and Trash Screen, in the vicinty of Bromley | Environment Agency | Thames | Bromley - BR1 2BJ | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 2021 on | 36.43 | 3.57 | 0 | 0 | 0 | 0 | 0 | 0 | 215.847 |  | THC022E/000A/027A
Dagenham Brook Flood Alleviation | Environment Agency | Thames | London Borough of Waltham Forest - near Low Hall and Marsh Lane | 0 | 1391.61 | 0 | 620 | 0 | 0 | 11681 | 2018 to 2021 | 3088.09 | 2670.5 | 0 | 0 | 0 | 0 | 365 | 0 | 107988.567 |  | THC036E/001A/030B
Darent Industrial Estate Fluvial Flood Alleviation | Environment Agency | Thames | Crayford Marshes, Near Erith, Kent DA8 2LD | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 2018 to 2021 | 500 | 0 | 0 | 0 | 135 | 0 | 135 | 0 | 12070.679 |  | THC000E/011A/004A
Godalming Flood Alleviation | Environment Agency | Thames | Godalming | 0 | 0 | 0 | 0 | 0 | 0 | 3155.5 | 2016 to 2018 | 1040.75 | 2064.75 | 0 | 0 | 75 | 0 | 75 | 0 | 2846.41 |  | THC014E/001A/006A
Greenford Flood Management | Environment Agency | Thames | Greenford | 0 | 48.95 | 23.219 | 11.05 | 0 | 0 | 1547 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 3346 |  | THC024E/000A/016A
Horley Flood Relief | Environment Agency | Thames | Horley and Hookwood, Surrey | 0 | 64.61 | 0 | 10.39 | 0 | 0 | 575 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 3545 |  | THC009E/000A/003A
Illford, Seven Kings Water Flood Alleviation | Environment Agency | Thames | Seven Kings Water, Redbridge | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 2018 to 2021 | 0 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 9868.126 |  | THC029E/000A/005A
Kingston Town Centre Flood Alleviation | Environment Agency | Thames | Kingston Town Centre | 0 | 0 | 0 | 150 | 0 | 0 | 4700 | 2018 to 2021 | 247 | 1953 | 0 | 0 | 0 | 0 | 500 | 0 | 6894.181 |  | THC020E/000A/009A
Kingsway, Blackwater Flood Alleviation | Environment Agency | Thames | Kingsway and Christchurch Drive | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 2021 on | 39.657 | 0.343 | 0 | 0 | 0 | 0 | 35 | 0 | 732 |  | THC003E/000A/005A
Leatherhead and Middle Mole Flood Alleviation | Environment Agency | Thames | Mole Valley | 0 | 0 | 0 | 100 | 0 | 0 | 2700 | 2016 to 2018 | 2315 | 185 | 0 | 0 | 645 | 0 | 645 | 0 | 17501.1729 |  | THC010E/000A/001A
Lower Mole Flood Alleviation: Penstocks, Access and Flood Wall Repairs | Environment Agency | Thames | Lower River Mole. Hersham, Esher and Molesey in the Surrey Borough of Elmbridge | 100 | 0 | 0 | 0 | 0 | 0 | 670 | 2018 to 2021 | 570 | 0 | 0 | 0 | 3065 | 0 | 3065 | 0 | 9184 |  | THC013E/000A/013A
Mayes Brook & Ripple Road, Barking - actuator improvements | Environment Agency | Thames | Mayes Brook Inlet Sluice, Mayes Brook Outlet Sluice & Ripple Road Sluice, Barking, Essex | 0 | 5 | 0 | 0 | 0 | 0 | 150 | 2018 to 2021 | 145 | 0 | 0 | 0 | 315 | 0 | 315 | 0 | 3941.57 |  | THC000E/000A/254A
Mereway Sluice Gate Replacement | Environment Agency | Thames | Twickenham | 0 | 0 | 0 | 0 | 0 | 0 | 405 | 2016 to 2018 | 350 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 4206 |  | THC000E/000A/222A
Mereway Sluice, Twickenham - Gate Replacement | Environment Agency | Thames | Mereway Road, Twickenham, Middlesex, TW2 6RR | 0 | 75 | 0 | 0 | 0 | 0 | 385 | 2018 to 2021 | 310 | 0 | 0 | 0 | 205 | 0 | 205 | 0 | 4203 |  | THC000E/000A/252A
Misbourne Flood alleviation and water management level strategy | Environment Agency | Thames | Old Amersham - Chalfont St Giles High - Chalfont St Peter High Street - Missenden | 0 | 0 | 0 | 20 | 0 | 0 | 350 | 2018 to 2021 | 26.7 | 103.3 | 0 | 0 | 0 | 0 | 140 | 0 | 1368.504 |  | THC018E/000A/018A
Newmans Sluices, Waltham Abbey, Installation of Lorry Access | Environment Agency | Thames | Newmans Sluices, Waltham Abbey, Lee Flood Relief Channel | 0 | 5 | 0 | 0 | 0 | 0 | 60 | 2018 to 2021 | 55 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 1048.876 |  | THC036E/001A/038A
North Yateley Flood Impact Reduction | Environment Agency | Thames | Yateley Green, Yateley | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 2016 to 2018 | 148.124 | 14.876 | 0 | 0 | 0 | 0 | 55 | 0 | 971.499 |  | THC016E/000A/002A
Pangbourne Flood Alleviation | Environment Agency | Thames | Pangbourne | 0 | 0 | 0 | 0 | 0 | 0 | 187 | 2016 to 2018 | 101.94 | 68.06 | 0 | 0 | 25 | 0 | 25 | 0 | 503 |  | THC044E/001A/006A
Papermill Stream Penstock, Channel and Bridge, Standon | Environment Agency | Thames | Papermill House, Papermill Lane, Standon, Herts | 0 | 15 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 85 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 2163.342 |  | THC034E/000A/011A
Pinn Flood Alleviation | Environment Agency | Thames | Pinner, Ruislip, Ickenham, Uxbridge | 0 | 88.4397 | 0 | 1.56 | 0 | 0 | 3212.9997 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 905 | 0 | 6012 |  | THC019E/000A/002A
Puckeridge Flood Alleviation | Environment Agency | Thames | Puckeridge , Hertfordshire - River Rib | 0 | 0 | 0 | 40 | 0 | 0 | 1510 | 2018 to 2021 | 7.7 | 437.3 | 0 | 0 | 0 | 0 | 125 | 0 | 7050.998 |  | THC034E/000A/009A
Purley on Thames Property Level Protection | Environment Agency | Thames | Purley on Thames | 48.969 | 0 | 0 | 0 | 0 | 0 | 116.887 | 2016 to 2018 | 0.75 | 60.781 | 0 | 0 | 20 | 0 | 20 | 0 | 558 |  | THC044E/001A/007A
Quaggy at Hither Green flood alleviation study | Environment Agency | Thames | Hither Green, Lewisham | 0 | 30 | 0 | 0 | 0 | 0 | 500 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6753.457 |  | THC022E/000A/025A
Ravensbourne West Wickham to Shortlands flood alleviation | Environment Agency | Thames | Bromley - West Wickham to Shortlands | 0 | 0 | 0 | 900 | 0 | 0 | 10500 | 2018 to 2021 | 6010 | 3590 | 0 | 0 | 700 | 0 | 700 | 0 | 17926.248 |  | THC022E/000A/030A
River Ash & Staines Reservoirs Aqueduct | Environment Agency | Thames | Staines, Shepperton - River Ash, Colne Brook, County Ditch and Staines Reservoir Aqueduct | 30 | 50 | 0 | 0 | 0 | 0 | 995 | 2016 to 2018 | 900 | 0 | 0 | 0 | 945 | 0 | 945 | 0 | 9880.716 |  | THC038E/000A/031A
River Churn Strategy Phase two | Environment Agency | Thames | River Churn Cirencester | 0 | 0 | 0 | 0 | 0 | 0 | 877 | TBC | 877 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 77511 |  | THC001E/001A/004A
River Loddon Soft Engineering | Environment Agency | Thames | River Loddon at Winnersh | 0 | 19 | 0 | 0 | 0 | 0 | 169 | 2018 to 2021 | 150 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 835 |  | THC999/000/249A
River Rythe: Flood Relief Culvert intake screen | Environment Agency | Thames | River Rythe: U/S of Haven Court, Hinchley Wood | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 1631.576 |  | THC038E/000A/030A
Stanstead Mountfitchet Flood Alleviation | Environment Agency | Thames | Stanstead Mountfitchet, Essex - Ugley Brook | 0 | 0 | 0 | 80 | 0 | 0 | 1030 | 2018 to 2021 | 34.6 | 865.4 | 0 | 0 | 25 | 0 | 25 | 0 | 206.148 |  | THC033E/000A/014A
Takeley - Culvert removal and screen replacement | Environment Agency | Thames | Takeley | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 2018 to 2021 | 35 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 271.524 |  | THC000E/000A/250A
The Beck (East Branch) at Langley Park flood alleviation | Environment Agency | Thames | Park Langley, Bromley | 0 | 30 | 0 | 0 | 0 | 0 | 300 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150.086 |  | THC022E/000A/028A
Tokyngton & Stonebridge Flood Alleviation | Environment Agency | Thames | D/S of Welsh Harp/Tokyngton Park & Stonebridge Park Tube/Willesden Junction Station | 0 | 0 | 0 | 300 | 0 | 0 | 4050 | 2018 to 2021 | 2865 | 835 | 0 | 0 | 495 | 0 | 495 | 0 | 2284.278 |  | THC024E/000A/018A
Tudor and Cricket Hill Stream Flood Reduction | Environment Agency | Thames | Yateley | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 2021 on | 76.065 | 58.935 | 0 | 0 | 25 | 0 | 25 | 0 | 207 |  | THC003E/000A/004A
Twyford Flood Mitigation | Environment Agency | Thames | Twyford, Reading | 0 | 0 | 0 | 0 | 0 | 0 | 153 | TBC | 50.4 | 102.6 | 0 | 0 | 25 | 0 | 25 | 0 | 25.972 |  | THC016E/000A/005A
Upminster Flood Alleviation | Environment Agency | Thames | Upstream of Upminster | 0 | 21.109 | 0 | 10.891 | 0 | 0 | 690 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 4575 |  | THC025E/000A/005A
Wendlebury | Environment Agency | Thames | Wendlebury, Nr Bicester | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 2016 to 2018 | 160.586 | 139.414 | 0 | 0 | 0 | 0 | 0 | 0 | 724 |  | THC002E/000A/013B
Wey Meadows Flood Alleviation | Environment Agency | Thames | Wey Meadows, Surrey | 0 | 37.086 | 0 | 7.914 | 0 | 0 | 305 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 1778.4225 |  | THC012E/000A/004A
Wey Road, Weybridge Flood Alleviation | Environment Agency | Thames | Weybridge, Surrey on the River Wey | 0 | 27.05 | 0 | 42.95 | 0 | 0 | 595 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 3377.084 |  | THC012E/001A/007A
Windlesham Flood Alleviation | Environment Agency | Thames | Windlesham | 50 | 0 | 0 | 0 | 0 | 0 | 115 | 2016 to 2018 | 30 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 4556 |  | THC008E/000A/008A
Witney Initial Assessment | Environment Agency | Thames | Witney, Oxfordshire | 27 | 0 | 0 | 0 | 0 | 0 | 120 | 2016 to 2018 | 0 | 63 | 0 | 0 | 10 | 0 | 10 | 0 | 17.4285 |  | THC002E/000A/019A
Woodford Access Improvements - River Roding | Environment Agency | Thames | Roding Lane South, Woodford | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 2018 to 2021 | 162 | 0 | 0 | 0 | 150 | 0 | 150 | 0 | 1838.777 |  | THC029E/000A/006A
Woodford Surface Water Flood Alleviation | Environment Agency | Thames | Essex | 0 | 0 | 0 | 0 | 0 | 0 | 827.707 | 2016 to 2018 | 124 | 96 | 0 | 0 | 405 | 0 | 405 | 0 | 38374.148 |  | THC029E/001A/009A
Sands (High Wycombe) Surface Water Flood Risk Management | Buckinghamshire County Council | Thames | Sands, High Wycombe | 0 | 0 | 0 | 5 | 0 | 0 | 255 | 2016 to 2018 | 57.3 | 192.7 | 0 | 0 | 20 | 0 | 20 | 0 | 361.791 |  | THC018E/000A/015A
Ashenden Road Surface water | Guildford BC | Thames | Guildford | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 2018 to 2021 | 150 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 1056 |  | THO999F/016A/007A
Kimpton Groundwater Flood Risk Management | Hertfordshire CC | Thames | Kimpton | 5 | 30 | 0 | 0 | 0 | 0 | 675.0059 | 2021 on | 290.413 | 309.5929 | 0 | 0 | 0 | 0 | 150 | 0 | 3815 |  | THO999F/045A/001A
Rickmansworth Combined Flood Risk Study | Hertfordshire CC | Thames | Various sites in Rickmansworth, Hertfordshire | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2018 to 2021 | 30 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 1578.0064 |  | THC018E/000A/016A
Decoy Brook Catchment Flood Alleviation. | London Borough of Barnet | Thames | Decoy Brook - London Borough of Barnet | 0 | 0 | 0 | 20 | 0 | 0 | 395 | 2018 to 2021 | 266.3 | 108.7 | 0 | 0 | 190 | 0 | 190 | 0 | 822.765 |  | THO999F/014A/002A
Ravensbourne West branch and Main River Culvert improvement | London Borough of Bromley | Thames | London Borough of Bromley, | 0 | 15 | 0 | 0 | 0 | 0 | 115 | 2018 to 2021 | 100 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 1802.822 |  | THO999F/050A/001A
Highgate Flood Alleviation | London Borough of Camden | Thames | Highgate Ward, London Borough of Camden | 0 | 15 | 0 | 0 | 0 | 0 | 165 | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 683.866 |  | THC024E/000A/025A
Clothworkers Wood - Wet Woodland Flood Storage | London Borough of Greenwich | Thames | Plumstead, Wickham Valley Watercourse | 0 | 0 | 0 | 25 | 0 | 0 | 175 | 2021 on | 16.35 | 8.65 | 0 | 0 | 0 | 0 | 30 | 0 | 444.525 |  | THO999F/028A/004A
Greenwich Groundwater preparation | London Borough of Greenwich | Thames | Royal Borough of Greenwich | 75 | 0 | 0 | 0 | 0 | 0 | 505 | 2018 to 2021 | 430 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 3690.514 |  | THO999F/028A/003A
Wickham Valley Water Course Flood Storage | London Borough of Greenwich | Thames | East Wickham, Wickham Valley Watercourse | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 2021 on | 20.35 | 24.65 | 0 | 0 | 0 | 0 | 60 | 0 | 956.909 |  | THO999F/028A/002A
Norcott Road Surface Water Flood Alleviation - Hackney | London Borough of Hackney | Thames | Hackney | 0 | 60 | 0 | 0 | 0 | 0 | 1236.7 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 730 | 0 | 20699.3 |  | THO999F/044A/004A
Islington Central | London Borough of Islington | Thames | Islington | 0 | 20 | 70 | 0 | 0 | 0 | 761.091 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 5410.173 |  | THC024E/000A/024A
Islington North | London Borough of Islington | Thames | Islington | 0 | 20 | 70 | 0 | 0 | 0 | 481.037 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 2241.009 |  | THC024E/000A/023A
Islington South | London Borough of Islington | Thames | Islington | 0 | 20 | 0 | 0 | 0 | 0 | 387.686 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 1650.488 |  | THC024E/000A/030A
Streatham Vale Flood Alleviation | London Borough of Lambeth | Thames | Streatham Vale, Lambeth | 0 | 60 | 0 | 0 | 0 | 0 | 725 | 2018 to 2021 | 620 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 10697 |  | THO999F/026A/003A
Cottenham Park Flood Alleviation | London Borough of Merton | Thames | Cottenham Park, Merton | 0 | 60 | 0 | 0 | 0 | 0 | 570 | 2016 to 2018 | 460 | 0 | 0 | 0 | 90 | 0 | 90 | 0 | 9294 |  | THO999F/040A/005A
East Merton Flood Alleviation | London Borough of Merton | Thames | East Merton, Merton | 0 | 34.674 | 19.8072 | 0 | 0 | 0 | 276.2068 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 3720 |  | THO999F/040A/006A
Seely Road Flood Alleviation | London Borough of Merton | Thames | Tooting | 0 | 0 | 0 | 0 | 0 | 0 | 397.5 | 2016 to 2018 | 335 | 0 | 0 | 0 | 195 | 0 | 195 | 0 | 12292 |  | THO999F/040A/001A
Chadwell Heath Flood Alleviation | London Borough of Redbridge | Thames | Chadwell Heath, London Borough of Redbridge | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 200 | 0 | 0 | 0 | 85 | 0 | 85 | 0 | 1735.146 |  | THO999F/024A/009A
North Peckham Flood Alleviation | London Borough of Southwark | Thames | Peckham, London Borough of Southwark | 0 | 0 | 0 | 110 | 0 | 0 | 1342.477 | 2021 on | 47 | 153 | 0 | 0 | 0 | 0 | 180 | 0 | 1775.318 |  | THO999F/027A/007A
Peckham Rye Flood Alleviation | London Borough of Southwark | Thames | Peckham, London Borough of Southwark | 0 | 200 | 0 | 0 | 0 | 0 | 2794 | 2018 to 2021 | 2594 | 0 | 0 | 0 | 255 | 0 | 255 | 0 | 19385.44 |  | THO999F/027A/005A
West Camberwell Flood Alleviation | London Borough of Southwark | Thames | Camberwell, London Borough of Southwark | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 2021 on | 50 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 1314 |  | THO999F/027A/006A
Clapham Junction Flood Alleviation | London Borough of Wandsworth | Thames | Clapham Junction | 0 | 75 | 0 | 0 | 0 | 0 | 950 | 2016 to 2018 | 820 | 0 | 0 | 0 | 565 | 0 | 565 | 0 | 22457 |  | THO999F/034A/002A
Tooting & Earlsfield Flood Alleviation | London Borough of Wandsworth | Thames | Tooting & Earlsfield | 0 | 50 | 40 | 0 | 0 | 0 | 710 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 8427 |  | THO999F/034A/003A
Westminster North West Strategy | London Borough of Westminster | Thames | Westminster | 0 | 0 | 0 | 90 | 0 | 0 | 4944 | 2018 to 2021 | 1203 | 1626 | 0 | 0 | 0 | 0 | 395 | 0 | 4196.842 |  | THO999F/041A/002B
Barton Road, Great Bramingham Flood Alleviation | Luton Borough Council | Thames | Luton/ Bramingham | 0 | 348 | 0 | 217 | 0 | 0 | 3065 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9909.58 |  | THC035E/000A/001A
Bloxham (Tadmarton Road) Flood Risk Management | Oxfordshire CC | Thames | Tadmarton Road, Bloxham, Cherwell District, Oxfordshire | 0 | 0 | 0 | 9 | 0 | 0 | 79 | 2016 to 2018 | 56 | 14 | 0 | 0 | 10 | 0 | 10 | 0 | 541.332 |  | THC002E/000A/035A
Mill Lane Chalgrove Flood Attenuation | South Oxfordshire DC | Thames | CHALGROVE, OXFORDSHIRE | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 40 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 134.701 |  | THC005E/000A/010A
West Hagbourne Flood Alleviation | South Oxfordshire DC | Thames | WEST HAGBOURNE, OXFORDSHIRE | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2016 to 2018 | 20 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 125.584 |  | THC043E/000A/040A
Wheatley West Attenuation | South Oxfordshire DC | Thames | Wheatley Brook in Wheatley, Oxfordshire | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 40 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 309.401 |  | THC005E/000A/009A
Bookham Flood Alleviation | Surrey CC | Thames | Great Bookham and Little Bookham | 0 | 75 | 0 | 0 | 0 | 0 | 1290 | 2018 to 2021 | 995.675 | 204.325 | 0 | 0 | 265 | 0 | 265 | 0 | 2167 |  | THO999F/032A/006A
Waller Drive, Newbury - Property Level Protection | West Berkshire Council | Thames | Waller Drive,Newbury | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 2016 to 2018 | 80.135 | 74.865 | 0 | 0 | 30 | 0 | 30 | 0 | 761 |  | THO999F/011A/002C
Barton-Under-Needwood, Barton brook Flood Alleviation | Environment Agency | Trent | Barton Under Needwood | 0 | 0 | 0 | 0 | 0 | 0 | 849.2 | 2016 to 2018 | 367 | 376 | 0 | 0 | 75 | 0 | 75 | 0 | 1542 |  | TRC003E/000A/031A
Braunstone Brook Flood Alleviation | Environment Agency | Trent | Braunstone, Leicester, Braunstone Brook | 0 | 290.5 | 0 | 0 | 0 | 0 | 3195.5 | 2016 to 2018 | 2905 | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 15017.027 |  | TRC003E/000A173A
Breaston Upstream Storage | Environment Agency | Trent | Breaston, Derbyshire | 0 | 20 | 0 | 0 | 0 | 0 | 295 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 1313.967 |  | TRC003E/000A195A
Collins Road Sheet Pile Refurbishment | Environment Agency | Trent | Wednesbury, West Bromwich | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 125 | 75 | 0 | 0 | 60 | 0 | 60 | 0 | 783.25 |  | TRC003E/000A161A
Cosby Flood Alleviation | Environment Agency | Trent | Cosby, Leicestershire | 0 | 35 | 0 | 0 | 0 | 0 | 547 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 3895.356 |  | TRC003E/000A184A
Fowlea Brook | Environment Agency | Trent | Stoke-on-Trent | 0 | 322 | 0 | 28 | 0 | 0 | 2000 | 2016 to 2018 | 1513 | 137 | 0 | 0 | 550 | 0 | 550 | 0 | 5152 |  | TRC003E/000A/021A
Isle of Axholme, Dirtness Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 780 | 2021 on | 8 | 152 | 0 | 0 | 0 | 0 | 95 | 0 | 259 |  | TRC002E/000A/007A
Isle of Axholme, Keadby Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 5000 | 3000 | 0 | 0 | 0 | 0 | 47100 | 0 | 35795.291 | 0 | 0 | 0 | 5750 | 0 | 5750 | 0 | 354676.52 | Other | TRC002E/000A/002A
Isle of Axholme, Low Bank Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 2018 to 2021 | 120 | 180 | 0 | 0 | 0 | 0 | 85 | 0 | 0.54 |  | TRC002E/000A/009A
Isle of Axholme, Snow Sewer Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 2021 on | 47 | 120 | 0 | 0 | 0 | 0 | 150 | 0 | 894.323 |  | TRC002E/000A/010A
Isle of Axholme, Tunnel Pits Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 841 | 2016 to 2018 | 146.5 | 490.5 | 0 | 0 | 15 | 0 | 15 | 0 | 1.74 |  | TRC002E/000A/011A
Isle of Axholme, Waterton Farm Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 147.1 | 2016 to 2018 | 60 | 72.6 | 0 | 0 | 35 | 0 | 35 | 0 | 0.8 |  | TRC002E/000A/012A
Isle of Axholme, West Stockwith Pumping Station Improvements | Environment Agency | Trent | West Stockwith | 0 | 0 | 0 | 0 | 0 | 0 | 2850 | TBC | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48570.869 |  | TRC002E/000A021A
Isle of Axholme, Woodcarr Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 2021 on | 94.5 | 26.5 | 0 | 0 | 55 | 0 | 75 | 0 | 0.834 |  | TRC002E/000A/013A
Keadby Warping Drain Outfall | Environment Agency | Trent | River Trent, Keadby | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 2016 to 2018 | 350 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 813.523 |  | TRC003E/000A192A
Kelverley Grove flood defence repairs | Environment Agency | Trent | West Bromwich | 100 | 0 | 0 | 0 | 0 | 0 | 489.9 | 2016 to 2018 | 365 | 0 | 0 | 0 | 140 | 0 | 140 | 0 | 2282 |  | TRC003E/000A/012A
Loughborough Flood Risk Management | Environment Agency | Trent | Loughborough, Tributaries of the River Soar | 109.398 | 109.398 | 0 | 0 | 0 | 0 | 2521.264 | 2016 to 2018 | 2202.468 | 0 | 0 | 0 | 430 | 0 | 430 | 0 | 14117.632 |  | TRC003E/000A/063A
Nuneaton FRC Refurbishment | Environment Agency | Trent | Nuneaton | 0 | 50 | 0 | 0 | 0 | 0 | 450 | 2018 to 2021 | 400 | 0 | 0 | 0 | 570 | 0 | 570 | 0 | 3451.365 |  | TRC003E/000A190A
River Tame, Bromford, Birmingham, Flood Alleviation | Environment Agency | Trent | River Tame Catchment, Bromford, Birmingham | 150 | 2157.542 | 0 | 0 | 0 | 0 | 14947.01 | 2016 to 2018 | 9491.368 | 0 | 0 | 0 | 3040 | 0 | 3040 | 0 | 102228 |  | TRC003E/000A/534A
Saffron Brook Flood Alleviation | Environment Agency | Trent | Aylestone, Leicester, Saffron Brook | 0 | 556 | 0 | 0 | 0 | 0 | 6116 | 2018 to 2021 | 5560 | 0 | 0 | 0 | 695 | 0 | 695 | 0 | 21147.749 |  | TRC003E/000A169A
Selly Park South (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 99.92 | 0 | 0 | 0 | 0 | 762.17 | 2018 to 2021 | 662.25 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 6382.83 |  | TRC003E/000A/057A
Sheepy Magna Flood Risk Reduction | Environment Agency | Trent | Sheepy Magna on River Sence | 1.5 | 0 | 0 | 3.5 | 0 | 0 | 50.2 | 2021 on | 13.5 | 31.7 | 0 | 0 | 5 | 0 | 5 | 0 | 24 |  | IMMI001397
Bean Croft Property Level Protection | Birmingham City Council | Trent | Woodgate Valley, Birmingham | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 2018 to 2021 | 48 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 192 |  | TRC003F/000A/121A
Nesfield Close Community Protection | Birmingham City Council | Trent | Kings Norton, Birmingham | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 2018 to 2021 | 24 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 57.477 |  | TRC003F/000A/124A
Overdale Road Property Level Protection | Birmingham City Council | Trent | Quinton, Birmingham | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 8.734 | 6.266 | 0 | 0 | 2 | 0 | 2 | 0 | 45 |  | TRC003F/000A/089A
Slade Road Community Protection | Birmingham City Council | Trent | Erdington, Birmingham | 0 | 0 | 0 | 0 | 0 | 0 | 173 | 2018 to 2021 | 173 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 152.908 |  | TRC003F/000A/110A
Littleover Brook, conveyance and flood detention | Derby City Council | Trent | Littleover Brook, Derby | 0 | 133.046 | 0 | 0 | 0 | 0 | 1229.808 | 2018 to 2021 | 1096.762 | 0 | 0 | 0 | 455 | 0 | 455 | 0 | 16092.1496 |  | TRC003F/000A/094A
Leicester, Egginton Street Surface Water Flood Alleviation | Leicester City Council | Trent | Areas around Eggington Street to the East of the City of Leicester to the east of the River Soar | 0 | 10 | 0 | 0 | 0 | 0 | 150 | 2018 to 2021 | 80 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 232.524 |  | TRC003F/000A/111A
Leicester, Leicester Royal Infirmary Surface Water Flood Alleviation | Leicester City Council | Trent | Areas around the LRI to the South of the City of Leicester to the east of the River Soar | 0 | 4 | 0 | 3 | 0 | 0 | 100 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 9.07 |  | TRC003F/000A/082A
Leicester, Oakland Road Surface Water Flood Alleviation | Leicester City Council | Trent | Areas around Oakland Road to the South of the City of Leicester to the east of the River Soar | 0 | 16 | 0 | 10 | 0 | 0 | 250 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 651.942 |  | TRC003F/000A/084A
Leicester, Redhill Way Surface Water Flood Alleviation | Leicester City Council | Trent | Areas around Redhill Way to the North of the City of Leicester to the west of the River Soar | 0 | 20 | 0 | 0 | 0 | 0 | 250 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 275 |  | TRC003F/000A/085A
Broughton Astley, Harborough | Leicestershire CC | Trent | Broughton Astely, Harborough | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2018 to 2021 | 40 | 10 | 0 | 0 | 10 | 0 | 10 | 0 | 250 |  | TRC003F/000A/120A
Swithland Brook, Swithland Flood Alleviation | Leicestershire CC | Trent | Swithland Brook , Swithland | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 2018 to 2021 | 70 | 80 | 0 | 0 | 20 | 0 | 20 | 0 | 460 |  | TRC003F/000A/047A
Nottingham City Council Individual Property Protection Programme | Nottingham City Council | Trent | Nottingham, various | 0 | 56.373 | 0 | 0 | 0 | 0 | 338.238 | 2018 to 2021 | 112.746 | 0 | 0 | 0 | 35 | 0 | 70 | 0 | 939.604 |  | TRC003F/000A/101A
Anston Brook Catchment Flood Risk Reduction, Anston & Dinnington | Rotherham MBC | Trent | Laughton Common & Dinnington, Sheffield, South Yorkshire | 0 | 20 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 180 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 785.219 |  | TRC003F/000A/108A
Maltby Surface Water Flood Alleviation | Rotherham MBC | Trent | Maltby, Rotherham, South Yorkshire | 0 | 30 | 0 | 0 | 0 | 0 | 253 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 541.086 |  | TRC003F/000A/104A
Dickens Heath balancing pond improvement | Solihull MBC | Trent | On the south edge of Dickens Heath, off Rumbush Brook which is a tributary of the Mount Brook | 0 | 20 | 0 | 10 | 0 | 0 | 230 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 325.304 |  | TRC004F/000A/129A
Codsall Flood Alleviation | Staffordshire County Council | Trent | Codsall , Oaken Park | 13.5 | 0 | 0 | 0 | 0 | 0 | 18.5 | 2018 to 2021 | 5 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 108.04 |  | TRC003F/000A/090A
Marsh Lane, Lichfield | Staffordshire County Council | Trent | Lichfield, Marsh Lane | 0 | 0 | 0 | 0 | 0 | 0 | 54.6 | 2021 on | 27 | 27.6 | 0 | 0 | 0 | 0 | 5 | 0 | 80.376 |  | _C
Stretton Surface Water Pumping Station, Clay Mills, Burton on Trent | Staffordshire County Council | Trent | Burton upon Trent | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 2016 to 2018 | 500 | 0 | 0 | 0 | 130 | 0 | 130 | 0 | 3076 |  | TRC003F/000A/066A
Weston Coyney, Stoke-on-Trent, Surface Water Flood Alleviation | Stoke on Trent City Council | Trent | Stoke-on-Trent | 0 | 50 | 0 | 0 | 0 | 0 | 575 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 6088 |  | TRC003F/000A/028A
Polesworth,Tamworth, Flood Alleviation | Warwickshire CC | Trent | Polesworth | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 2021 on | 12 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 482 |  | TRC003F/000A/057A
Bradford -on-Avon Flood Defence | Environment Agency | Wessex | Bradford -on-Avon, Wiltshire. Bristol Avon. | 0 | 0 | 0 | 5 | 0 | 0 | 367.23 | 2016 to 2018 | 131.73 | 230.5 | 0 | 0 | 20 | 0 | 20 | 0 | 1589 |  | WXC005E/000A/139A
Bridport | Environment Agency | Wessex | Bridport Dorset. | 0 | 0 | 0 | 0 | 0 | 0 | 569.765 | 2018 to 2021 | 168.13 | 401.635 | 0 | 0 | 50 | 0 | 50 | 0 | 333.503 |  | WXC004E/000A/093A
Brislington Flood Defence Improvements | Environment Agency | Wessex | Brislington, Bristol. | 0 | 0 | 0 | 49.155 | 0 | 0 | 1956.65 | 2016 to 2018 | 1039 | 868.495 | 0 | 0 | 235 | 0 | 235 | 0 | 1538.9 |  | WXC005E/000A/138A
Christchurch Priory Quay | Environment Agency | Wessex | Christchurch Harbour, Christchurch, Dorset. | 0 | 0 | 0 | 5.175 | 0 | 0 | 211.365 | 2016 to 2018 | 157.98 | 48.21 | 0 | 0 | 40 | 0 | 40 | 0 | 474.509 |  | WXC002E/000A/060A
Christchurch Willow Way / Riverside | Environment Agency | Wessex | Christchurch Harbour, Christchurch, Dorset. | 0 | 0 | 0 | 5.356 | 0 | 0 | 411.251 | 2016 to 2018 | 211.87 | 194.025 | 0 | 0 | 35 | 0 | 35 | 0 | 1774.9 |  | WXC002E/000A/061A
Currymoor Pumping Station Improvements | Environment Agency | Wessex | Currymoor pumping station, River Tone, Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 286.885 | 2018 to 2021 | 200.82 | 86.065 | 0 | 0 | 50 | 0 | 50 | 0 | 602.224 |  | WXC007E/000A/230A
Dalby Avenue Trash Screen Improvements | Environment Agency | Wessex | Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 2018 to 2021 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 80.465 |  | WXC007E/000A/171A
Dorchester Flood Defence Improvements | Environment Agency | Wessex | Dorchester, Dorset. | 0 | 0 | 0 | 0 | 0 | 0 | 573.76 | 2016 to 2018 | 286.88 | 286.88 | 0 | 0 | 65 | 0 | 65 | 0 | 635.554 |  | WXC001E/000A/040A
Dunball Sluice Gates Refurbishment | Environment Agency | Wessex | Dunball sluice, Kings Sedgemoor Drain | 0 | 0 | 0 | 0 | 0 | 0 | 258.75 | 2018 to 2021 | 207 | 51.75 | 0 | 0 | 130 | 0 | 130 | 0 | 1965.782 |  | WXC007E/000A/229A
Gold Corner Pumping StationImprovements | Environment Agency | Wessex | Gold Corner pumping station, River Brue, Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 293.945 | 2018 to 2021 | 186.82 | 107.125 | 0 | 0 | 15 | 0 | 15 | 0 | 119.725 |  | WXC007E/000A/228A
Henley Sluice | Environment Agency | Wessex | Somerton | 0 | 0 | 0 | 0 | 0 | 0 | 370.65 | 2018 to 2021 | 370.65 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 594 |  | WXS007E/000A/187A
Kings Sedgmoor Drain Asset Improvements | Environment Agency | Wessex | River Parrett, Somerset Levels | 0 | 0 | 0 | 0 | 0 | 0 | 237.54 | 2018 to 2021 | 195.97 | 41.57 | 0 | 0 | 65 | 0 | 65 | 0 | 2428 |  | WXC007E/000A/231A
Kingston Seymour Asset Improvements | Environment Agency | Wessex | South of Clevedon, North Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 148.16 | 2016 to 2018 | 96.41 | 51.75 | 0 | 0 | 30 | 0 | 30 | 0 | 358 |  | WXC006E/000A/162A
Land Yeo Lower & Blind Yeo Asset Improvements | Environment Agency | Wessex | Clevedon North Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 1511.88 | 2021 on | 498.925 | 166.31 | 0 | 0 | 0 | 0 | 200 | 0 | 3437.251 |  | WXS004E/001A/052A
Longmoor Tunnel Refurbishment | Environment Agency | Wessex | Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 2016 to 2018 | 300 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 435.145 |  | WXC005E/000A/172A
Maiden Newton Improvements | Environment Agency | Wessex | Maiden Newton, Dorset. | 0 | 0 | 0 | 0 | 0 | 0 | 573.72 | 2016 to 2018 | 143.4 | 430.32 | 0 | 0 | 40 | 0 | 40 | 0 | 158.803 |  | WXC001E/000A/039A
Malago Asset Improvements | Environment Agency | Wessex | Bedminster, Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 161.755 | 2018 to 2021 | 54.635 | 107.12 | 0 | 0 | 20 | 0 | 20 | 0 | 121.521 |  | WXC005E/000A/169A
Muchelney Ham Flood Defence Improvements | Environment Agency | Wessex | Muchelney, Somerset. | 0 | 0 | 0 | 0 | 0 | 0 | 310.5 | 2018 to 2021 | 207 | 103.5 | 0 | 0 | 25 | 0 | 25 | 0 | 245.423 |  | WXC008E/000A/035A
Parrett at Langport Asset Improvements | Environment Agency | Wessex | River Parrett near Langport | 0 | 0 | 0 | 0 | 0 | 0 | 114.75 | 2018 to 2021 | 80.32 | 34.43 | 0 | 0 | 50 | 0 | 50 | 0 | 120 |  | WXC006E/000A/160A
Parrett Estuary - Cannington Bends | Environment Agency | Wessex | River Parrett between Bridgwater and Combwich | 0 | 0 | 0 | 100 | 0 | 0 | 3307 | 2016 to 2018 | 2642 | 500 | 0 | 0 | 1255 | 0 | 1255 | 0 | 6700 |  | WXS003E/001A/003A
Parrett Langport - Thorney Asset Improvements | Environment Agency | Wessex | River Parrett, Somerset Levels | 0 | 0 | 0 | 0 | 0 | 0 | 221.745 | 2018 to 2021 | 166.31 | 55.435 | 0 | 0 | 40 | 0 | 40 | 0 | 775.17 |  | WXC006E/000A/161A
River Brue Fish Passage Improvements | Environment Agency | Wessex | Baltonsborough / River Brue | 0 | 0 | 0 | 0 | 0 | 0 | 419 | 2016 to 2018 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | WXC006E/000A/149A
Roadwater Improvements | Environment Agency | Wessex | Roadwater, West Somerset. | 0 | 0 | 0 | 20.175 | 0 | 0 | 563.5 | 2018 to 2021 | 197.375 | 345.95 | 0 | 0 | 35 | 0 | 35 | 0 | 1272 |  | WXC008E/000A/036A
Salisbury City Centre Flood Alleviation | Environment Agency | Wessex | Salisbury | 140 | 508.165 | 0 | 210 | 0 | 0 | 4614 | 2016 to 2018 | 3153.835 | 570 | 0 | 0 | 705 | 0 | 705 | 0 | 21639.781 |  | WXC002E/00A/054A
Saltmoor Pumping Station Improvements | Environment Agency | Wessex | Saltmoor pumping station, River Parret, Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 138.59 | 2018 to 2021 | 83.155 | 55.435 | 0 | 0 | 50 | 0 | 50 | 0 | 727.224 |  | WXO002E/000A/159A
Tisbury Asset Improvements | Environment Agency | Wessex | Tisbury, | 0 | 0 | 0 | 0 | 0 | 0 | 122.93 | 2018 to 2021 | 61.465 | 61.465 | 0 | 0 | 50 | 0 | 50 | 0 | 29 |  | WXC002E/000A/062A
Twerton Gate Vertical Gate Refurbishment | Environment Agency | Wessex | Twerton Gate, River Avon, Bath | 0 | 0 | 0 | 0 | 0 | 0 | 160.68 | 2018 to 2021 | 107.12 | 53.56 | 0 | 0 | 50 | 0 | 50 | 0 | 702.224 |  | WXC005E/000A/170A
Wessex Property Level Protection yrs 4 to 8 | Environment Agency | Wessex | Various | 0 | 400 | 0 | 400 | 0 | 0 | 5000 | 2018 to 2021 | 950 | 950 | 0 | 0 | 330 | 0 | 600 | 0 | 25043.913 |  | WXO004E/000A/060A_2
West Bay Coastal Improvements | Environment Agency | Wessex | West Bay, near Bridport, Dorset | 0 | 0 | 0 | 0 | 0 | 0 | 2374.65 | 2018 to 2021 | 545 | 544.825 | 0 | 0 | 0 | 0 | 255 | 0 | 575.392 |  | WXS002E/000A/103A
West Sedgemoor Pumping Station Improvements | Environment Agency | Wessex | West Sedgemoor pumping station, River Parrett, Somerset | 0 | 0 | 0 | 0 | 0 | 0 | 296.925 | 2018 to 2021 | 166.275 | 130.65 | 0 | 0 | 15 | 0 | 15 | 0 | 117.846 |  | WXC007E/000A/227A
Westmoor & Southmoor Asset Improvements | Environment Agency | Wessex | Somerset Levels | 0 | 0 | 0 | 0 | 0 | 0 | 114.75 | 2018 to 2021 | 91.8 | 22.95 | 0 | 0 | 0 | 0 | 0 | 0 | 18 |  | WXC007E/000A/232A
Williton Flood Defence | Environment Agency | Wessex | Williton, West Somerset. | 0 | 0 | 0 | 55.439 | 0 | 0 | 2088.812 | 2016 to 2018 | 937.21 | 1096.163 | 0 | 0 | 170 | 0 | 170 | 0 | 3345.4 |  | WXC008E/000A/034A
Wilton Wylye Flood Bank | Environment Agency | Wessex | Wilton River Avon SSSI | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 2016 to 2018 | 47 | 130 | 0 | 0 | 35 | 0 | 35 | 0 | 222 |  | WXC002E/000A/039A
Wimborne Flood Defence Improvements | Environment Agency | Wessex | Wimborne | 0 | 0 | 0 | 0 | 0 | 0 | 217.465 | 2018 to 2021 | 163.9 | 53.565 | 0 | 0 | 50 | 0 | 50 | 0 | 95 |  | WXC003E/000A/065A
Yate Chipping Sodbury Defence Improvements | Environment Agency | Wessex | River Frome, Yate, Bristol | 0 | 30 | 0 | 0 | 0 | 0 | 300 | 2018 to 2021 | 270 | 0 | 0 | 0 | 125 | 0 | 125 | 0 | 2602.712 |  | WXC005E/000A/136A
Central Poole Flood Defences | Borough of Poole | Wessex | Poole Town Centre | 0 | 0 | 0 | 0 | 0 | 0 | 780 | 2016 to 2018 | 438 | 0 | 0 | 0 | 30 | 0 | 75 | 0 | 39928 |  | WXS001F/000A/036A
Poole Frontage Management - Beach Renourishment 2015 - 16 | Borough of Poole | Wessex | Poole coastal frontage | 50 | 0 | 0 | 0 | 0 | 0 | 1600 | 2016 to 2018 | 1450 | 0 | 0 | 0 | 0 | 795 | 0 | 795 | 136654.875 |  | WXS001C/000A/025A
Sterte Pumping Station | Borough of Poole | Wessex | Sterte, Poole | 50 | 0 | 0 | 0 | 0 | 0 | 412 | 2016 to 2018 | 362 | 0 | 0 | 0 | 210 | 0 | 210 | 0 | 5347.8 |  | WXS001F/000A/038A
Lyme Regis Coast Protection Beach Management 2017/18 on | West Dorset DC | Wessex | Lyme Regis | 0 | 45 | 0 | 0 | 0 | 0 | 315 | 2016 to 2018 | 135 | 0 | 0 | 0 | 0 | 85 | 0 | 135 | 2421.5 |  | WXS002C/000A/096A
West Bay Coast Protection - Beach Management 2017/18 on | West Dorset DC | Wessex | West Bay | 0 | 56 | 0 | 0 | 0 | 0 | 392 | 2016 to 2018 | 168 | 0 | 0 | 0 | 0 | 60 | 0 | 90 | 9556 |  | WXS002C/000A/097A
Melksham, Forest Road Surface Water Drainage Improvements | Wiltshire Council | Wessex | Melksham | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 2018 to 2021 | 153 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 1324 |  | WXC005F/000A/151A
Blackburn Brook Culvert | Environment Agency | Yorkshire | Chapeltown, Blackburn Brook | 0 | 10 | 0 | 0 | 0 | 0 | 110 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 199.3611 |  | YOC356E/000A/137A
Boroughbridge Floodgates Maintenance | Environment Agency | Yorkshire | Boroughbridge, River Ure | 10 | 0 | 0 | 0 | 0 | 0 | 110 | 2016 to 2018 | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 1711.554 |  | YOC353E/000A/047A
Boroughbridge Pumping Station Refurbishment | Environment Agency | Yorkshire | Boroughbridge, River Tutt Diversion Channel | 0 | 20 | 0 | 0 | 0 | 0 | 320 | 2018 to 2021 | 300 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 2247.794 |  | YOC353E/000A/049A
Catterick Gravel Removal | Environment Agency | Yorkshire | Catterick, Brough Beck | 0 | 10 | 0 | 0 | 0 | 0 | 110 | 2018 to 2021 | 100 | 0 | 0 | 0 | 145 | 0 | 145 | 0 | 484.466 |  | YOC353E/000A/053A
Cawood Foreshore Erosion | Environment Agency | Yorkshire | Cawood, River Ouse | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 2018 to 2021 | 140 | 0 | 0 | 0 | 125 | 0 | 125 | 0 | 502.988 |  | YOC353E/000A/055A
Dearne Mouth Sluices Refurbishments | Environment Agency | Yorkshire | Conisborough, River Dearne | 0 | 20 | 0 | 0 | 0 | 0 | 145 | 2018 to 2021 | 125 | 0 | 0 | 0 | 55 | 0 | 55 | 0 | 392.3955 |  | YOC356E/000A/071A
Dearne Washlands Optimisation | Environment Agency | Yorkshire | Bolton Upon Dearne, River Dearne | 50 | 0 | 0 | 0 | 0 | 0 | 350 | 2018 to 2021 | 300 | 0 | 0 | 0 | 190 | 0 | 190 | 0 | 2605.3645 |  | YOC356E/000A/074A
Ellin Street Culvert | Environment Agency | Yorkshire | Sheffield, Porter Brook | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 2016 to 2018 | 120 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 1814.61 |  | YOC356E/000A/080A
Foss Barrier Pump & Software Replacement | Environment Agency | Yorkshire | York, River Foss | 400 | 0 | 0 | 0 | 0 | 0 | 3150 | 2016 to 2018 | 2750 | 0 | 0 | 0 | 1780 | 0 | 1780 | 0 | 19758.005 |  | YOC353E/000A/091A
Grimscar Dyke Culverts Repairs | Environment Agency | Yorkshire | Huddersfield, Grimscar Dyke | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 2016 to 2018 | 175 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 998.196 |  | YOC355E/000A/095A
Hipper Shoal Removal | Environment Agency | Yorkshire | Brampton, River Hipper | 0 | 10 | 0 | 0 | 0 | 0 | 160 | 2018 to 2021 | 150 | 0 | 0 | 0 | 120 | 0 | 120 | 0 | 338.5552 |  | YOC356E/000A/086A
Hull River Defences | Environment Agency | Yorkshire | Hull | 620 | 1700 | 0 | 0 | 0 | 0 | 21208.625 | 2016 to 2018 | 17850 | 0 | 0 | 0 | 15000 | 0 | 45000 | 0 | 724444 |  | YOC357E/001A/002A
Humber: Hull frontage | Environment Agency | Yorkshire | Hull | 900 | 1085 | 0 | 0 | 0 | 0 | 19181 | 2016 to 2018 | 16300 | 0 | 0 | 0 | 22000 | 0 | 22000 | 0 | 427000 |  | YOS399E/001A/036A
Humber: Skeffling Land Purchase and Managed Realignment | Environment Agency | Yorkshire | Skeffling, River Humber | 2000 | 0 | 0 | 0 | 0 | 0 | 12024 | 2016 to 2018 | 4596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory Requirement | YOS399E/001A/039A
Keighley Replacement of "Ski Jump", Aireworth Road | Environment Agency | Yorkshire | Keighley, River Worth | 0 | 15 | 0 | 0 | 0 | 0 | 165 | 2018 to 2021 | 150 | 0 | 0 | 0 | 125 | 0 | 125 | 0 | 97.722 |  | YOC354E/000A/044A
Lowther Penstock / Outfall replacement & barrier bank Refurbishment | Environment Agency | Yorkshire | Allerton Bywater, River Aire | 0 | 20 | 0 | 0 | 0 | 0 | 220 | 2018 to 2021 | 200 | 0 | 0 | 0 | 295 | 0 | 295 | 0 | 2025.767 |  | YOC354E/000A/046A
Marsden Culvert | Environment Agency | Yorkshire | Marsden, River Colne | 0 | 20 | 0 | 0 | 0 | 0 | 170 | 2018 to 2021 | 150 | 0 | 0 | 0 | 135 | 0 | 135 | 0 | 2087.4386 |  | YOC355E/000A/101A
Meadowgate Regulator Refurbishment | Environment Agency | Yorkshire | Beighton, River Rother | 0 | 10 | 0 | 0 | 0 | 0 | 110 | 2018 to 2021 | 100 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 851.7227 |  | YOC356E/000A/092A
Meersbrook Culvert | Environment Agency | Yorkshire | Sheffield, Meersbrook | 0 | 15 | 0 | 0 | 0 | 0 | 115 | 2018 to 2021 | 100 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 818.0802 |  | YOC356E/000A/094A
Mile Thorne Bank Refurbishment | Environment Agency | Yorkshire | Doncaster, River Don | 100 | 0 | 0 | 0 | 0 | 0 | 965 | 2016 to 2018 | 775 | 0 | 0 | 0 | 265 | 0 | 265 | 0 | 1305.61 |  | YOC356E/000A/053A
Selby Floodgates Maintenance | Environment Agency | Yorkshire | Selby, River Ouse | 0 | 30 | 0 | 0 | 0 | 0 | 330 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 375 | 0 | 0 |  | YOC353E/000A/077A
Sheaf Screen Works | Environment Agency | Yorkshire | Sheffield, River Sheaf | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 100 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 849.176 |  | YOC356E/000A/110A
Skell Banks Reforming | Environment Agency | Yorkshire | Skellow, The Skell | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 200 | 0 | 0 | 0 | 130 | 0 | 130 | 0 | 562.667 |  | YOC356E/000A/112A
Skellow Rail Tie-in Bridge Parapet Raising | Environment Agency | Yorkshire | Skellow, The Skell | 400 | 0 | 0 | 0 | 0 | 0 | 500 | 2018 to 2021 | 100 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 188107.6 |  | YOC356E/000A/113A
Skipton Coach Street Culvert | Environment Agency | Yorkshire | Skipton, Eller-Embsay Beck | 0 | 10 | 0 | 0 | 0 | 0 | 110 | 2018 to 2021 | 100 | 0 | 0 | 0 | 125 | 0 | 125 | 0 | 1038.914 |  | YOC354E/000A/049A
Spen Culverts Replacement | Environment Agency | Yorkshire | Cleckheaton, River Spen | 0 | 20 | 0 | 0 | 0 | 0 | 220 | 2018 to 2021 | 200 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 747.258 |  | YOC355E/000A/105A
St Aiden's Reforming banks | Environment Agency | Yorkshire | Mickletown, River Aire | 0 | 20 | 0 | 0 | 0 | 0 | 220 | 2018 to 2021 | 200 | 0 | 0 | 0 | 145 | 0 | 145 | 0 | 1350.565 |  | YOC354E/000A/051A
Thorne Flood Wall Replacement | Environment Agency | Yorkshire | Thorne, River Don | 50 | 0 | 0 | 0 | 0 | 0 | 550 | 2018 to 2021 | 500 | 0 | 0 | 0 | 275 | 0 | 275 | 0 | 4192.198 |  | YOC356E/000A/118A
Tickton Pumping Station Refurbishment | Environment Agency | Yorkshire | Tickton, Holderness Drain | 0 | 20 | 0 | 0 | 0 | 0 | 320 | 2021 on | 300 | 0 | 0 | 0 | 130 | 0 | 130 | 0 | 733.312 |  | YOC357E/000A/055A
Upper and Middle Hull Embankment Repairs | Environment Agency | Yorkshire | Beverley, River Hull | 0 | 250 | 0 | 0 | 0 | 0 | 2000 | TBC | 500 | 0 | 0 | 0 | 0 | 0 | 2690 | 0 | 26750.506 |  | YOC357E/000A/056A
Victoria Clough, Earby Culvert Repair | Environment Agency | Yorkshire | Earby, Victoria Clough | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 2016 to 2018 | 450 | 0 | 0 | 0 | 145 | 0 | 145 | 0 | 1266.0554 |  | YOC354E/000A/055A
Whitwood Mere Barrier Bank | Environment Agency | Yorkshire | Castleford, River Calder | 0 | 30 | 0 | 0 | 0 | 0 | 330 | 2018 to 2021 | 300 | 0 | 0 | 0 | 185 | 0 | 185 | 0 | 1628.602 |  | YOC354E/000A/056A
Wyke Beck Repair Riparian wall upstream of Selby Road | Environment Agency | Yorkshire | Leeds, Wyke Beck | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 100 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 1223.4094 |  | YOC354E/000A/058A
York Flood Gates Maintenance | Environment Agency | Yorkshire | York, River Ouse | 0 | 30 | 0 | 0 | 0 | 0 | 330 | 2016 to 2018 | 300 | 0 | 0 | 0 | 215 | 0 | 215 | 0 | 2662.81 |  | YOC353E/000A/085A
River Foss Channel Improvements | Ainsty 2008 IDB | Yorkshire | Earswick,York | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2016 to 2018 | 20 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 319 |  | YOC353I/000A/050A
Causeway Dale Weel | Beverley & North Holderness IDB | Yorkshire | Causeway Dale Weel | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2016 to 2018 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345.918 |  | YOC357I/000A/046A
Constable Drain North Frodingham | Beverley & North Holderness IDB | Yorkshire | Constable Drain North Frodingham | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 10 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 349.064 |  | YOC357I/000A/038A
Cross Drain Leven | Beverley & North Holderness IDB | Yorkshire | Cross Drain Leven | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695.836 |  | YOC357I/000A/047A
Firth Drain Leven | Beverley & North Holderness IDB | Yorkshire | Firth Drain Leven | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341.397 |  | YOC357I/000A/049A
Fox Drain Tributary Dunswell | Beverley & North Holderness IDB | Yorkshire | Fox Drain Tributary Dunswell | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 2018 to 2021 | 8 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 626.112 |  | YOC357I/000A/051A
Hards Covert Burton Agnes | Beverley & North Holderness IDB | Yorkshire | Hards Covert Burton Agnes | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2018 to 2021 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169.698 |  | YOC357I/000A/052A
Hull Road East Drain Woodmansey | Beverley & North Holderness IDB | Yorkshire | Hull Road East Drain Woodmansey | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2016 to 2018 | 6 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 770.055 |  | YOC357I/000A/053A
Hull Road West Drain Woodmansey | Beverley & North Holderness IDB | Yorkshire | Hull Road West Drain Woodmansey | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2016 to 2018 | 6 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 661.228 |  | YOC357I/000A/054A
Mill Dam Beck Brandesburton | Beverley & North Holderness IDB | Yorkshire | Mill Dam Beck Brandesburton | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337.918 |  | YOC357I/000A/041A
North Bullock Arram | Beverley & North Holderness IDB | Yorkshire | North Bullock Arram | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2016 to 2018 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514.377 |  | YOC357I/000A/042A
Old Main Drain Wawne 2 | Beverley & North Holderness IDB | Yorkshire | Old Main Drain Wawne | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336.397 |  | YOC357I/000A/056A
Parting Dike Eske | Beverley & North Holderness IDB | Yorkshire | Parting Dike Eske | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2018 to 2021 | 7 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 620.966 |  | YOC357I/000A/057A
Riston Pumping Station | Beverley & North Holderness IDB | Yorkshire | Arnold & Riston Drain near the White Cross Roundabout Leven | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 2018 to 2021 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 673.836 |  | YOC357I/000A/019A
Rotsea Drain Hempholme | Beverley & North Holderness IDB | Yorkshire | Rotsea Drain Hempholme | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 10 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 1059.114 |  | YOC357I/000A/058A
Swinemoor North Tickton | Beverley & North Holderness IDB | Yorkshire | Swinemoor North Tickton | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 10 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 1132.786 |  | YOC357I/000A/061A
Western Drain Woodmansey | Beverley & North Holderness IDB | Yorkshire | Western Drain Woodmansey | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 10 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 774.361 |  | YOC357I/000A/063A
Skipton Road | Bradford MDC | Yorkshire | Skipton Road, Utley, Keighley. Ordinary watercourse | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2016 to 2018 | 90 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 531.739 |  | YOC354F/000A/037A
Allescholes Road Catchment Flood Alleviation | Calderdale MBC | Yorkshire | Allescholes Road, Walsden | 0 | 25 | 0 | 0 | 0 | 0 | 145 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 395 |  | YOC355F/000A/085A
Cragg Road Culvert Improvements | Calderdale MBC | Yorkshire | Cragg Road, Mytholmroyd | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2021 on | 150 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 929 |  | YOC355F/000A/091A
London Road, Mankinholes | Calderdale MBC | Yorkshire | Upstream of the confluence between Luddenden Brook and River Calder in the centre of Luddenden Foot. | 0 | 10 | 0 | 0 | 0 | 0 | 60 | 2018 to 2021 | 50 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 480 |  | YOC355F/000A/098A
Luddenden Brook Gravel Arrest | Calderdale MBC | Yorkshire | Upstream of the confluence between Luddenden Brook and River Calder in the centre of Luddenden Foot. | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 150 | 0 | 0 | 0 | 55 | 0 | 55 | 0 | 1345 |  | YOC355F/000A/099A
Major Clough | Calderdale MBC | Yorkshire | Major Clough, Todmorden | 0 | 10 | 0 | 0 | 0 | 0 | 60 | 2018 to 2021 | 50 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 1456 |  | YOC355F/000A/100A
Stoodley Grange/Lee Bottom Road | Calderdale MBC | Yorkshire | Mankinholes | 0 | 10 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 80 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 2048 |  | YOC355F/000A/108A
Willowfield Estate | Calderdale MBC | Yorkshire | Hillslope to the South West of Walsden Water in Shade, Todmorden. | 0 | 10 | 0 | 0 | 0 | 0 | 110 | 2018 to 2021 | 100 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 1115 |  | YOC355F/000A/112A
Beverley Model Farm Drain | East Riding of Yorkshire Council | Yorkshire | Beverley | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2018 to 2021 | 100 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 5972.252 |  | YOC357F/000A/074A
Flamborough Hartendale Gutter | East Riding of Yorkshire Council | Yorkshire | Flamborough | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2016 to 2018 | 20 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 374.243 |  | YOC357F/000A/080A
Hessle Fleet Drain Ancillaries | East Riding of Yorkshire Council | Yorkshire | Hessle | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2016 to 2018 | 500 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 10429.293 |  | YOC357F/000A/083A
Howden East Drainage Improvements | East Riding of Yorkshire Council | Yorkshire | Howden | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 40 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 874.9 |  | YOC357F/000A/087A
Molescroft Sister Beck Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Molescroft | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 2018 to 2021 | 190 | 30 | 0 | 0 | 0 | 0 | 190 | 0 | 4100.336 |  | YOC357F/000A/103A
Nunburnholme Watercourse Improvements | East Riding of Yorkshire Council | Yorkshire | Nunburnholme | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2018 to 2021 | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 648.974 |  | YOC353F/000A/004A
Wilberfoss Flood Attenuation | East Riding of Yorkshire Council | Yorkshire | Wilberfoss | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 20 | 20 | 0 | 0 | 30 | 0 | 30 | 0 | 660.876 |  | YOC353F/000A/009A
Bund alongside Old Fleet Drain, Kingston upon Hull | Kingston upon Hull City Council | Yorkshire | Kingston upon Hull, Old Fleet Drain. | 0 | 30 | 0 | 0 | 0 | 0 | 590 | 2018 to 2021 | 560 | 0 | 0 | 0 | 295 | 0 | 295 | 0 | 5360 |  | YOC357F/000A/027A
Newland Flood Alleviaiton - Sustainable Drainage retrofit | Kingston upon Hull City Council | Yorkshire | Kingston upon Hull, Newland | 0 | 40 | 0 | 0 | 0 | 0 | 2534 | 2018 to 2021 | 1298.8 | 0 | 0 | 0 | 260 | 0 | 1295 | 0 | 58480 |  | YOC357F/000A/038A
Sutton Ings Flood Alleviation - Sustainable Drainage retrofit | Kingston upon Hull City Council | Yorkshire | Kingston upon Hull, Sutton Ings | 0 | 40 | 0 | 0 | 0 | 0 | 3510 | 2018 to 2021 | 2294 | 0 | 0 | 0 | 410 | 0 | 2055 | 0 | 36330 |  | YOC357F/000A/037A
Potternewton Surface Water Flood Alleviation, Leeds. | Leeds City Council | Yorkshire | Potternewton, Leeds. Unamed Watercourse | 0 | 30 | 0 | 0 | 0 | 0 | 174 | 2018 to 2021 | 144 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 403 |  | YOC354F/000A/021A
Victoria Road Surface Water Flood Alleviation, Guisley | Leeds City Council | Yorkshire | Victoria Road, Guisley, Leeds. | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 2018 to 2021 | 34 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 537 |  | YOC354F/000A/019A
Wortley Beck Improvements, Leeds | Leeds City Council | Yorkshire | Wortley, Leeds. | 0 | 50 | 0 | 50 | 0 | 0 | 1050 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 2192.765 |  | YOC354F/000A/007A
Wyke Beck Improvements, Leeds | Leeds City Council | Yorkshire | East Leeds. Wyke Beck | 0 | 50 | 0 | 50 | 0 | 0 | 1050 | 2018 to 2021 | 900 | 0 | 0 | 0 | 220 | 0 | 220 | 0 | 3383.543 |  | YOC354F/000A/006A
Hagthorpe Pumping Station improvements | Ouse & Derwent Internal Drainage Board | Yorkshire | Loftsome Bridge, River Derwent | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2018 to 2021 | 20 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 376 |  | YOC351I/000A/001A
Herringthorpe Valley Flood Alleviation | Rotherham MBC | Yorkshire | Herringthorpe Valley Flood, Rotherham, South Yorkshire | 0 | 30 | 0 | 0 | 0 | 0 | 300 | 2016 to 2018 | 270 | 0 | 0 | 0 | 110 | 0 | 110 | 0 | 531.563 |  | YOC356F/000A/049A
Whiston Brook Flood Storage | Rotherham MBC | Yorkshire | Whiston Brook, Whiston, Rotherham, South Yorkshire | 0 | 30 | 0 | 0 | 0 | 0 | 300 | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 1255.8575 |  | YOC356F/000A/062A
Runswick Bay Works | Scarborough Borough Council | Yorkshire | Runswick Bay Village, North Yorkshire TS13 | 0 | 200 | 0 | 0 | 0 | 0 | 1500 | 2021 on | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 16200 |  | YOS351C/001A/012A
Scalby Ness Works | Scarborough Borough Council | Yorkshire | Scalby Mills, North Yorkshire, YO12 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2021 on | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1254 |  | YOS351C/001A/020A
Whitby Coastal Strategy 2 Flood Cell 1 Rowing Club to Museum | Scarborough Borough Council | Yorkshire | Scarborough North Yorkshire, YO11 | 0 | 0 | 0 | 0 | 0 | 0 | 202 | 2018 to 2021 | 97 | 105 | 0 | 0 | 10 | 0 | 10 | 0 | 987 |  | YOS351C/000A/102A
Whitby Coastal Strategy 2 Management Unit 19 Haggerlythe | Scarborough Borough Council | Yorkshire | Whitby, North Yorkshire, YO21 | 0 | 232 | 0 | 0 | 0 | 0 | 1232 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 1207 |  | YOS351C/000A/100A
Coates Marsh Pumping Station | Selby Area Internal Drainage Board | Yorkshire | North Snaith, River Aire | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 40 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 1960 |  | YOC354I/000A/001A
Temple Hirst Pumping Station | Selby Area Internal Drainage Board | Yorkshire | Temple Hirst, River Aire | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2016 to 2018 | 125 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 9875 |  | YOC354I/000A/006A
Wistow Clough Pumping Station | Selby Area Internal Drainage Board | Yorkshire | East of Wistow, River Ouse | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 2018 to 2021 | 140 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 9860 |  | YOC353I/000A/036A
b. Projects in development, expected to start construction in future years, subject to approval of a full business case and securing other funding contributions. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wash East Coastal Management Strategy - Works arising | Environment Agency | Anglian Central | Wash East | 0 | 210 | 0 | 75 | 520 | 0 | 5090 | 2016 to 2018 | 210 | 0 | 125 | 0 | 300 | 0 | 550 | 0 | 6414.655 |  | ACS451E/001A/004A
Kings Ditch Flood Risk Management | Bedfordshire and River Ivel Internal Drainage Board | Anglian Central | Kings Ditch, Bedford | 0 | 0 | 0 | 0 | 10 | 0 | 200 | 2016 to 2018 | 50 | 0 | 140 | 0 | 25 | 0 | 25 | 0 | 617 |  | ACC451I/000A/238A
Caldecotte Flood Risk Management | Buckingham and River Ouzel Internal Drainage Board | Anglian Central | Walnut Tree & Browne Wood Milton Keynes, Caldecotte | 0 | 94 | 0 | 0 | 6 | 0 | 734 | 2018 to 2021 | 0 | 608 | 26 | 0 | 270 | 0 | 270 | 0 | 7316 |  | ACC451I/000A/003A
Eaton Bray Flood Risk Management | Buckingham and River Ouzel Internal Drainage Board | Anglian Central | Eaton Bray & Eddlesborough, River Ouzel | 0 | 8.75 | 0 | 37.25 | 20 | 0 | 666 | 2018 to 2021 | 406.25 | 13.75 | 180 | 0 | 150 | 0 | 150 | 0 | 3881.239 |  | ACC451I/000A/002A
Brunswick Surface Water Flood Alleviation | Cambridge City Council | Anglian Central | Cambridge | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 2016 to 2018 | 20 | 0 | 30 | 0 | 5 | 0 | 5 | 0 | 58.024 |  | ACC451F/000A/017A
Kelvin Close Surface Water Flood Alleviation | Cambridge City Council | Anglian Central | Cambridge | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 2016 to 2018 | 60 | 0 | 30 | 0 | 10 | 0 | 10 | 0 | 194.311 |  | ACC451F/000A/018A
Riverside Surface Water Flood Alleviation | Cambridge City Council | Anglian Central | Cambridge | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 2016 to 2018 | 55 | 0 | 20 | 0 | 10 | 0 | 10 | 0 | 213 |  | ACC451F/000A/019A
Histon/Impington Surface Water Flood Alleviation | Cambridgeshire County Council | Anglian Central | Histon and Impington Ward | 0 | 0 | 0 | 0 | 0 | 0 | 251 | 2016 to 2018 | 105 | 50 | 25 | 0 | 95 | 0 | 95 | 0 | 149.335 |  | ACC451F/000A/016A
Kings Hedges & Arbury Estate, Surface Water Flood Alleviation | Cambridgeshire County Council | Anglian Central | Kings Hedges Estate, Cambridge | 0 | 0 | 0 | 0 | 0 | 0 | 566 | 2016 to 2018 | 275 | 0 | 95 | 0 | 165 | 0 | 165 | 0 | 3548.5 |  | ACC451F/000A/003A
March Surface Water Flood Alleviation | Cambridgeshire County Council | Anglian Central | March | 0 | 100 | 0 | 0 | 0 | 0 | 1146.5 | 2016 to 2018 | 770 | 0 | 230 | 0 | 210 | 0 | 210 | 0 | 7800.3 |  | ACC451F/000S/008A
Stow Fen 1950's pumping station replacement | Downham & Stow Bardolph Internal Drainage Board | Anglian Central | Downham Market | 0 | 80 | 0 | 0 | 60 | 0 | 1500 | 2016 to 2018 | 825 | 0 | 520 | 0 | 150 | 0 | 150 | 0 | 13378.143 |  | ACC451I/000A/237A
Gaywood River, Millfleet Tilting Gate - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Central | Kings Lynn | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2016 to 2018 | 28 | 0 | 2 | 0 | 200 | 0 | 200 | 0 | 692.5 |  | ACC451I/004A/141A
Green Bank Pumping Station - Pump Refurbishment | Kings Lynn Internal Drainage Board | Anglian Central | Broad Fen | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 77 | 0 | 3 | 0 | 280 | 0 | 280 | 0 | 1265 |  | ACC451I/004A/146A
Islington Catchment Flood Risk Management | Kings Lynn Internal Drainage Board | Anglian Central | Tilney Cum Islington | 0 | 0 | 0 | 0 | 390 | 0 | 12313 | 2016 to 2018 | 1092.7 | 3103.3 | 7487 | 0 | 760 | 0 | 760 | 0 | 149005.99 |  | ACC451I/004A/169A
Knowles Sluice - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Central | Eau Brink | 0 | 0 | 0 | 0 | 10 | 0 | 70 | 2018 to 2021 | 10 | 0 | 50 | 0 | 55 | 0 | 55 | 0 | 42.8 |  | ACC451I/004A/007A
Merries Farm Sluice - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Central | West Lynn | 0 | 0 | 0 | 0 | 10 | 0 | 70 | 2018 to 2021 | 5 | 0 | 55 | 0 | 25 | 0 | 25 | 0 | 0 |  | ACC451I/004A/142A
North Lynn Pumping Station - Pump Refurbishment | Kings Lynn Internal Drainage Board | Anglian Central | North Lynn | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2018 to 2021 | 50 | 0 | 20 | 0 | 300 | 0 | 300 | 0 | 481.7 |  | ACC451I/004A/144A
Wolferton Pumping station - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Central | Wolferton | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 2018 to 2021 | 356 | 50 | 150 | 0 | 265 | 0 | 265 | 0 | 10240.939 |  | ACC451I/004A/147A
Great Fen - Upstream storage | Middle Level Commissioners | Anglian Central | Great Fen project area | 0 | 235 | 50 | 0 | 0 | 0 | 3265 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 4680.17 |  | ACC451I/004A/167A
Middle Level Bank Raising | Middle Level Commissioners | Anglian Central | Thoughout the MLC District | 0 | 230 | 0 | 0 | 125 | 0 | 2005 | 2016 to 2018 | 690 | 0 | 300 | 0 | 0 | 0 | 2000 | 0 | 42500 |  | ACC451I/004A/018A
Stocking Fen Pumping Station Health & Safety Works | Ramsey Internal Drainage Board | Anglian Central | Ramsey, Huntingdon | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2016 to 2018 | 4.75 | 37.25 | 38 | 0 | 25 | 0 | 25 | 0 | 113.193 |  | ACC451I/000A/239A
Newmarket Flood Alleviation | Suffolk County Council | Anglian Central | Newmarket | 0 | 35 | 0 | 0 | 0 | 0 | 420 | 2016 to 2018 | 250 | 0 | 100 | 0 | 215 | 0 | 215 | 0 | 3107.6 |  | ACC451F/000A/021A
Coggeshall and Kelvedon Community Flood Alleviation | Environment Agency | Anglian Eastern | Coggeshall | 50 | 0 | 0 | 0 | 0 | 0 | 350 | 2016 to 2018 | 100 | 0 | 200 | 0 | 55 | 0 | 55 | 0 | 189.06 |  | AEO000E/000A/406A
Great Yarmouth Tidal Defences - Compartment C - Stage 2 | Environment Agency | Anglian Eastern | Great Yarmouth | 0 | 1092.5 | 0 | 0 | 0 | 1092.5 | 36521.5 | 2016 to 2018 | 16041 | 0 | 0 | 2082.5 | 0 | 0 | 820 | 0 | 788969 |  | AES502E/002A/002C
Heybridge Community Flood Risk Alleviation | Environment Agency | Anglian Eastern | Heybridge, Essex | 50 | 700 | 0 | 0 | 300 | 0 | 8000 | 2016 to 2018 | 750 | 0 | 6200 | 0 | 620 | 0 | 620 | 0 | 18262.6694 |  | AEO000E/000A/407A
Horning Flood risk management | Environment Agency | Anglian Eastern | Horning | 0 | 10 | 0 | 0 | 0 | 0 | 285 | 2018 to 2021 | 225 | 0 | 50 | 0 | 100 | 0 | 100 | 0 | 730.448 |  | AEC503E/000A/011A
Flood Alleviation Norwich, Oak Lane | Anglian Water | Anglian Eastern | King's Lynn | 0 | 0 | 0 | 0 | 0 | 0 | 1116.797 | 2018 to 2021 | 416.797 | 0 | 700 | 0 | 30 | 0 | 30 | 0 | 0 |  | AEO000E/000A/594A
Ashtree Pumping Station Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Great Yarmouth | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 40 | 0 | 40 | 0 | 5 | 0 | 5 | 0 | 1854.804 |  | AEC503I/003A/110A
Berney Arms Pumping Station Refurbishment | Broads (2006) Internal Drainage Board | Anglian Eastern | Reedham CP | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2018 to 2021 | 14 | 0 | 56 | 0 | 2 | 0 | 2 | 0 | 99.182 |  | AEC503I/003A/006A
Broads Pumping Station Telemetry Improvements | Broads (2006) Internal Drainage Board | Anglian Eastern | Various | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 20 | 0 | 10 | 0 | 0 | 0 | 25 | 0 | 665.951 |  | AEC503I/003A/013A
Cantley Pumping Station Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Cantley CP | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 40 | 0 | 50 | 0 | 10 | 0 | 10 | 0 | 410.448 |  | AEC503I/003A/114A
Chapelfield Drainage Improvements | Broads (2006) Internal Drainage Board | Anglian Eastern | Chapelfield, Stalham, Norfolk. River Ant | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2018 to 2021 | 7 | 0 | 33 | 0 | 1 | 0 | 1 | 0 | 42.592 |  | AEC503I/003A/154A
Hickling Drainage Improvements | Broads (2006) Internal Drainage Board | Anglian Eastern | Hickling, Norfolk. | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2018 to 2021 | 4.5 | 0 | 35.5 | 0 | 0 | 0 | 0 | 0 | 27.702 |  | AEC503I/003A/155A
Horse Fen Pumping Station Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Ludham CP | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 50 | 0 | 50 | 0 | 15 | 0 | 15 | 0 | 797.595 |  | AEC503I/003A/125A
Horsey Pumping Station Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Horsey CP | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 40 | 0 | 40 | 0 | 20 | 0 | 20 | 0 | 377.557 |  | AEC503I/003A/126A
Management of Acle Landspring and Pumping Station | Broads (2006) Internal Drainage Board | Anglian Eastern | Acle CP | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 20 | 0 | 20 | 0 | 10 | 0 | 10 | 0 | 869.903 |  | AEC503I/003A/022A
Martham Boat Dyke Culvert Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Martham CP | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 1.1 | 0 | 88.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | AEC503I/003A/004A
Postwick Pumping Station Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Postwick with Witton CP | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 35.1 | 0 | 44.9 | 0 | 5 | 0 | 5 | 0 | 291.928 |  | AEC503I/003A/130A
Somerton North Pumping Station Automatic Weedscreen | Broads (2006) Internal Drainage Board | Anglian Eastern | Somerton CP | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 4 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 1.136 |  | AEC503I/003A/136A
Somerton South Pumping Station Automatic Weedscreen | Broads (2006) Internal Drainage Board | Anglian Eastern | Somerton CP | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 6 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 31.895 |  | AEC503I/003A/138A
Thurne Boat Dyke Culvert Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Thurne CP | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 30 | 0 | 60 | 0 | 5 | 0 | 5 | 0 | 275.146 |  | AEC503I/003A/069A
Tonnage Pumping Station Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Dilham CP | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 5 | 0 | 75 | 0 | 1 | 0 | 1 | 0 | 0 |  | AEC503I/003A/147A
Upton Boat Dyke Culvert Replacement | Broads (2006) Internal Drainage Board | Anglian Eastern | Upton with Fishley CP | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 9 | 0 | 81 | 0 | 2 | 0 | 2 | 0 | 32.38 |  | AEC503I/003A/072A
Bawdsey Pumping Station Refurbishment | East Suffolk Internal Drainage Board | Anglian Eastern | Bawdsey, Alderton & Ramsholt Marshes | 0 | 6 | 0 | 0 | 0 | 0 | 146 | 2021 on | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 231.3485 |  | AEC504I/001A/001A
Iken Pumping Station Refurbishment | East Suffolk Internal Drainage Board | Anglian Eastern | Iken Village and Marshes | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 2016 to 2018 | 70 | 0 | 70 | 0 | 15 | 0 | 15 | 0 | 504.3469 |  | AEC504I/001A/009A
Scratby Coast Protection | Great Yarmouth Borough Council | Anglian Eastern | Coastline of Scratby Great Yarmouth Norfolk | 0 | 0 | 0 | 0 | 0 | 0 | 617 | 2018 to 2021 | 527 | 0 | 90 | 0 | 0 | 35 | 0 | 35 | 59 |  | AES502C/002A/003A
Norwich: Catton Grove and Sewell Sustainable Urban drainage | Norfolk CC | Anglian Eastern | Norwich, Catton Grove and Sewell | 0 | 11 | 0 | 0 | 0 | 0 | 500 | 2016 to 2018 | 204 | 0 | 285 | 0 | 30 | 0 | 30 | 0 | 12831 |  | AEC501F/000A/002A
Norwich: Nelson and Town Close Sustainable Urban drainage | Norfolk CC | Anglian Eastern | Norwich, Nelson and Town Close | 0 | 20 | 0 | 0 | 0 | 0 | 500 | 2016 to 2018 | 290 | 0 | 190 | 0 | 665 | 0 | 665 | 0 | 10050.33 |  | AEC501F/000A/001A
Bacton Gas Terminal to Ostend Coastal Management | North Norfolk District Council | Anglian Eastern | Bacton, Walcott and Ostend, Norfolk | 0 | 0 | 0 | 0 | 0 | 0 | 10130 | 2018 to 2021 | 50 | 0 | 0 | 10000 | 0 | 145 | 0 | 145 | 191913 |  | AES502E/000A/004A
Mundesley Coast Protection | North Norfolk District Council | Anglian Eastern | Mundesley | 0 | 0 | 0 | 0 | 70 | 0 | 1937 | 2016 to 2018 | 1622 | 0 | 245 | 0 | 0 | 280 | 0 | 280 | 8248.44 |  | AES502C/000A/012A
Leiston Flood Alleviation | Suffolk County Council | Anglian Eastern | Leiston | 20 | 0 | 0 | 0 | 0 | 0 | 125 | 2016 to 2018 | 50 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 979.002 |  | AEC504F/000A/004A
Lowestoft Flood Risk Management | Waveney DC | Anglian Eastern | Lowestoft Lake Lothing and Kirkley Stream | 35 | 660 | 0 | 0 | 1555 | 0 | 30290 | 2016 to 2018 | 6810 | 2590 | 17600 | 0 | 0 | 0 | 840 | 0 | 75580 |  | AES503E/008A/006A
Haddiscoe Pump Replacement | Waveney, Lower Yare & Lothingland Internal Drainage Board | Anglian Eastern | Thorpe and Haddiscoe Marshes | 0 | 0 | 0 | 0 | 8 | 0 | 108 | 2018 to 2021 | 72 | 0 | 28 | 0 | 0 | 0 | 35 | 0 | 401.9336 |  | AEC503I/003A/096A
Langley Double Pump Replacement and Automatic Weedscreen Installation | Waveney, Lower Yare & Lothingland Internal Drainage Board | Anglian Eastern | Langley and Hardley Marshes | 0 | 0 | 0 | 0 | 10 | 0 | 202 | 2018 to 2021 | 50 | 0 | 50 | 0 | 0 | 0 | 25 | 0 | 670.7055 |  | AEC503I/003A/099A
Langley Monks Pump Automatic Weedscreen | Waveney, Lower Yare & Lothingland Internal Drainage Board | Anglian Eastern | Langley Monks and Carleton Broad Marshes | 0 | 0 | 0 | 0 | 8 | 0 | 98 | 2018 to 2021 | 12 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 129.1917 |  | AEC503I/003A/101A
Limpenhoe Pump Automatic Weedscreen | Waveney, Lower Yare & Lothingland Internal Drainage Board | Anglian Eastern | Limpenhoe Marshes | 0 | 0 | 0 | 0 | 8 | 0 | 98 | 2018 to 2021 | 42 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 668.0378 |  | AEO000E/000A/395A
Ancholme Valley Improvements and Wetland Creation | Environment Agency | Anglian Northern | Brigg | 0 | 0 | 0 | 0 | 600 | 0 | 6500 | 2016 to 2018 | 3300 | 0 | 600 | 0 | 0 | 0 | 540 | 0 | 74599.787 |  | ANC401E/000A/004A
Barrow Flood Alleviation & Wetland Creation | Environment Agency | Anglian Northern | Barrow Beck | 0 | 25 | 0 | 0 | 0 | 0 | 275 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 58.9465 |  | ANO000E/000A/438A
Boston Barrage/Barrier | Environment Agency | Anglian Northern | River Witham, Boston, Lincs | 3952 | 3345 | 0 | 0 | 0 | 0 | 89619.389 | 2016 to 2018 | 65902 | 0 | 11000 | 0 | 15130 | 0 | 15130 | 0 | 1106542 | Time Constrained Contribution | ANC403E/004A/002A
East & West Fen Catchwater Slowing the Flow Attenuation | Environment Agency | Anglian Northern | East & West Fen Catchwater Catchment | 0 | 0 | 0 | 0 | 30 | 0 | 530 | 2018 to 2021 | 250 | 0 | 250 | 0 | 200 | 0 | 200 | 0 | 1932.3193 |  | ANC404E/000A/058A
Humber - Barton Haven to New Holland tidal defence improvements | Environment Agency | Anglian Northern | Barrow upon Humber, North Lincolnshire | 20 | 1080 | 0 | 0 | 0 | 0 | 6200 | 2021 on | 3000 | 0 | 2000 | 0 | 430 | 0 | 430 | 0 | 58035 |  | ANS399E/000A/003A
Humber - Winteringham Ings & South Ferriby | Environment Agency | Anglian Northern | Winteringham to South Ferriby | 100 | 0 | 0 | 0 | 0 | 0 | 5895.5 | 2016 to 2018 | 2210 | 0 | 3000 | 0 | 145 | 0 | 145 | 0 | 39492 |  | ANS399E/001A/008A
Leasingham - Surface Water Flood Risk Improvement | Environment Agency | Anglian Northern | Leasingham | 20 | 0 | 0 | 0 | 5 | 0 | 135 | TBC | 20 | 0 | 65 | 0 | 10 | 0 | 10 | 0 | 32.743 |  | ANC403E/000A/075A
Managing water above Nettleham | Environment Agency | Anglian Northern | Nettleham | 0 | 0 | 0 | 0 | 50 | 0 | 500 | 2018 to 2021 | 80 | 0 | 370 | 0 | 20 | 0 | 20 | 0 | 0 |  | ANO000E/000A/429A
Nether Heyford Flood Alleviation | Environment Agency | Anglian Northern | Nether Heyford | 61.464 | 0 | 0 | 0 | 105 | 0 | 1327.544 | 2016 to 2018 | 933.291 | 21.789 | 120 | 0 | 50 | 0 | 50 | 0 | 12903.9333 |  | ANC405E/000A/045A
Saltfleet to Gibraltar Point Strategy Works Arising | Environment Agency | Anglian Northern | Mablethorpe to Skegness | 0 | 6170 | 12640 | 0 | 1000 | 0 | 118050 | 2018 to 2021 | 0 | 0 | 0 | 0 | 2185 | 0 | 32790 | 0 | 1098117.2278 |  | ANS401E/001C/001A
Swaton Resilience | Environment Agency | Anglian Northern | Swaton Village | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2016 to 2018 | 22 | 58 | 30 | 0 | 5 | 0 | 5 | 0 | 504.5269 |  | ANC403I/005A/015A
Wootton Brook Flood Risk Management | Environment Agency | Anglian Northern | Wootton Brook | 0 | 0 | 0 | 0 | 0 | 50 | 1060 | 2018 to 2021 | 217.193 | 0 | 782.807 | 0 | 25 | 0 | 25 | 0 | 477.252 |  | ANC405E/000A/105A
Maltings Lane Donington Pipe replacement | Black Sluice Internal Drainage Board | Anglian Northern | Boston | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 2018 to 2021 | 75 | 0 | 2 | 0 | 30 | 0 | 30 | 0 | 1029.438 |  | ANC403I/005A/031A
Hundred of Wisbech Channel Conveyance Improvements | Hundred of Wisbech Internal Drainage Board | Anglian Northern | Wisbech, Cambs | 0 | 0 | 0 | 0 | 10 | 0 | 250 | 2016 to 2018 | 150 | 0 | 90 | 0 | 150 | 0 | 150 | 0 | 5561 |  | ANC405I/001A/046A
Chalk Lane Sluice - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Northern | Fens | 0 | 12.75 | 0 | 0 | 2.25 | 0 | 140 | 2018 to 2021 | 106.25 | 0 | 18.75 | 0 | 225 | 0 | 225 | 0 | 6068.8 |  | ACC451I/004A/139A
Lighthouse Sluice - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Northern | PE12 9 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2018 to 2021 | 120 | 0 | 5 | 0 | 30 | 0 | 30 | 0 | 8986.47 |  | ACC451I/004A/143A
Main Sluice - Refurbishment | Kings Lynn Internal Drainage Board | Anglian Northern | PE12 9 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2018 to 2021 | 100 | 0 | 25 | 0 | 275 | 0 | 275 | 0 | 13420.015 |  | ACC451I/004A/140A
Market Harborough Town Centre | Leicestershire CC | Anglian Northern | Market Harborough Town Centre | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 2018 to 2021 | 175 | 0 | 70 | 0 | 30 | 0 | 30 | 0 | 1215 |  | ANC405F/000A/015A
Keelby - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Keelby | 0 | 0 | 0 | 0 | 0 | 0 | 88.25 | TBC | 12.5 | 0 | 63.75 | 0 | 10 | 0 | 10 | 0 | 202.476 |  | ANC403F/000A/020A
Kirkby on Bain - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Kirkby on Bain | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 2016 to 2018 | 45 | 0 | 65 | 0 | 15 | 0 | 15 | 0 | 327.7705 |  | ANC403I/003A/003A
Lincoln - Bunkers Hill - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Lincoln | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 2016 to 2018 | 6.8 | 32.2 | 38 | 0 | 5 | 0 | 5 | 0 | 2.9481 |  | ANC403F/000A/019A
Local Communities at Risk - Surface Water Flood Risk Improvements | Lincolnshire County Council | Anglian Northern | Lincolnshire | 0 | 80 | 0 | 0 | 160 | 0 | 1500 | TBC | 60 | 0 | 120 | 0 | 0 | 0 | 395 | 0 | 11111.0874 |  | ANO000E/000A/476A
Middle Rasen - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Middle Rasen | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2018 to 2021 | 45 | 10 | 115 | 0 | 10 | 0 | 10 | 0 | 157.4833 |  | ANC403F/000A/025A
Ruskington - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Ruskington | 25 | 0 | 0 | 0 | 0 | 0 | 177.5 | 2016 to 2018 | 35 | 0 | 97.5 | 0 | 10 | 0 | 10 | 0 | 249.226 |  | ANC403F/000A/022A
Scopwick - Surface Water Flood Risk Improvements | Lincolnshire County Council | Anglian Northern | Scopwick | 0 | 5 | 5 | 0 | 5 | 0 | 150 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 318.3895 |  | ANC403F/000A/027A
Timberland - Surface Water Flood Risk Improvement | Lincolnshire County Council | Anglian Northern | Timberland | 0 | 5 | 0 | 0 | 5 | 0 | 100 | 2018 to 2021 | 41 | 0 | 49 | 0 | 15 | 0 | 15 | 0 | 401.4911 |  | ANC403F/000A/024A
Boygrift Pumping Station Refurbishment | Lindsey Marsh Drainage Board | Anglian Northern | Sandilands | 0 | 0 | 0 | 0 | 0 | 0 | 397 | 2018 to 2021 | 297 | 0 | 100 | 0 | 345 | 0 | 345 | 0 | 4206 |  | ANC402I/000A/028A
Howdales Pumping Station Refurbishment | Lindsey Marsh Drainage Board | Anglian Northern | Saltfleet | 0 | 0 | 0 | 0 | 0 | 0 | 146 | 2018 to 2021 | 96 | 0 | 50 | 0 | 5 | 0 | 5 | 0 | 3680 |  | ANC402I/000A/027A
Saltfleet Pumping Station Replacement | Lindsey Marsh Drainage Board | Anglian Northern | Saltfleet | 0 | 0 | 0 | 0 | 0 | 0 | 2115 | 2018 to 2021 | 1015 | 0 | 1100 | 0 | 175 | 0 | 175 | 0 | 9600 |  | ANC402I/000A/001A
Theddlethorpe Pumping Station Refurbishment | Lindsey Marsh Drainage Board | Anglian Northern | Theddlethorp | 0 | 0 | 0 | 0 | 0 | 0 | 537 | 2018 to 2021 | 385 | 0 | 152 | 0 | 175 | 0 | 175 | 0 | 8223 |  | ANC402I/000A/029A
NE Lincolnshire Surface Water - Coniston Crescent Flood Alleviation | North East Lincs Council | Anglian Northern | Humberston | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2016 to 2018 | 95 | 0 | 155 | 0 | 65 | 0 | 65 | 0 | 1700 |  | ANC401F/000A/015A
North East Lincolnshire Surface Water - Peaksfield Avenue | North East Lincs Council | Anglian Northern | Grimsby | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 2018 to 2021 | 115 | 0 | 160 | 0 | 150 | 0 | 150 | 0 | 4190.4 |  | ANC401F/000A/019A
North East Lincolnshire Surface Water - North Immingham | North East Lincs Council | Anglian Northern | Immingham, Grimsby, Humberston | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 2018 to 2021 | 290 | 0 | 60 | 0 | 380 | 0 | 380 | 0 | 11110 |  | ANC401F/000A/020A
North East Lincolnshire Surface Water - Willingham Street | North East Lincs Council | Anglian Northern | Grimsby | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2016 to 2018 | 190 | 0 | 60 | 0 | 155 | 0 | 155 | 0 | 4400 |  | ANC401F/000A/021A
North Promenade Terminal Groyne replacement, Cleethorpes | North East Lincs Council | Anglian Northern | Cleethorpes, Humber Estuary SSSI | 150 | 0 | 0 | 0 | 0 | 0 | 750 | 2016 to 2018 | 314 | 0 | 271 | 0 | 270 | 0 | 270 | 0 | 7290 |  | ANS401C/001A/002A
Hundreds Pumping Station Refurbishment | North Level District Internal Drainage Board | Anglian Northern | B1040, Nene Terrace, Peterborough | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 18 | 0 | 22 | 0 | 15 | 0 | 15 | 0 | 5963.138 |  | ANC405I/001A/060A
Goxhill, Thornton Road Flood Alleviation | North Lincolnshire Council | Anglian Northern | Goxhill, Thornton Road, North Lincs | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2018 to 2021 | 10.35 | 0 | 24 | 0 | 20 | 0 | 20 | 0 | 16.67 |  | ANC401F/000A/014A
Redbourne Beck Lane/School Lane, Scunthorpe | North Lincolnshire Council | Anglian Northern | Beck Lane/School Lane, Redbourne, North Lincs | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 2016 to 2018 | 41.5 | 0 | 38.5 | 0 | 10 | 0 | 10 | 0 | 132.233 |  | ANC401F/000A/018A
Ulceby Flood Alleviation | North Lincolnshire Council | Anglian Northern | Spruce Lane, Coronation Road, Ulceby, North Lincs | 0 | 0 | 0 | 0 | 10 | 0 | 403 | 2016 to 2018 | 28 | 0 | 365 | 0 | 15 | 0 | 15 | 0 | 0 |  | ANC401F/000A/017A
Donningtons Pumping Station Refurbishment | South Holland Internal Drainage Board | Anglian Northern | PUMPING STATION ON SOUTH SIDE OF SOUTH HOLLAND MAIN DRAIN AT DONNINGTONS BRIDGE NEAR WHAPLODE DROVE | 225 | 0 | 0 | 0 | 0 | 0 | 475 | 2016 to 2018 | 150 | 0 | 75 | 0 | 65 | 0 | 65 | 0 | 18056.259 |  | ANC405I/001A/049A
Fleet Haven Pumping Station Refurbishment | South Holland Internal Drainage Board | Anglian Northern | PUMPING STATION IS WITHIN THE RAF HOLBEACH SITE OFF DURHAMS ROAD, GEDNEY MARSH, SPALDING | 0 | 0 | 0 | 0 | 40 | 0 | 700 | 2018 to 2021 | 220 | 0 | 440 | 0 | 5 | 0 | 5 | 0 | 5635.251 |  | ANC405I/001A/033A
Westmere Pumping Station and Sluice Refurbishment | South Holland Internal Drainage Board | Anglian Northern | THE PUMPING STATION AND TIDAL SLUICE ARE ON THE TIDAL BANK OF THE RIVER NENE OFF PETTS LANE, SUTTON BRIDGE, SPALDING | 0 | 0 | 0 | 0 | 35 | 0 | 525 | 2018 to 2021 | 120 | 0 | 370 | 0 | 5 | 0 | 5 | 0 | 1323.482 |  | ANC405I/001A/043A
Broxholme Pumping Station | Upper Witham Internal Drainage Board | Anglian Northern | River Till | 0 | 11 | 0 | 0 | 3.3 | 0 | 119.6 | 2018 to 2021 | 81 | 0 | 24.3 | 0 | 15 | 0 | 15 | 0 | 2271.8765 |  | ANC403I/002A/035A
Westborough Flood Alleviation | Upper Witham Internal Drainage Board | Anglian Northern | Westborough, Lincolnshire | 0 | 10 | 0 | 0 | 2 | 0 | 110 | 2018 to 2021 | 37 | 0 | 61 | 0 | 10 | 0 | 10 | 0 | 380.1967 |  | ANC403I/002A/039A
Five Towns Sluice Refurbishment | Welland & Deepings Internal Drainage Board | Anglian Northern | Fosdyke Bridge | 0 | 47 | 0 | 0 | 0 | 0 | 422 | 2018 to 2021 | 365 | 0 | 0 | 0 | 190 | 0 | 190 | 0 | 44816.319 |  | ANC404I/000A/004A
Risegate Eau Sluice Refurbishment | Welland & Deepings Internal Drainage Board | Anglian Northern | Fosdyke Bridge | 0 | 0 | 0 | 0 | 37 | 0 | 422 | 2018 to 2021 | 200 | 0 | 25 | 0 | 0 | 0 | 130 | 0 | 32244.92 |  | ANC404I/000A/003A
Branston Fen Engine Drain Culvert Replacement | Witham 1st Internal Drainage Board | Anglian Northern | Bardney | 43 | 0 | 0 | 0 | 0 | 0 | 65 | 2018 to 2021 | 0 | 0 | 22 | 0 | 10 | 0 | 10 | 0 | 288.6012 |  | ANC403I/003A/001A
Branston Fen Pumping Station Refurbishment | Witham 1st Internal Drainage Board | Anglian Northern | Bardney | 34 | 0 | 0 | 0 | 0 | 0 | 79 | 2016 to 2018 | 17 | 0 | 28 | 0 | 10 | 0 | 10 | 0 | 3552.8466 |  | ANC403I/003A/002A
Badsey Brook (Broadway, Childswickham and Murcot) Flood Alleviation | Environment Agency | English Severn and Wye | Badsey | 0 | 0 | 0 | 0 | 0 | 0 | 2795.5 | 2016 to 2018 | 1505.5 | 222.5 | 312 | 0 | 250 | 0 | 250 | 0 | 3725 |  | SNC001E/000A/650A
Gloucester to Tewkesbury River Severn Property Level Protection | Environment Agency | English Severn and Wye | Gloucester to Tewkesbury, River Severn | 0 | 0 | 0 | 191 | 42 | 0 | 1440 | 2018 to 2021 | 111 | 0 | 54 | 0 | 20 | 0 | 180 | 0 | 3960 |  | SNC001E/000A147A
Stratford-Upon-Avon, Racecourse Brook, Flood Alleviation | Environment Agency | English Severn and Wye | North West Stratford-Upon-Avon | 0 | 0 | 0 | 0 | 0 | 0 | 668 | 2018 to 2021 | 78 | 40 | 0 | 0 | 0 | 0 | 50 | 0 | 106 |  | SNC001E/000A133A
Pilley Cheltenham Flood Alleviation | Cheltenham District (B) | English Severn and Wye | Cheltenham | 0 | 50 | 0 | 0 | 25 | 0 | 380 | 2018 to 2021 | 280 | 0 | 25 | 0 | 40 | 0 | 40 | 0 | 6384 |  | SNC001F/000A/003A
Southfield, Cheltenham, Flood Alleviation | Cheltenham District (B) | English Severn and Wye | Cheltenham | 0 | 0 | 0 | 0 | 0 | 0 | 435 | 2016 to 2018 | 200 | 0 | 150 | 0 | 25 | 0 | 25 | 0 | 6407 |  | SNC001F/000A/004A
Upper Hearne Brook Flood Alleviation (Beeches Road) | Cheltenham District (B) | English Severn and Wye | Cheltenham - Hearne Brook | 0 | 0 | 0 | 0 | 25 | 0 | 180 | 2021 on | 25 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 3902 |  | SNC001F/000A/069A
Deans Walk, Property Level Protection, Gloucester | Gloucester City Council | English Severn and Wye | Deans Walk, Gloucester - River Twyver | 0 | 0 | 0 | 0 | 10 | 0 | 230 | 2018 to 2021 | 220 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 452.276 |  | SNC001F/000A/090A
Tewkesbury Road, Longford Property Level Protection | Gloucester City Council | English Severn and Wye | Tewkesbury Road, Gloucester - properties affected when River Severn is high which impacts on both the Wotton and Horsbere brooks | 0 | 0 | 0 | 0 | 1 | 0 | 30 | 2018 to 2021 | 20 | 0 | 9 | 0 | 5 | 0 | 5 | 0 | 150 |  | SNC001F/000A/088A
Brockworth, Gloucestershire Surface Water | Gloucester District (B) | English Severn and Wye | Brockworth, Gloucester | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 2016 to 2018 | 142 | 15 | 0 | 0 | 40 | 0 | 40 | 0 | 2753 |  | SNC001F/000A/022A
Bishops Cleeve, Gloucestershire Flood Alleviation | Gloucestershire County Council | English Severn and Wye | Bishops Cleeve | 0 | 0 | 0 | 0 | 0 | 0 | 894.034 | 2016 to 2018 | 728.034 | 16 | 55 | 0 | 90 | 0 | 90 | 0 | 5035 |  | SNC001F/000A/023A
Churchdown Surface Water | Gloucestershire County Council | English Severn and Wye | Churchdown | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 2016 to 2018 | 71 | 13 | 0 | 0 | 30 | 0 | 30 | 0 | 1896 |  | SNC001F/000A/021A
Whaddon, Cheltenham Flood Alleviation | Gloucestershire County Council | English Severn and Wye | Cheltenham | 0 | 0 | 0 | 0 | 43 | 0 | 1591 | 2016 to 2018 | 1298 | 50 | 200 | 0 | 160 | 0 | 160 | 0 | 27565 |  | SNC001F/001A/405A
Cherry Brook, Hope Under Dinmore, Flood Alleviation | Herefordshire Council | English Severn and Wye | Hope Under Dinmore | 0 | 0 | 0 | 15 | 0 | 0 | 151 | 2018 to 2021 | 69 | 0 | 52 | 0 | 25 | 0 | 25 | 0 | 645 |  | SNC001F/001A/012A
Aston, Near Wem, Surface Water Property Level Protection | Shropshire Council | English Severn and Wye | Wem, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2018 to 2021 | 2.9 | 1.6 | 1.5 | 0 | 1 | 0 | 1 | 0 | 24 |  | SNC001F/000A/075A
Bitterley Property Level Protection | Shropshire Council | English Severn and Wye | Bitterley, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 2018 to 2021 | 2.985 | 2.015 | 1.3 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/074A
Bridge Street, River Clun, Property Level Protection | Shropshire Council | English Severn and Wye | Clun, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 2.5 | 0.5 | 3.5 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/083A
Clun Bridge, River Clun, Property Level Protection | Shropshire Council | English Severn and Wye | Clun, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 2.9 | 0.6 | 3 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/081A
Coton Hill, property Level Protection, River Severn, Shrewsbury | Shropshire Council | English Severn and Wye | Shrewsbury, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 2.8 | 1.5 | 2.2 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/080A
Culmington Property Level Protection Phase 2 | Shropshire Council | English Severn and Wye | Culmington, Shropshire | 0 | 0 | 0 | 0 | 1.015 | 0 | 7 | 2018 to 2021 | 2.985 | 0 | 3 | 0 | 1 | 0 | 1 | 0 | 23 |  | SNC001F/000A/086A
Culmington Property Level Protection Phase 3 | Shropshire Council | English Severn and Wye | Culmington, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 2.985 | 1.515 | 2 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/079A
Dulas, Near Knighton Property Level Protection | Shropshire Council | English Severn and Wye | Knighton, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 2.5 | 0 | 4 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/085A
East Church Stretton Surface and Ordinary Watercourse Flood Relief | Shropshire Council | English Severn and Wye | Church Stretton | 0 | 0 | 0 | 35 | 0 | 0 | 500 | 2021 on | 50 | 20 | 0 | 0 | 110 | 0 | 110 | 0 | 811 |  | SNC001F/000A/030A
Hunters Gate, Surface Water Flood Alleviation, Much Wenlock | Shropshire Council | English Severn and Wye | Much Wenlock, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 2016 to 2018 | 138 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 522 |  | SNC001F/000A/067A
Kinnerley Individual Property Protection | Shropshire Council | English Severn and Wye | Kinnerley, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2018 to 2021 | 2.9 | 1.6 | 2.5 | 0 | 1 | 0 | 1 | 0 | 23 |  | SNC001F/000A/076A
Pant Glas, Near Oswestry Property Level Protection | Shropshire Council | English Severn and Wye | Oswestry, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 4.6 | 0.6 | 1.3 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/082A
Shropshire Individual Property Protection Phase 2 | Shropshire Council | English Severn and Wye | Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 2016 to 2018 | 36 | 30 | 10 | 0 | 10 | 0 | 10 | 0 | 284 |  | SNC001F/000A/073A
Temeside, Phase 2, Ludlow, Property Level Protection | Shropshire Council | English Severn and Wye | Ludlow, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2018 to 2021 | 2.985 | 1.515 | 2 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | SNC001F/000A/077A
Westbury Brook, Westbury, Shropshire | Shropshire Council | English Severn and Wye | Westbury, Shropshire | 0 | 5 | 0 | 0 | 4 | 0 | 66 | 2016 to 2018 | 45 | 8 | 4 | 0 | 10 | 0 | 10 | 0 | 264 |  | SNC001F/000A/084A
Bilton Road, Rugby, Surface Water Flood Alleviation | Warwickshire CC | English Severn and Wye | Bilton Road, Rugby | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 2018 to 2021 | 95 | 0 | 220 | 0 | 30 | 0 | 30 | 0 | 174.162 |  | SNC001F/000A/063A
Ladbroke, Southam, Lot Brook, Flood Alleviation | Warwickshire CC | English Severn and Wye | Ladbroke | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 2018 to 2021 | 15 | 0 | 40 | 0 | 0 | 0 | 10 | 0 | 1 |  | SNC001F/000A/056A
Cummersdale, Carlisle | Environment Agency | North West | Carlisle, Cumbria | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 2018 to 2021 | 300 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 6706 |  | NWC004E/000A/029A
Grange-Over-Sands, Windermere Road | Environment Agency | North West | Grange-over-Sands | 0 | 0 | 0 | 0 | 0 | 0 | 880 | TBC | 190 | 0 | 690 | 0 | 40 | 0 | 40 | 0 | 819 |  | NWC006E/000A/011A
Rainford Brook, Beech Gardens Rainford | Environment Agency | North West | Rainford, St Helens | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2018 to 2021 | 9 | 61 | 20 | 0 | 5 | 0 | 5 | 0 | 29 |  | NWC008E/000A/010A
Birch Hall, Darwen | Blackburn with Darwen Borough Council | North West | Darwen, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 2018 to 2021 | 140 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 1325 |  | NWC009F/000A/047A
Old Gate Drive, Blackburn | Blackburn with Darwen Borough Council | North West | Blackburn, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 2018 to 2021 | 192 | 0 | 0 | 0 | 795 | 0 | 795 | 0 | 2.201 |  | NWC009F/000A/014A
Bolton Critical Culvert Rehabilitation | Bolton Council | North West | Bolton, Greater Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 2016 to 2018 | 1014 | 0 | 150 | 0 | 90 | 0 | 90 | 0 | 2125 |  | NWC005F/000A/024A
Bolton Culvert Improvements | Bolton Council | North West | Bolton, Greater Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 2016 to 2018 | 219 | 0 | 21 | 0 | 55 | 0 | 55 | 0 | 637 |  | NWC005F/000A/023A
Bolton Upland Storage | Bolton Council | North West | Various, Bolton, greater Manchester | 0 | 50 | 0 | 0 | 0 | 0 | 450 | 2018 to 2021 | 300 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 2650 |  | NWC003F/000A/009A
Horwich Town Centre Flood Alleviation | Bolton Council | North West | Horwich, Bolton, greater Manchester | 0 | 0 | 0 | 0 | 0 | 0 | 2452 | 2016 to 2018 | 2152 | 0 | 100 | 0 | 190 | 0 | 190 | 0 | 2589 |  | NWC003F/000A/005A
Ainsworth Rd/Water St, Radcliffe, Bury | Bury Council | North West | Ainsworth Rd / Water St, Radcliffe, Bury | 0 | 0 | 0 | 0 | 0 | 0 | 6893 | 2016 to 2018 | 100 | 0 | 6693 | 0 | 60 | 0 | 60 | 0 | 0 |  | NWC005F/000A/033A
A50 Pear Tree Cottages, Brereton | Cheshire East Council | North West | Brereton, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 2018 to 2021 | 15 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 132 |  | NWC012F/000A/026A
Mobberley Brook and tributaries, Wilmslow | Cheshire East Council | North West | Wilmslow, cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 2016 to 2018 | 20 | 0 | 181 | 0 | 15 | 0 | 15 | 0 | 275 |  | NWC012F/000A/041A
Clay Lane, Marton, Winsford | Cheshire West and Chester Borough Council | North West | Winsford, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2018 to 2021 | 2 | 0 | 28 | 0 | 1 | 0 | 1 | 0 | 0 |  | NWC012F/000A/035A
Hooton Green, Ellesmere Port | Cheshire West and Chester Borough Council | North West | Hooton Green, Ellesmere Port | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2018 to 2021 | 35 | 0 | 35 | 0 | 15 | 0 | 15 | 0 | 259.646 |  | NWC012F/000A/033A
Howey Lane, Frodsham | Cheshire West and Chester Borough Council | North West | Frodsham, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2016 to 2018 | 20 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 103.34 |  | NWC012F/000A/034A
Littleton, Chester | Cheshire West and Chester Borough Council | North West | Littleton, Chester | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2018 to 2021 | 8 | 0 | 22 | 0 | 2 | 0 | 2 | 0 | 10.743 |  | NWC012F/000A/036A
Liverpool Road, Neston, Ellesmere Port | Cheshire West and Chester Borough Council | North West | Neston, Ellesmere Port | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2018 to 2021 | 3 | 0 | 17 | 0 | 1 | 0 | 1 | 0 | 9.631 |  | NWC014F/000A/001A
Weetwood Common, Tarporley | Cheshire West and Chester Borough Council | North West | Tarporley, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2016 to 2018 | 4 | 0 | 6 | 0 | 2 | 0 | 2 | 0 | 30.743 |  | NWC012F/000A/046A
Birch Vale, Derbyshire Suface Water Mgmt | Derbyshire County Council | North West | Birch Vale, Derbyshire | 0 | 8 | 7 | 2 | 5 | 0 | 217 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 611.528 |  | NWC011F/008A/017A
New Mills, Derbyshire Surface Water Mgmt | Derbyshire County Council | North West | New Mills, Derbyshire | 0 | 16 | 0 | 0 | 2 | 0 | 150 | 2018 to 2021 | 124 | 0 | 8 | 0 | 35 | 0 | 35 | 0 | 833.23 |  | NWC011F/008A/016A
Fairhaven and Church Scar Coast Protection | Fylde Borough Council | North West | Lytham St Annes, Lancashire | 0 | 0 | 0 | 0 | 0 | 0 | 18119.8469 | 2018 to 2021 | 16082.3455 | 0 | 400 | 0 | 1155 | 990 | 1155 | 990 | 242027.9355 |  | NWS002C/00A/011C
Bridgewater and Lockgate, Runcorn | Halton BC | North West | Windmill Hill, Runcorn, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 2018 to 2021 | 180 | 0 | 40 | 0 | 120 | 0 | 120 | 0 | 2234 |  | NWC012F/000A/022A
Runcorn & Widnes Culvert Study | Halton BC | North West | Farnworth, Widnes, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 35 | TBC | 10 | 0 | 10 | 0 | 15 | 0 | 15 | 0 | 61 |  | NWC008F/000A/044A
Knowsley Village Land Drainage Investigation | Knowsley MBC | North West | Knowsley Village, Knowsley, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 112 | TBC | 85 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 346.452 |  | NWC008F/000A/045A
Salerno Drive, Knowsley | Knowsley MBC | North West | Knowsley, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 100 | TBC | 80 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 358.283 |  | NWC008F/000A/074A
Warrington Road, Knowsley | Knowsley MBC | North West | Knowsley, Merseyside | 0 | 15 | 0 | 0 | 5 | 0 | 120 | 2018 to 2021 | 100 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 583.655 |  | NWC008F/000A/077A
Hurlston Brook, Ormskirk West Study | Lancashire County Council | North West | Ormskirk, Lancashire | 0 | 112 | 0 | 0 | 0 | 0 | 2111 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 46256 |  | NWC009F/000A/028A
Liverpool Debris screens and access | Liverpool City Council | North West | Liverpool, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 2016 to 2018 | 121 | 0 | 50 | 0 | 85 | 0 | 85 | 0 | 486.667 |  | NWC008F/000A/088A
Lower Tue Brook Culvert, Liverpool | Liverpool City Council | North West | Liverpool, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2016 to 2018 | 375 | 0 | 125 | 0 | 155 | 0 | 155 | 0 | 1029.245 |  | NWC008F/000A/048A
Mab Lane Surface Water Culvert, Liverpool | Liverpool City Council | North West | Liverpool, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2018 to 2021 | 375 | 0 | 125 | 0 | 270 | 0 | 270 | 0 | 1453.279 |  | NWC008F/000A/050A
Upper Brook Surface Water Mgmt, Liverpool | Liverpool City Council | North West | Liverpool, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 235 | TBC | 160 | 0 | 75 | 0 | 105 | 0 | 105 | 0 | 476.043 |  | NWC008F/000A/049A
King William IV Fishing Lake Outfall and Overflow Replacement | Manchester City Council | North West | Higher Blackley King William IV Fishing Lake discharging to the River Irk | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2018 to 2021 | 100 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 3149.419 |  | NWC005F/000A/020A
Broomes Park, Royton, Oldham | Oldham Council | North West | Royton, Oldham | 0 | 15 | 0 | 0 | 0 | 0 | 165 | 2018 to 2021 | 130 | 0 | 20 | 0 | 15 | 0 | 15 | 0 | 675 |  | NWC005F/000A/040A
Churchfields, Dobcross, Oldham | Oldham Council | North West | Dobcross, Oldham | 0 | 15 | 0 | 0 | 0 | 0 | 570 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 2510 |  | NWC005F/000A/027A
Delph New Road, Oldham | Oldham Council | North West | Delph, Oldham | 0 | 10 | 0 | 0 | 55 | 0 | 360 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 660 |  | NWC005F/000A/028A
Dobcross New Road, Oldham | Oldham Council | North West | Dobcross, Oldham | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 2021 on | 10 | 0 | 70 | 0 | 0 | 0 | 15 | 0 | 230 |  | NWC005F/000A/029A
Greencroft Meadow, Royton, Oldham | Oldham Council | North West | Royton, Oldham, Luzley Brook Culvert Improvement Flood Defence | 0 | 10 | 0 | 0 | 0 | 0 | 130 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 100 |  | NWC005F/000A/043A
Merton Avenue, Medlock Vale, Oldham | Oldham Council | North West | Medlock Vale, Oldham | 0 | 15 | 0 | 0 | 0 | 0 | 115 | 2018 to 2021 | 90 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 305 |  | NWC005F/000A/044A
Patridge Way, Chadderton, Oldham | Oldham Council | North West | Royton, Oldham | 0 | 15 | 0 | 0 | 30 | 0 | 260 | 2018 to 2021 | 170 | 0 | 45 | 0 | 20 | 0 | 20 | 0 | 625 |  | NWC005F/000A/041A
Pencil Brook - River Beal , Shaw Oldham | Oldham Council | North West | Shaw, Oldham | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 2016 to 2018 | 250 | 0 | 50 | 0 | 20 | 0 | 20 | 0 | 15 |  | NWC005F/000A/025A
Heywood Surface Water Management Programme | Rochdale MBC | North West | Heywood, Greater Manchester | 0 | 75 | 0 | 0 | 75 | 0 | 1150 | 2018 to 2021 | 375 | 0 | 375 | 0 | 0 | 0 | 200 | 0 | 4850 |  | NWC005F/000A/034A
Betton, Shropshire | Shropshire Council | North West | Betton, Shropshire | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 2016 to 2018 | 2.8 | 1.5 | 2.2 | 0 | 1 | 0 | 1 | 0 | 23.5 |  | NWC012F/000A/047A
The Rookery, Kidsgrove | Staffordshire County Council | North West | Kidsgrove, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 2018 to 2021 | 145 | 75 | 0 | 0 | 40 | 0 | 40 | 0 | 316.442 |  | NWC012F/000A/045A
Burford Lane, Lymm Telemetry | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2018 to 2021 | 4 | 0 | 3 | 0 | 1 | 0 | 1 | 0 | 26.753 |  | NWC008F/000A/071A
Warrington Culverted Ordinary Watercourse Improvements | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 2018 to 2021 | 105 | 0 | 30 | 0 | 80 | 0 | 80 | 0 | 837.591 |  | NWC008F/000A/057A
Warrington Ordinary Watercourse Asset Identification Survey | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 80 | 0 | 20 | 0 | 40 | 0 | 40 | 0 | 450.979 |  | NWC008F/000A/073A
Warrington Road, Walton | Warrington Borough Council | North West | Warrington, Cheshire | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 10 | 0 | 5 | 0 | 2 | 0 | 2 | 0 | 52.506 |  | NWC008F/000A/070A
Rock Park Esplanade Restoration, Birkenhead | Wirral MBC | North West | Birkenhead, Merseyside | 0 | 0 | 0 | 0 | 0 | 0 | 1680.94 | 2018 to 2021 | 373.243 | 0 | 452.772 | 0 | 0 | 20 | 0 | 50 | 332 |  | NWS001C/000A/016A
Wirral Surface Water Management | Wirral MBC | North West | Wirral, Merseyside | 0 | 180 | 0 | 0 | 85 | 0 | 1365 | 2018 to 2021 | 50 | 0 | 50 | 0 | 0 | 0 | 2720 | 0 | 8953.245 |  | NWC008F/000A/060A
Dene Beck Culvert Remedials | Environment Agency | Northumbria | South Church, Bishop Auckland: Dene Beck Watercourse | 0 | 0 | 0 | 0 | 0 | 0 | 154.9 | 2016 to 2018 | 144.9 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 2365 |  | NOC305E/000A/048A
Forest Hall Culvert Remedials | Environment Agency | Northumbria | Forest Hall Letch, Newcastle | 0 | 0 | 0 | 0 | 0 | 0 | 175.6 | 2016 to 2018 | 165.6 | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 3736 |  | NOC304E/000A/045A
Great Ayton | Environment Agency | Northumbria | Great Ayton | 0 | 0 | 0 | 0 | 0 | 0 | 1032.5 | 2018 to 2021 | 232.5 | 650 | 150 | 0 | 95 | 0 | 95 | 0 | 0.096 |  | NOC306E/000A/057A
St Omer's Haugh Flood Defence, Gateshead | Environment Agency | Northumbria | St Omer's Haugh, Gateshead | 0 | 0 | 0 | 0 | 0 | 0 | 138.474 | 2018 to 2021 | 15.974 | 60 | 62.5 | 0 | 5 | 0 | 5 | 0 | 175 |  | NOC304E/000A/049A
Team Valley Flood Alleviation | Environment Agency | Northumbria | Team Valley, Gateshead | 0 | 0 | 0 | 80 | 0 | 0 | 1824.5 | 2016 to 2018 | 754.5 | 375 | 600 | 0 | 20 | 0 | 20 | 0 | 3005 |  | NOC304E/000A/039A
Tindale Beck Flood Alleviation | Environment Agency | Northumbria | West Auckland, Tindale Beck | 100 | 0 | 0 | 0 | 0 | 0 | 648.9 | 2016 to 2018 | 201.9 | 197 | 100 | 0 | 30 | 0 | 30 | 0 | 1988 |  | NOC305E/000A/018A
Wolsingham Culverts | Environment Agency | Northumbria | Trod Beck, Wolsingham, County Durham | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 2016 to 2018 | 167 | 0 | 40 | 0 | 25 | 0 | 25 | 0 | 2150 |  | NOC305F000A018A
Darlington Town Centre Fringe Flood Alleviation | Darlington Borough Council | Northumbria | Darlington Town Centre Fringe | 0 | 0 | 0 | 200 | 1500 | 0 | 11022.4 | 2021 on | 124.5 | 0 | 2400 | 0 | 0 | 0 | 175 | 0 | 3730 |  | NOC306E/000A/032A
Castlefields, Bournmoor | Durham County Council | Northumbria | Side of Castlefields, Bournmoor | 0 | 0 | 0 | 0 | 0 | 0 | 36.3 | 2018 to 2021 | 10.3 | 21 | 5 | 0 | 2 | 0 | 2 | 0 | 20 |  | NOC305F/000A/022A
Hardwick Road, Sedgefield | Durham County Council | Northumbria | 14 - 22 hardwick Road, Sedgefield | 0 | 0 | 0 | 0 | 0 | 0 | 160.7 | 2018 to 2021 | 55.7 | 55 | 50 | 0 | 10 | 0 | 10 | 0 | 120 |  | NOC305F/000A/028A
Hillmeads, Nettlesworth | Durham County Council | Northumbria | Rear of 23-32, Hillmeads, Nettleworth | 0 | 0 | 0 | 0 | 0 | 0 | 98.3 | 2018 to 2021 | 88.3 | 0 | 10 | 0 | 2 | 0 | 2 | 0 | 230 |  | NOC305F/000A/030A
New Brancepeth and Ushaw Moor Surface Water Flood Management | Durham County Council | Northumbria | New Brancepeth and Ushaw Moor | 84.1 | 0 | 0 | 0 | 0 | 0 | 172.1 | 2018 to 2021 | 0 | 58 | 30 | 0 | 10 | 0 | 10 | 0 | 76.5 |  | NOC305F/000A/013A
North West Durham Property Level Protection | Durham County Council | Northumbria | North West Durham Co Const (Consett, Stanley, Burnhope, Langley Park) | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 2018 to 2021 | 26 | 2 | 5 | 0 | 5 | 0 | 5 | 0 | 120 |  | NOC305F/000A/014A
Pelton Flood Alleviation | Durham County Council | Northumbria | Heathmeads, Pelton and Brackenbeds Close, Pelton | 0 | 0 | 0 | 0 | 0 | 0 | 32.1 | 2016 to 2018 | 27.1 | 0 | 5 | 0 | 10 | 0 | 10 | 0 | 269 |  | NOC305F/000A/015A
Shotley Bridge Surface Water Flood Management | Durham County Council | Northumbria | Shotley Bridge | 0 | 0 | 0 | 5 | 0 | 0 | 90.9 | 2018 to 2021 | 45.9 | 10 | 30 | 0 | 5 | 0 | 5 | 0 | 62.5 |  | NOC304F/000A/040A
Field Lane / Laburnum Avenue | Gateshead Council | Northumbria | Field Lane, Heworth | 0 | 16.1 | 0 | 0 | 0 | 0 | 165.8 | 2021 on | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 345.952 |  | NOC304F/000A/021A
Green Lane Gardens | Gateshead Council | Northumbria | Green Lane Gardens, East Gateshead | 53.6 | 0 | 0 | 0 | 0 | 0 | 497.1 | 2021 on | 316 | 67.5 | 60 | 0 | 30 | 0 | 30 | 0 | 329.67 |  | NOC304F/000A/023A
Heworth | Gateshead Council | Northumbria | Heworth, East Gateshead | 0 | 10.3 | 0 | 5 | 5 | 0 | 216.3 | 2018 to 2021 | 80.3 | 15 | 15 | 0 | 0 | 0 | 20 | 0 | 575 |  | NOC304F/000A/048A
Ridgeway & Leam Lane, East Gateshead | Gateshead Council | Northumbria | Leam Lane, East Gateshead | 0 | 10.3 | 0 | 5 | 5 | 0 | 127.8 | 2016 to 2018 | 92.5 | 10 | 5 | 0 | 40 | 0 | 40 | 0 | 819.134 |  | NOC306F/000A/025A
Sherburn Park Estate, Rowlands Gill Surface water management | Gateshead Council | Northumbria | Rowlands Gill, Gateshead | 0 | 5.2 | 0 | 5 | 10 | 0 | 106.4 | 2018 to 2021 | 76.2 | 5 | 5 | 0 | 30 | 0 | 30 | 0 | 556.926 |  | NOC304F/000A/046A
Cornwall Close | Middlesbrough Borough Council | Northumbria | Nunthorpe, Middlesbrough | 0 | 0 | 0 | 10 | 0 | 0 | 82.8 | 2018 to 2021 | 41.8 | 15.5 | 15.5 | 0 | 0 | 0 | 0 | 0 | 107.206 |  | NOC306F/000A/022A
Middlebeck, Town Farm | Middlesbrough Borough Council | Northumbria | Town Farm, Middlesbrough, Middlebeck | 0 | 0 | 0 | 30 | 0 | 0 | 342.5 | 2018 to 2021 | 252.5 | 0 | 60 | 0 | 20 | 0 | 20 | 0 | 291.622 |  | NOC306F/000A/019A
Middlesbrough Golf Club dam, Marton West Beck | Middlesbrough Borough Council | Northumbria | Middlesbrough, Marton West Beck | 0 | 0 | 0 | 27.058 | 0 | 0 | 394.458 | 2018 to 2021 | 114.8 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 1139.554 |  | NOC306F/000A/020A
Ormesby High Street | Middlesbrough Borough Council | Northumbria | Ormesby | 0 | 0 | 0 | 55 | 0 | 0 | 324.724 | 2018 to 2021 | 119.2 | 0 | 150.524 | 0 | 0 | 0 | 0 | 0 | 227.728 |  | NOC306F/000A/021A
Saltersgill Fields | Middlesbrough Borough Council | Northumbria | Middlesbrough | 0 | 10 | 0 | 0 | 0 | 0 | 223.2 | 2016 to 2018 | 187.8 | 0 | 0 | 0 | 70 | 0 | 70 | 0 | 1774.783 |  | NOC306F/000A/012A
Coast Road Drainage | Newcastle City Council | Northumbria | A1058 Junction with Chillingham Road, Newcastle | 0 | 0 | 0 | 0 | 20 | 0 | 215.5 | 2016 to 2018 | 56.5 | 44 | 75 | 0 | 0 | 0 | 0 | 0 | 785 |  | NOC304F/000A/016A
Fawdon Flood Alleviation | Newcastle City Council | Northumbria | Fawdon, Newcastle | 0 | 0 | 0 | 0 | 0 | 0 | 213.5 | 2016 to 2018 | 88.5 | 55 | 45 | 0 | 10 | 0 | 10 | 0 | 40 |  | NOC304F/000A/019A
Newcastle Central Motorway Drainage | Newcastle City Council | Northumbria | A167 Cowgate to Swan House Roundabout, Newcastle | 0 | 0 | 0 | 0 | 0 | 0 | 206.65 | 2016 to 2018 | 54.1 | 37.55 | 0 | 0 | 0 | 0 | 0 | 0 | 780 |  | NOC304F/000A/028A
Scrogg Road Flood Alleviation | Newcastle City Council | Northumbria | Newcastle - Byker/Walkergate - Scrogg Rd and surrounding area, inc Moorland Crescent, Ennerdale Rd, Ashbourne Avenue | 0 | 0 | 0 | 0 | 50 | 0 | 571.05 | 2016 to 2018 | 277.8 | 173.25 | 50 | 0 | 90 | 0 | 90 | 0 | 1175 |  | NOC304F/000A/038A
West Gosforth Flood Alleviation | Newcastle City Council | Northumbria | Regent Farm Estate and surrounding area, including Park Avenue, Gosforth, Newcastle | 0 | 0 | 0 | 0 | 0 | 0 | 112.1 | 2016 to 2018 | 49.6 | 17.5 | 20 | 0 | 15 | 0 | 15 | 0 | 395 |  | NOC304F/000A/041A
Briar Vale | North Tyneside Council | Northumbria | Briar Vale | 117.8 | 0 | 0 | 0 | 0 | 0 | 277.8 | 2018 to 2021 | 0 | 20 | 140 | 0 | 20 | 0 | 20 | 0 | 330.622 |  | NOC304F/000A/002A
Central Promenade Appraisal, Design And Construction, North Tyneside | North Tyneside Council | Northumbria | Whitely Bay, Tyne & Wear | 350 | 0 | 0 | 0 | 0 | 0 | 3086.2 | 2016 to 2018 | 489.2 | 100 | 1700 | 0 | 0 | 60 | 0 | 60 | 3608 |  | NOS301C/000A/006A
Fairfield Green | North Tyneside Council | Northumbria | Fairfield Green, West Monkseaton | 0 | 0 | 0 | 0 | 0 | 0 | 399.1 | 2016 to 2018 | 269.1 | 0 | 0 | 0 | 90 | 0 | 90 | 0 | 2273.297 |  | NOC304F/000A/001A
Killingworth, Longbenton, and Forest Hall Surface Water | North Tyneside Council | Northumbria | Killingworth, Longbenton and Forest Hall, North Tyneside | 0 | 144.4 | 0 | 45 | 1285 | 0 | 9512.7 | 2018 to 2021 | 337.7 | 0 | 6670 | 0 | 65 | 0 | 65 | 0 | 11347 |  | NOC304F/000A/025A
Killingworth, Longbenton, and Forest Hall Surface Water | North Tyneside Council | Northumbria | Killingworth, Longbenton and Forest Hall, North Tyneside | 0 | 0 | 0 | 0 | 1999 | 0 | 11855.033 | 2018 to 2021 | 166.3 | 0 | 2000 | 0 | 0 | 0 | 125 | 0 | 7902 |  | NOC304F/000A/026A
Long Sands and Bear's Back Sea Wall, Tynemouth | North Tyneside Council | Northumbria | Tynemouth, Tyne & Wear | 0 | 32.1 | 0 | 0 | 0 | 0 | 452.3 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426 |  | NOS301C/000A/010A
Sea Banks Sea Wall - Appraisal Design and Construction, Tynemouth | North Tyneside Council | Northumbria | Tynemouth, Tyne & Wear | 0 | 32.1 | 0 | 45 | 0 | 0 | 450.7 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1426 |  | NOS301C/000A/012A
Southern Promenade Sea Wall Repair - Whitely Bay | North Tyneside Council | Northumbria | Whitely Bay, Tyne & Wear | 0 | 0 | 0 | 0 | 0 | 0 | 766.2 | 2016 to 2018 | 281.2 | 65 | 270 | 0 | 0 | 40 | 0 | 40 | 665.168 |  | NOS301C/000A/017A
Upper Tees Flood Risk Management | North Yorkshire County Council | Northumbria | Upper Tees | 0 | 0 | 0 | 60 | 60 | 0 | 932.16 | 2016 to 2018 | 568.512 | 0 | 0 | 0 | 95 | 0 | 95 | 0 | 13176.1941 |  | NOC306F/000A/015A
Alnwick East Surface Water Flood Alleviation | Northumberland County Council | Northumbria | Alnwick, Northumberland | 0 | 0 | 0 | 0 | 0 | 0 | 258.1 | 2016 to 2018 | 50.1 | 25 | 156 | 0 | 10 | 0 | 10 | 0 | 57.302 |  | NOC301F/000A/003A
Beadnell North Sea Wall Improvements | Northumberland County Council | Northumbria | Harbour Rd, Beadnell, Northumberland | 0 | 322.726 | 0 | 0 | 0 | 0 | 3093 | 2018 to 2021 | 587.274 | 0 | 2093 | 0 | 0 | 70 | 0 | 70 | 7446.682 |  | NOS301C000A016A
Blenkinsopp Flood Alleviation | Northumberland County Council | Northumbria | Blenkinsopp, Northumberland | 0 | 0 | 0 | 10 | 0 | 0 | 215 | 2018 to 2021 | 60 | 0 | 140 | 0 | 5 | 0 | 5 | 0 | 811.683 |  | NOC304F/000A/011A
Boulmer Coast Protection | Northumberland County Council | Northumbria | Boulmer, Northumberland | 0 | 0 | 0 | 0 | 24 | 0 | 205.9 | 2016 to 2018 | 178.9 | 0 | 3 | 0 | 0 | 25 | 0 | 25 | 686.731 |  | NOS301C/000A/026A
Haltwhistle Flood Alleviation | Northumberland County Council | Northumbria | Haltwhistle, Northumberland | 300.1 | 0 | 0 | 0 | 0 | 0 | 316.6 | 2016 to 2018 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 3693.635 |  | NOC304F/000A/024A
Lowick Flood Mitigation | Northumberland County Council | Northumbria | Lowick | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 2018 to 2021 | 12.5 | 0 | 3 | 0 | 2 | 0 | 2 | 0 | 64 |  | NOC301F/000A/009A
Newbiggin Point Coast Protection | Northumberland County Council | Northumbria | Newbiggin Point, Northumberland | 0 | 0 | 0 | 0 | 0 | 0 | 177.8 | 2018 to 2021 | 92.3 | 42 | 43.5 | 0 | 0 | 0 | 0 | 0 | 1250.269 |  | NOS301C/000A/033A
Red Row Property Level Protection | Northumberland County Council | Northumbria | Red Row | 0 | 0 | 0 | 0 | 0 | 0 | 5.22 | 2018 to 2021 | 2.5 | 0.67 | 2.05 | 0 | 1 | 0 | 1 | 0 | 12.755 |  | NOC301F/000A/008A
Seaton Sluice Harbour Improvements | Northumberland County Council | Northumbria | Seaton Sluice | 0 | 0 | 0 | 25 | 25 | 0 | 1549.9 | 2018 to 2021 | 499.9 | 0 | 1000 | 0 | 0 | 60 | 0 | 60 | 1706.98 |  | NOS301C/000A/066A
Shilbottle Surface Water Flood Alleviation | Northumberland County Council | Northumbria | Shilbottle, Northumberland | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 2018 to 2021 | 160 | 30 | 60 | 0 | 15 | 0 | 15 | 0 | 1126.59 |  | NOC301F/000A/007A
Charltons Inland Flood Alleviation | Redcar and Cleveland Borough Council | Northumbria | Charltons | 0 | 0 | 0 | 39 | 0 | 0 | 445 | 2018 to 2021 | 186 | 0 | 220 | 0 | 10 | 0 | 10 | 0 | 353 |  | NOC306F/000A/005A
Cross Beck Inland Flood Alleviation | Redcar and Cleveland Borough Council | Northumbria | Eston | 0 | 0 | 0 | 100 | 0 | 0 | 1461.9 | 2018 to 2021 | 307 | 205 | 300 | 0 | 0 | 0 | 30 | 0 | 2100 |  | NOC306F/000A/007A
St Joseph's Court Property Level protection | Redcar and Cleveland Borough Council | Northumbria | Redcar | 79.3 | 0 | 0 | 0 | 0 | 0 | 137.3 | 2018 to 2021 | 0 | 0 | 48 | 0 | 25 | 0 | 25 | 0 | 71 |  | NOC306F/000A/026A
Whale Hill Ironstone Culvert | Redcar and Cleveland Borough Council | Northumbria | Eston | 0 | 0 | 0 | 200 | 0 | 0 | 1282.8 | 2021 on | 350.9 | 100 | 0 | 0 | 0 | 0 | 50 | 0 | 1900 |  | NOC306F/000A/014A
Boldon Flats Improvement | South Tyneside Council | Northumbria | East Boldon, South Tyneside | 0 | 0 | 0 | 0 | 0 | 0 | 542.4 | 2018 to 2021 | 150.4 | 177 | 15 | 0 | 0 | 0 | 10 | 0 | 100 |  | NOC304E/000A/037A
Cleadon Village - Appraisal, Design and Construction | South Tyneside Council | Northumbria | Cleadon, South Tyneside | 0 | 0 | 0 | 50 | 0 | 0 | 1805.9 | 2018 to 2021 | 228.4 | 220.5 | 450 | 0 | 0 | 0 | 55 | 0 | 2317.136 |  | NOC304F/000A/015A
Marsden Bay Cliff Erosion Study | South Tyneside Council | Northumbria | Marsden Bay, Whitburn | 0 | 0 | 0 | 0 | 50 | 0 | 856.1 | 2018 to 2021 | 310.5 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 9187 |  | NOS302C/000A/013A
Monkton Village Flood Alleviation Study | South Tyneside Council | Northumbria | Hebburn, South Tyneside | 0 | 0 | 0 | 100 | 400 | 0 | 5499.97 | 2016 to 2018 | 3999.97 | 200 | 600 | 0 | 750 | 0 | 750 | 0 | 7729.2186 |  | NOC304F/000A/009A
Newmarket Walk South Shields Flood Alleviation Study | South Tyneside Council | Northumbria | South Shields, South Tyneside | 0 | 0 | 0 | 50 | 50 | 0 | 1325.3 | 2018 to 2021 | 237.5 | 140 | 185 | 0 | 0 | 0 | 85 | 0 | 410.625 |  | NOC304F/000A/044A
Citywide Culvert Repairs | Sunderland City Council | Northumbria | Sunderland City | 0 | 53.6 | 0 | 220 | 200 | 0 | 2517.2 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18954.8174 |  | NOC305F/000A/024A
Hendon Foreshore Barrier / Stonehill Wall / Breakwater | Sunderland City Council | Northumbria | Sunderland | 0 | 0 | 0 | 100 | 1500 | 0 | 11111.767 | 2016 to 2018 | 631.9 | 300 | 1500 | 0 | 0 | 0 | 0 | 0 | 66210.517 |  | NOS302C/000A/050A
Bishops Tawton Flood Defence | Environment Agency | South West | Bishops Tawton Barnstaple River Taw | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 2016 to 2018 | 60 | 75 | 200 | 0 | 15 | 0 | 15 | 0 | 849.967 |  | SWC014E/000A/059A
Bude flood defence and river restoration | Environment Agency | South West | Bude | 64 | 0 | 0 | 0 | 94 | 0 | 1102 | 2016 to 2018 | 456 | 0 | 468 | 0 | 30 | 0 | 30 | 0 | 6844 |  | SWC009E/000A/032A
Calstock flood defence improvements and habitat creation | Environment Agency | South West | Calstock | 80 | 0 | 0 | 0 | 10 | 0 | 768.159 | 2016 to 2018 | 478 | 0 | 190 | 0 | 20 | 0 | 20 | 0 | 960 |  | SWC011E/000A/045A
Clyst St Mary Flood Defence Improvements | Environment Agency | South West | Clyst St Mary | 0 | 75 | 0 | 0 | 150 | 0 | 1225 | 2018 to 2021 | 750 | 250 | 0 | 0 | 40 | 0 | 40 | 0 | 4526.006 |  | SWC013E/000A/092A
Copperhouse Gate Refurbishment | Environment Agency | South West | Hayle | 0 | 30 | 0 | 0 | 0 | 0 | 163 | 2018 to 2021 | 53 | 0 | 80 | 0 | 25 | 0 | 25 | 0 | 3269 |  | SWC010E/000A/098A
East The Water, Bideford | Environment Agency | South West | Bideford | 0 | 20 | 0 | 0 | 50 | 0 | 1095 | 2018 to 2021 | 75 | 0 | 950 | 0 | 30 | 0 | 30 | 0 | 0 |  | SWC014E/000A/061A
Exmouth Tidal Defence | Environment Agency | South West | Exmouth | 50 | 276 | 0 | 0 | 0 | 0 | 4369.383 | 2016 to 2018 | 3300 | 0 | 500 | 0 | 1100 | 0 | 1100 | 0 | 31220 |  | SWS006E/000A/051A
Fowey Flood Alleviation | Environment Agency | South West | Fowey | 0 | 50 | 0 | 0 | 100 | 0 | 1080 | 2018 to 2021 | 330 | 0 | 495 | 0 | 0 | 0 | 30 | 0 | 7765 |  | SWS005E/000A/036A
Hayle Flood Alleviation - Foundry Square | Environment Agency | South West | Hayle | 0 | 0 | 0 | 0 | 100 | 0 | 575 | 2018 to 2021 | 20 | 0 | 455 | 0 | 5 | 0 | 5 | 0 | 1710 |  | SWC010E/000A/038A
Hayle River flood bank re-alignment and habitat creation | Environment Agency | South West | Hayle | 0 | 40 | 0 | 0 | 100 | 0 | 2300 | 2016 to 2018 | 180 | 0 | 1980 | 0 | 25 | 0 | 25 | 0 | 437 |  | SWC010E/000A/067A
Looe | Environment Agency | South West | Looe | 100 | 100 | 0 | 0 | 400 | 0 | 4850 | 2016 to 2018 | 1180 | 0 | 3070 | 0 | 115 | 0 | 115 | 0 | 29480 |  | SWS005E/000A/007A
Mevagissey - fluvial | Environment Agency | South West | Mevagissey | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 2018 to 2021 | 237 | 185 | 25 | 0 | 45 | 0 | 45 | 0 | 1832 |  | SWS005E/000A/037A
Newlyn - fluvial | Environment Agency | South West | Newlyn | 0 | 30 | 0 | 0 | 70 | 0 | 965 | 2018 to 2021 | 50 | 0 | 815 | 0 | 15 | 0 | 15 | 0 | 3719 |  | SWS005E/000A/021A
Newlyn - tidal | Environment Agency | South West | Newlyn | 0 | 25 | 0 | 0 | 45 | 0 | 410 | 2018 to 2021 | 30 | 0 | 310 | 0 | 10 | 0 | 10 | 0 | 658 |  | SWS005E/000A/040A
Newton Abbot and Kingsteignton Flood Defence Improvements | Environment Agency | South West | Newton Abbot and Kingsteignton | 0 | 333 | 0 | 50 | 0 | 0 | 2533 | 2018 to 2021 | 1800 | 100 | 250 | 0 | 530 | 0 | 530 | 0 | 17689.78 |  | SWC015E/000A/077A
Par/st. Blazey | Environment Agency | South West | Par/St. Blazey | 0 | 450 | 0 | 0 | 550 | 0 | 19933 | 2018 to 2021 | 6453 | 0 | 12480 | 0 | 450 | 0 | 450 | 0 | 111843 |  | SWC010C/000A/111A
Penryn tidal | Environment Agency | South West | Penryn | 0 | 70 | 0 | 0 | 30 | 0 | 507 | 2018 to 2021 | 105 | 0 | 302 | 0 | 20 | 0 | 20 | 0 | 2479 |  | SWS005E/000A/022A
Penzance Wherrytown and harbour tidal | Environment Agency | South West | Penzance | 85 | 0 | 0 | 0 | 110 | 0 | 1345 | 2016 to 2018 | 355 | 0 | 795 | 0 | 60 | 0 | 60 | 0 | 6368 |  | SWS005E/000A/012A
Sandy River Improvements | Environment Agency | South West | St Austell | 0 | 36 | 0 | 0 | 60 | 0 | 626.41 | 2018 to 2021 | 343.41 | 0 | 187 | 0 | 90 | 0 | 90 | 0 | 7488 |  | SWC009E/000A/036A
Seaton Estuary Improvements | Environment Agency | South West | Seaton | 0 | 275 | 0 | 0 | 30 | 0 | 3485 | 2018 to 2021 | 1700 | 0 | 1150 | 0 | 480 | 0 | 480 | 0 | 5207.57 |  | SWC012E/000A/055A
Totnes Flood Defence Improvements | Environment Agency | South West | Totnes | 147 | 0 | 0 | 24 | 0 | 0 | 4114.1 | 2016 to 2018 | 3291 | 0 | 319 | 0 | 225 | 0 | 225 | 0 | 51962.02 |  | SWC015E/000A/052A
Victoria Stream Improvements, Dartmouth | Environment Agency | South West | Dartmouth, Devon | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 100 | 0 | 0 | 0 | 60 | 0 | 60 | 0 | 950 |  | SWC015E/000A/049A
Wadebridge flood defence improvements and habitat creation | Environment Agency | South West | Wadebridge | 0 | 60 | 0 | 0 | 150 | 0 | 3144 | 2018 to 2021 | 269 | 0 | 2665 | 0 | 170 | 0 | 170 | 0 | 0 |  | SWC009E/000A/047A
Wadebridge sheet pile wall | Environment Agency | South West | Wadebridge | 0 | 37 | 0 | 0 | 0 | 0 | 310 | 2018 to 2021 | 165 | 0 | 108 | 0 | 15 | 0 | 15 | 0 | 3994 |  | SWC009E/000A/021A
White River flood defence re-alignment and habitat creation | Environment Agency | South West | St Austell | 0 | 0 | 0 | 0 | 180 | 0 | 2685 | 2016 to 2018 | 289 | 0 | 2196 | 0 | 45 | 0 | 45 | 0 | 3592 |  | SWC009E/000A/037A
Wrafton Flood Defence | Environment Agency | South West | Wrafton Braunton North Devon River Knowl and tidal | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 2018 to 2021 | 185 | 50 | 20 | 0 | 95 | 0 | 95 | 0 | 490.249 |  | SWC014E/000A/068A
A390 Tregrehan Stream culvert improvements | Cornwall Council | South West | Tregehan Stream, Par | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 2016 to 2018 | 200 | 0 | 150 | 0 | 5 | 0 | 5 | 0 | 5710 |  | SWC010F/000A/104A
Chapel Square, Mevagissey Culvert Improvements | Cornwall Council | South West | Mevagissey | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 2018 to 2021 | 190 | 115 | 25 | 0 | 45 | 0 | 45 | 0 | 1938 |  | SWO007F/000A/049A
Downderry Coast Protection Phase 2 | Cornwall Council | South West | Downderry | 0 | 0 | 0 | 0 | 0 | 0 | 826 | 2018 to 2021 | 495 | 0 | 331 | 0 | 0 | 25 | 0 | 25 | 3580.189 |  | SWC011C/000A/055A
Halzephron Coastal Adaptation | Cornwall Council | South West | Gunwalloe | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2018 to 2021 | 62.5 | 0 | 187.5 | 0 | 0 | 0 | 0 | 0 | 982.139 |  | SWC010C/000A/049A
Hannafore Sea Defence Refurbishment | Cornwall Council | South West | Hannafore | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 80 | 0 | 20 | 0 | 0 | 15 | 0 | 15 | 2306.649 |  | SWC009C/000A/049A
Individual Property Protection East Cornwall CFMP Area Year 2 | Cornwall Council | South West | East Cornwall | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2018 to 2021 | 33 | 12 | 54 | 0 | 20 | 0 | 20 | 0 | 444.348 |  | SWC009F/000A/054A_2
Individual Property Protection East Cornwall CFMP Area Year 3 | Cornwall Council | South West | East Cornwall | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2018 to 2021 | 33 | 12 | 54 | 0 | 20 | 0 | 20 | 0 | 447.582 |  | SWC009F/000A/054A_1
Individual Property Protection Tamar CFMP Area Year 2 | Cornwall Council | South West | Tamar | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2018 to 2021 | 33 | 12 | 54 | 0 | 20 | 0 | 20 | 0 | 444.348 |  | SWC011F/000A/087A
Individual Property Protection Tamar CFMP Area Year 3 | Cornwall Council | South West | Tamar | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2018 to 2021 | 33 | 12 | 54 | 0 | 20 | 0 | 20 | 0 | 447.582 |  | SWC011F/000A/088A
Individual Property Protection West Cornwall CFMP Area Year 2 | Cornwall Council | South West | West Conrwall | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2018 to 2021 | 33 | 12 | 54 | 0 | 20 | 0 | 20 | 0 | 444.348 |  | SWC010F/000A/088A
Individual Property Protection West Cornwall CFMP Area Year 3 | Cornwall Council | South West | West Conrwall | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 2018 to 2021 | 33 | 12 | 54 | 0 | 20 | 0 | 20 | 0 | 447.582 |  | SWC010F/000A/089A
Long Rock Revetment Extension East | Cornwall Council | South West | Long Rock, Penzance | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2018 to 2021 | 125 | 0 | 125 | 0 | 0 | 15 | 0 | 15 | 2082.139 |  | SWC010C/000A/050A
Long Rock Revetment Extension West | Cornwall Council | South West | Long Rock, Penzance | 0 | 0 | 0 | 0 | 0 | 0 | 1306 | 2018 to 2021 | 181 | 0 | 1125 | 0 | 0 | 0 | 0 | 0 | 2111.896 |  | SWC010C/000A/051A
Mevagissey Harbour Victoria Pier Refurbishment | Cornwall Council | South West | Mevagissey | 0 | 60 | 0 | 0 | 0 | 0 | 980 | 2018 to 2021 | 720 | 0 | 200 | 0 | 100 | 0 | 100 | 0 | 14878.558 |  | SWC010C/000A/052A
Millbrook Culvert Improvements Phase 2 | Cornwall Council | South West | Millbrook, SE Cornwall | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 2016 to 2018 | 95 | 0 | 30 | 0 | 25 | 0 | 25 | 0 | 2839 |  | SWC011F/000A/102A
Polruan Cliff Stabilisation | Cornwall Council | South West | Polruan | 0 | 0 | 0 | 0 | 0 | 0 | 99.5 | 2016 to 2018 | 59.5 | 0 | 40 | 0 | 0 | 10 | 0 | 10 | 862.58 |  | SWC010C/000A/105A
Prideaux and St Blazey Catchment Improvements | Cornwall Council | South West | St Blazey | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 2018 to 2021 | 275 | 0 | 0 | 0 | 70 | 0 | 70 | 0 | 867.3 |  | SWC009F/000A/056A
Tumble Tyn and Paul Stream Culvert Improvements | Cornwall Council | South West | Mousehole | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 2018 to 2021 | 135 | 75 | 50 | 0 | 20 | 0 | 20 | 0 | 708 |  | SWO007F/000A/052A
Branscombe Flood improvements | Devon County Council | South West | Street area of Branscombe | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 2016 to 2018 | 65 | 25 | 50 | 0 | 20 | 0 | 20 | 0 | 419.192 |  | SWC012F/000A/059A
Colaton Raleigh Flood Improvements | Devon County Council | South West | Colaton Raleigh | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 2018 to 2021 | 150 | 30 | 40 | 0 | 30 | 0 | 30 | 0 | 642.226 |  | SWC012F/000A/061A
Devon County Council Property Level Protection | Devon County Council | South West | Devon | 25 | 25 | 0 | 10 | 50 | 0 | 730 | 2016 to 2018 | 200 | 120 | 200 | 0 | 250 | 0 | 300 | 0 | 3713.084 |  | SWO005F/000A/058A
Exeter Flood Surface Water Improvements | Devon County Council | South West | Exeter | 0 | 0 | 0 | 0 | 0 | 0 | 585 | 2018 to 2021 | 300 | 50 | 70 | 0 | 60 | 0 | 60 | 0 | 417.038 |  | SWC013F/000A/099A
Kingsbridge Flood Improvements | Devon County Council | South West | Kingsbridge | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 2018 to 2021 | 500 | 50 | 100 | 0 | 100 | 0 | 100 | 0 | 2184.854 |  | SWS006F/000A/064A
Sidmouth Flood Improvement | Devon County Council | South West | Sidmouth | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 2018 to 2021 | 200 | 30 | 40 | 0 | 50 | 0 | 50 | 0 | 1096.564 |  | SWC012F/000A/060A
Uplyme Flood Resilience | Devon County Council | South West | Uplyme | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 2016 to 2018 | 250 | 30 | 70 | 0 | 50 | 0 | 50 | 0 | 1065.414 |  | SWC012F/000A/058A
New Feniton Flood Alleviation | East Devon District Council | South West | New Feniton, Devon | 0 | 0 | 0 | 0 | 0 | 0 | 1784 | 2016 to 2018 | 325 | 200 | 600 | 239.8 | 65 | 0 | 65 | 0 | 10369.223 |  | SWC012F/000A/06CA
Sidmouth Main Beach and Eastern Beach - Beach Management Plan | East Devon District Council | South West | Sidmouth | 0 | 0 | 0 | 0 | 0 | 0 | 370.5 | 2018 to 2021 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9737.339 |  | SWC012C/000A/044A_1
Mincinglake/Northbrook Watercourse Flood Alleviation | Exeter City Council | South West | EXETER | 0 | 75 | 0 | 0 | 0 | 0 | 1368 | 2018 to 2021 | 930 | 0 | 180 | 0 | 140 | 0 | 140 | 0 | 982 |  | SWCO13F/00A/077A
Topsham Tidal Defence | Exeter City Council | South West | Topsham, Exe Estuary | 14.342 | 0 | 0 | 0 | 0 | 0 | 234.342 | 2018 to 2021 | 100 | 0 | 120 | 0 | 20 | 0 | 20 | 0 | 1566.277 |  | SWC012E/000A/048A
Leigham Mill Culvert, Plymouth, culvert works | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 2018 to 2021 | 36 | 0 | 116 | 0 | 5 | 0 | 5 | 0 | 228 |  | SWS006F/000A/054A
The Ride, Plymouth, new watercourse culvert and tidal outfall | Plymouth city council | South West | Plymouth | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 2018 to 2021 | 60 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 113 |  | SWS006F/000A/062A
Salcombe Town Tidal Gates | South Hams DC | South West | Salcombe, Devon | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2016 to 2018 | 40 | 0 | 0 | 25 | 10 | 0 | 10 | 0 | 385.032 |  | SWC015F/000A/079A
Chudleigh - Bridgelands Bridge Flood Management | Teignbridge District Council | South West | Kate Brook, Chudleigh | 0 | 0 | 0 | 0 | 0 | 0 | 61.723 | 2018 to 2021 | 47.723 | 0 | 14 | 0 | 20 | 0 | 20 | 0 | 845.577 |  | SWC015F/000A/015A
Combeinteignhead, Culvert Replacement | Teignbridge District Council | South West | Combeinteignhead | 0 | 10 | 0 | 5 | 5 | 0 | 120 | 2016 to 2018 | 50 | 25 | 25 | 0 | 20 | 0 | 20 | 0 | 228.3029 |  | SWC015F/000A/058A
Coombe Valley Dam - Flood Storage Improvements | Teignbridge District Council | South West | Coombe Valley Dam, Teignmouth | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2018 to 2021 | 145 | 0 | 5 | 0 | 80 | 0 | 80 | 0 | 607.6512 |  | SWC015F/000A/059A
Dawlish Water - Flood Defence Improvements | Teignbridge District Council | South West | Dawlish Water | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2016 to 2018 | 60 | 0 | 0 | 0 | 35 | 0 | 35 | 0 | 478.4604 |  | SWC013F/000A/085A
Brixham Flood Alleviatioon | Torbay Council | South West | Brixham | 0 | 50 | 0 | 0 | 0 | 0 | 1280 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 16117.134 |  | SWC015F/000A/028A
Broadsands Sea Wall, Structural Repairs | Torbay Council | South West | Paignton | 0 | 5 | 0 | 0 | 0 | 0 | 180 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1560.257 |  | SWC015C/000A/034A
Coastal Defences in Torbay | Torbay Council | South West | Torbay | 0 | 200 | 0 | 0 | 20 | 0 | 1855 | 2016 to 2018 | 1500 | 0 | 60 | 0 | 970 | 0 | 970 | 0 | 27350.546 |  | SWC015F/000A/030A
Cockington Flood Alleviation | Torbay Council | South West | Torquay | 0 | 0 | 0 | 0 | 5 | 0 | 255 | 2018 to 2021 | 150 | 0 | 95 | 0 | 15 | 0 | 15 | 0 | 1347.277 |  | SWC015F/000A/081A
Collaton St Mary Flood Alleviation | Torbay Council | South West | Paignton | 0 | 5 | 0 | 0 | 0 | 0 | 191 | 2018 to 2021 | 86 | 50 | 50 | 0 | 10 | 0 | 10 | 0 | 1630.571 |  | SWC015F/000A/060A
Hollicombe Rock Armour | Torbay Council | South West | Paignton | 0 | 0 | 0 | 0 | 0 | 0 | 1390 | 2016 to 2018 | 1290 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 29622.935 |  | SWC015C/000A/082A
Monksbridge Flood Alleviation | Torbay Council | South West | Brixham | 0 | 0 | 0 | 0 | 10 | 0 | 260 | 2018 to 2021 | 210 | 0 | 40 | 0 | 35 | 0 | 35 | 0 | 3023.432 |  | SWS006F/000A/066A
Occombe Valley Watercourse Flood Alleviation | Torbay Council | South West | Paignton | 0 | 0 | 0 | 0 | 5 | 0 | 265 | 2016 to 2018 | 235 | 0 | 25 | 0 | 65 | 0 | 65 | 0 | 1458.881 |  | SWC015C/000A/045A
Paignton Flood Alleviation | Torbay Council | South West | Paignton | 0 | 60 | 0 | 0 | 0 | 0 | 1938 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 20464.078 |  | SWC015F/000A/031A
River Fleet Flood Alleviation | Torbay Council | South West | Torquay | 0 | 75 | 0 | 100 | 0 | 0 | 5359 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 25456.558 |  | SWC015F/000A/032A
Linear Flood Defence, Pebbleridge, Westward Ho! (Phase1) | Torridge District Council | South West | Coastal Village/SSSI/AONB/Biosphere | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 2018 to 2021 | 50 | 0 | 0 | 200 | 0 | 0 | 20 | 0 | 550 |  | SWS009F/000A/005A
Willow Road, Tavistock | West Devon Borough Council | South West | Tavistock, Devon | 0 | 5 | 0 | 0 | 5 | 0 | 105 | 2018 to 2021 | 40 | 0 | 45 | 0 | 105 | 0 | 105 | 0 | 522 |  | SWC011F/000A/091A_1
Aldingbourne Rife Integrated Flood Risk Management | Environment Agency | Southern | Aldingbourne, Bognor | 290 | 0 | 0 | 0 | 0 | 0 | 3217.5 | 2016 to 2018 | 1660 | 0 | 1050 | 0 | 450 | 0 | 450 | 0 | 7856.5 | Time Constrained Contribution | SOC008E/001A/012A
Arundel Tidal Defence Improvements Phase 1 - Low level raising | Environment Agency | Southern | Arundel | 0 | 50 | 0 | 0 | 0 | 0 | 600 | 2018 to 2021 | 230 | 0 | 320 | 0 | 140 | 0 | 140 | 0 | 5400 | Time Constrained Contribution | SOC008E/001A/013A
Elmer Beach Management Works | Environment Agency | Southern | Elmer, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2018 to 2021 | 475 | 0 | 25 | 0 | 105 | 20 | 105 | 20 | 6100 |  | SOS004E/003A/009A
Ferring Rife Embankment Improvements | Environment Agency | Southern | Ferring, Worthing | 0 | 75 | 0 | 0 | 0 | 0 | 600 | 2018 to 2021 | 275 | 0 | 250 | 0 | 170 | 0 | 170 | 0 | 3550 | Time Constrained Contribution | SOO002E/000A/296A
Five Oak Green Flood Alleviation | Environment Agency | Southern | Five Oak Green | 0 | 40 | 0 | 0 | 0 | 0 | 1534 | 2018 to 2021 | 494 | 0 | 1000 | 0 | 265 | 0 | 265 | 0 | 2810 |  | SOC003E/001A/009A
Hythe Ranges | Environment Agency | Southern | Hythe, Kent | 85.706 | 207.5 | 0 | 0 | 512.5 | 0 | 21052.107 | 2016 to 2018 | 6819.831 | 0 | 12874.169 | 0 | 670 | 0 | 670 | 0 | 730385.117 |  | SOS003E/001A/001A
Leigh & Lower Beult Flood Alleviation | Environment Agency | Southern | Tonbridge and Yalding, River Medway | 300 | 1005 | 0 | 0 | 1205 | 0 | 35160 | 2018 to 2021 | 11000 | 0 | 11000 | 0 | 0 | 0 | 1955 | 0 | 118925.15 |  | _B
Loxwood Flood Risk Management | Environment Agency | Southern | Loxwood, West Sussex | 50 | 0 | 0 | 0 | 0 | 0 | 370 | 2016 to 2018 | 80 | 0 | 240 | 0 | 30 | 0 | 30 | 0 | 660 | Time Constrained Contribution | SOC008E/000A/026A
Lydd Rangess | Environment Agency | Southern | Kent | 118.794 | 1277.886 | 0 | 0 | 3359.73 | 0 | 40461.412 | 2021 on | 7776.828 | 0 | 7735.672 | 0 | 0 | 0 | 3995 | 0 | 711765.568 |  | SOS003E/001A/015B
Middle Ouse WFD Mitigation and Wetland Habitat Creation | Environment Agency | Southern | Barcombe, East Sussex | 0 | 0 | 0 | 0 | 20 | 0 | 240 | 2016 to 2018 | 130 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 219.737 |  | SOC006E/000A/0013A
Pevensey Levels Desilting | Environment Agency | Southern | Pevensey Levels | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2016 to 2018 | 150 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 288.626 |  | SOC005E/000A/0010A
Portchester Castle to Paulsgrove Tidal Defence | Environment Agency | Southern | Portchester, North shore Portsmouth Harbour | 268 | 1332 | 0 | 0 | 0 | 0 | 9100 | 2016 to 2018 | 1019.946 | 0 | 6420.054 | 0 | 390 | 0 | 390 | 0 | 74372 |  | SOS005E/005A/001A
Romney Sands Coastal Defences | Environment Agency | Southern | Shepway District, Kent | 120.893 | 0 | 0 | 0 | 0 | 0 | 1460.607 | 2021 on | 1035 | 0 | 50 | 0 | 25 | 0 | 25 | 0 | 36725.197 |  | SOS003E/001A/012A
Rother Tidal Walls East | Environment Agency | Southern | Rother District, Kent | 100.666 | 385.283 | 0 | 0 | 50 | 0 | 7749.07 | 2021 on | 6796 | 0 | 25 | 0 | 210 | 0 | 210 | 0 | 176113.488 |  | SOS003E/001A/023A
Tidal Cuckmere River Restoration | Environment Agency | Southern | Tidal Cuckmere, South of Alfriston | 0 | 50 | 0 | 0 | 50 | 0 | 800 | 2018 to 2021 | 350 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 15.745 |  | SOC005E/000A/006A
West Brook North Flood Alleviation, Emsworth | Environment Agency | Southern | Emswoth The West Brook | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 2018 to 2021 | 280 | 0 | 320 | 0 | 55 | 0 | 55 | 0 | 4 |  | SOC009E/000A/002A
Arun Partnership Watercourse Management (East of District) | Arun DC | Southern | Rustington, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 2016 to 2018 | 70 | 0 | 20 | 0 | 50 | 0 | 50 | 0 | 120 |  | SOO003F/000A/007A
Arun to Pagham Beach Management Plan | Arun DC | Southern | Felpham, West Sussex | 0 | 10 | 0 | 0 | 0 | 0 | 223 | 2018 to 2021 | 132 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 27 |  | SOS004C/003A/010A
Land Drainage Outfall Extension - Peak Lane, Kingston | Arun DC | Southern | Kingston, West Sussex | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 2018 to 2021 | 24 | 0 | 44 | 0 | 10 | 0 | 10 | 0 | 132 |  | SOS004C/003A/018A
Bevendean Surface water | Brighton and Hove City Council | Southern | Bevendean, Brighton | 0 | 0 | 0 | 0 | 0 | 0 | 212.3187 | 2018 to 2021 | 20.847 | 0 | 191.4717 | 0 | 1 | 0 | 1 | 0 | 1569.7486 |  | SOC007E/000A/009A
Carden Avenue (Brighton) Surface Water | Brighton and Hove City Council | Southern | Warmdene Road, Brighton | 0 | 0 | 0 | 0 | 0 | 0 | 78.7228 | 2016 to 2018 | 16.6239 | 0 | 62.0989 | 0 | 5 | 0 | 5 | 0 | 833.998 |  | SOC007E/000A/010A
Patcham Flood Alleviation | Brighton and Hove City Council | Southern | Patcham Place Recreation Ground, Brighton | 0 | 0 | 0 | 0 | 0 | 0 | 141.2803 | 2016 to 2018 | 48.1319 | 0 | 93.1484 | 0 | 35 | 0 | 35 | 0 | 760.7108 |  | SOC007E/000A/014A
Works from Brighton Marina to River Adur Strategy | Brighton and Hove City Council | Southern | Shoreham to Brighton Marina, East Sussex | 0 | 384 | 384 | 0 | 416 | 0 | 167645.7477 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 250 | 131028 |  | SOS004C/011A/002A
Studd Hill & Hampton Coastal Defence | Canterbury City Council | Southern | Hampton nr Herne Bay | 0 | 690 | 0 | 0 | 100 | 0 | 5655 | 2016 to 2018 | 1707 | 0 | 200 | 0 | 60 | 245 | 60 | 245 | 25455 |  | SOS003C/000A/11AA
Tankerton Coast Protection | Canterbury City Council | Southern | Tankerton near Whitstable | 0 | 20 | 0 | 0 | 0 | 0 | 1420 | 2018 to 2021 | 1300 | 0 | 100 | 0 | 0 | 465 | 0 | 465 | 33654 |  | SOS002C/004A/02CA
Whitstable Harbour Flood Defence | Canterbury City Council | Southern | Whitstable | 0 | 0 | 0 | 0 | 0 | 0 | 1360 | 2018 to 2021 | 880 | 0 | 290 | 0 | 2380 | 0 | 2380 | 0 | 173500 |  | SOS002F/006A/01CA
Selsey, Bracklesham and East Wittering Beach Management | Chichester District Council | Southern | Selsey, Bracklesham & East Wittering | 150 | 0 | 0 | 0 | 0 | 0 | 1000 | 2018 to 2021 | 0 | 0 | 50 | 0 | 120 | 15 | 595 | 80 | 32000 |  | SOS005C/009A/015A
Selsey, Bracklesham and East Wittering Beach Management (2016 - 21) | Chichester District Council | Southern | Selsey, Bracklesham & East Wittering | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2016 to 2018 | 750 | 0 | 250 | 0 | 475 | 65 | 595 | 80 | 32000 |  | SOS005C/009A/30CA
Walmer to Kingsdown Timber Groyne Replacement | Dover DC | Southern | Walmer & Kingsdown | 0 | 0 | 0 | 0 | 0 | 0 | 5437 | 2016 to 2018 | 1843 | 0 | 100 | 0 | 65 | 130 | 65 | 130 | 43962 |  | SOS001C/006A/027B
Candover Brook Flood Alleviation | Hampshire CC | Southern | Preston and Brown Candover | 0 | 15 | 0 | 0 | 20 | 0 | 345 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 802.32 |  | SOC010F/000A/007A
Monks Brook (Chandler's Ford) Flood Alleviation | Hampshire CC | Southern | Monks Brook Catchment, Chandlers Ford | 0 | 39 | 0 | 0 | 0 | 0 | 635 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 2801 |  | SOC010F/000A/001A
Romsey Flood Alleviation | Hampshire CC | Southern | Romsey, Tadburn Lake, Fairbourne Stream, River Test Catchments | 0 | 95 | 360 | 20 | 0 | 0 | 3220 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 1270 | 0 | 22609.028 |  | SOC010E/003A/006A
Upper Test Villages (Deane and Cole Henley) Flood Alleviation | Hampshire CC | Southern | Deane and Cole Henley | 0 | 10 | 0 | 0 | 10 | 0 | 220 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 917.447 |  | SOC010F/000A/008A
Hastings Coastal Defence - Stage 2 (Pier to Harbour Arm) | Hastings Borough Council | Southern | Hastings, Pier to Harbour Arm | 0 | 1470 | 0 | 0 | 30 | 0 | 11260 | 2016 to 2018 | 1345 | 0 | 60 | 0 | 50 | 0 | 50 | 0 | 19860 |  | SOS003F/006A/02AA
Totland Bay Seawall | Isle of Wight Council | Southern | Totland Bay | 0 | 0 | 0 | 0 | 0 | 0 | 2125 | 2018 to 2021 | 725 | 0 | 1400 | 0 | 0 | 105 | 0 | 105 | 2975 |  | SOS006C/000A/06SA
Church Street, Deal Flood Alleviation | Kent CC | Southern | Deal, Kent | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 2018 to 2021 | 179 | 21 | 0 | 0 | 40 | 0 | 40 | 0 | 1590.094 |  | SOO001F/000A/059A
Dover Flood Alleviation | Kent CC | Southern | Dover, Kent | 0 | 150 | 0 | 0 | 0 | 0 | 10260 | 2018 to 2021 | 3500 | 0 | 0 | 0 | 0 | 0 | 2240 | 0 | 45298.482 |  | SOO001F/000A/058A
Edenbridge Flood Alleviation | Kent CC | Southern | Edenbridge, Kent | 30 | 0 | 0 | 0 | 0 | 0 | 110 | 2016 to 2018 | 50 | 0 | 0 | 0 | 220 | 0 | 220 | 0 | 3732.906 |  | SOO001F/000A/057A
Hythe Flood Alleviation | Kent CC | Southern | Hythe | 0 | 50 | 0 | 0 | 0 | 0 | 1535 | 2018 to 2021 | 450 | 0 | 0 | 0 | 590 | 0 | 590 | 0 | 6270.471 |  | SOS003F/000A/010A
Margate Flood Alleviation | Kent CC | Southern | Margate, Kent | 0 | 100 | 0 | 0 | 0 | 0 | 1190 | 2018 to 2021 | 1000 | 0 | 0 | 0 | 355 | 0 | 355 | 0 | 7794.412 |  | SOO001F/000A/055A
Paddock Wood Flood Alleviation | Kent CC | Southern | Paddock Wood, Kent | 0 | 10 | 0 | 40 | 0 | 0 | 1130 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 5773.01 |  | SOC003E/000A/010B
Whistable Flood Alleviation | Kent CC | Southern | Whitstabe, Kent | 0 | 100 | 0 | 0 | 0 | 0 | 1128 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 0 | 6477.571 |  | SOO004F/000A/017A
Fairlight Cove Coast Protection Stage 3 | Rother DC | Southern | The cliffs below Cliff Way, Sea Road & Rockmead Road, Fairlight Cove, East Sussex | 26 | 0 | 0 | 0 | 4 | 0 | 2396 | 2018 to 2021 | 1634 | 0 | 150 | 0 | 0 | 150 | 0 | 150 | 28546 |  | SOC999/000/127A
River Itchen (West Bank) Flood Alleviation | Southampton City Council | Southern | Southampton | 200 | 600 | 0 | 0 | 0 | 0 | 10707 | 2016 to 2018 | 6657 | 0 | 3000 | 0 | 860 | 0 | 860 | 0 | 121796.5 |  | SOS005C/000B/002A
Rolles Brook (Southampton) Flood Alleviation | Southampton City Council | Southern | Southampton, Rolles Brook | 0 | 0 | 0 | 80 | 0 | 0 | 705 | 2016 to 2018 | 454 | 136 | 0 | 0 | 160 | 0 | 160 | 0 | 1650 |  | SOC010F/000A/003A
Tanners Brook/Holly Brook (Southampton) Flood Alleviation | Southampton City Council | Southern | Southampton, Tanners Brook | 0 | 40 | 0 | 100 | 0 | 0 | 1200 | 2016 to 2018 | 1000 | 0 | 0 | 0 | 320 | 0 | 320 | 0 | 3917 |  | SOC010F/000A/004A
East of Epple to Westgate Bay - Sea Wall Refacing | Thanet District Council | Southern | Westgate on Sea, Kent | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 2016 to 2018 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1669 |  | SOS002C/000A/06CA
Cannon Brook & Mad Bess Brook Flood Management | Environment Agency | Thames | Cannon Brook, Mad Bess Brook & Ruislip Lido | 0 | 60 | 0 | 0 | 0 | 0 | 630 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 0 | 620 |  | THC024E/000A/017A
Houghton Regis Flood Storage Area | Environment Agency | Thames | Houghton Regis to Luton Hoo Lakes | 25 | 50.914 | 0 | 0 | 124.086 | 0 | 2586.358 | 2016 to 2018 | 2100 | 0 | 0 | 0 | 245 | 0 | 245 | 0 | 36901.465 |  | THC034E/001B/001A
Lewisham and Catford Flood Alleviation | Environment Agency | Thames | Lewisham and Catford on the River Ravensbourne | 0 | 0 | 0 | 310.5 | 0 | 0 | 17062.155 | 2018 to 2021 | 9920.242 | 2871.0365 | 3181.5365 | 0 | 835 | 0 | 835 | 0 | 220837.9905 |  | THC022E/000A/021A
Oxford Flood Alleviation Scheme | Environment Agency | Thames | Oxford | 100 | 1543.7469 | 0 | 3600 | 6000 | 0 | 126903.4849 | 2018 to 2021 | 40842.963 | 10300 | 45720 | 0 | 3810 | 0 | 7615 | 0 | 770596.75 |  | THC040E/001A/007A
River Thames Scheme (Datchet to Teddington) | Environment Agency | Thames | Datchet - Teddington | 5400 |  |  | 600 | 1000 | 500 | 302000 | 2018 to 2021 | 68200 | 15500 | 0 | 20800 | 0 | 0 | 12790 | 0 | 1393600 |  | THC038E/001A/001A
Shonks Mill - Works from River Roding Flood Risk Management Strategy | Environment Agency | Thames | Shonks Mill Bridge and Woodford, Redbridge | 4.075 | 14.997 | 0 | 115.465 | 115.465 | 0 | 3405.038 | 2021 on | 130.036 | 1500 | 1500 | 0 | 0 | 0 | 1500 | 0 | 168602 |  | THC029E/001A/002A
Surbiton Stream Flood Alleviation | Environment Agency | Thames | Surbiton Stream (Surbiton, Kingston upon Thames) | 0 | 300 | 0 | 0 | 0 | 23 | 1823 | 2018 to 2021 | 500 | 0 | 0 | 1000 | 0 | 0 | 235 | 0 | 1260.071 |  | THC020E/000A/008A
Wealdstone Brook Flood Alleviation | Environment Agency | Thames | Wealdstone Brook | 30 | 0 | 0 | 0 | 30 | 0 | 2720 | 2018 to 2021 | 100 | 2520 | 0 | 0 | 690 | 0 | 690 | 0 | 1475 |  | THC024E/001A/003A
Hughenden Road and Coates Lane, High Wycombe Surface Water Management | Buckinghamshire County Council | Thames | Hughenden Road and Coates Lane, High Wycombe | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2016 to 2018 | 14.158 | 17.842 | 8 | 0 | 10 | 0 | 10 | 0 | 193.624 |  | THC018E/000A/013A
Pednormead End, Brushwood Road and Harding Road (Surface Water) | Buckinghamshire County Council | Thames | Pednormead End, Brushwood Road and Harding Road, Chesham | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 85 | 0 | 65 | 0 | 35 | 0 | 35 | 0 | 538.364 |  | THO999F/030A/017A
Buckskin Lane Flood Aleviation, Basingstoke | Hampshire CC | Thames | Buckskin, Basingstoke | 0 | 30 | 0 | 0 | 0 | 0 | 2290 | 2018 to 2021 | 2060 | 0 | 190 | 0 | 175 | 0 | 175 | 0 | 50146.75 |  | THC004E/000A/002A
Middleton Gardens Flood Alleviation | Hampshire CC | Thames | Middleton Gardens, Rushmoor. South of Hawley Lake Stream | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 2018 to 2021 | 194 | 0 | 66 | 0 | 15 | 0 | 15 | 0 | 1839.57 |  | THC003E/000A/008A
Phoenix Green, Flood Alleviation Study | Hampshire CC | Thames | Phoenix Green, Hampshire | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 2016 to 2018 | 205 | 0 | 40 | 0 | 10 | 0 | 10 | 0 | 541.592 |  | THO999F/015A/002A
Rectory Road Flood Alleviation | Hampshire CC | Thames | Farnborough | 0 | 0 | 0 | 0 | 0 | 0 | 209.7 | 2016 to 2018 | 140 | 0 | 6 | 0 | 10 | 0 | 10 | 0 | 3102 |  | THO999F/033A/002A
Sycamore Road Flood Alleviation | Hampshire CC | Thames | Farnborough | 0 | 0 | 0 | 0 | 0 | 0 | 304 | 2016 to 2018 | 235 | 0 | 6 | 0 | 10 | 0 | 10 | 0 | 4514 |  | THO999F/033A/003A
Caterham Bourne Flood alleviation | London Borough of Croydon | Thames | Caterham Bourne watercourse, which rises in Caterham, Surrey and flows through whyteleafe, the Kenley and Purley in Croydon | 70 | 80 | 0 | 0 | 0 | 0 | 1145 | 2018 to 2021 | 820 | 0 | 100 | 0 | 0 | 0 | 210 | 0 | 18238.4803 |  | THC032E/000A/011A
Amhurst Road Dalston Lane Surface Water Flood Alleviation - Hackney | London Borough of Hackney | Thames | Dalston | 0 | 60 | 0 | 0 | 0 | 0 | 879.3 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 0 | 6040 |  | THO999F/044A/001A
Hackney Wick Surface Water Flood Alleviation - Hackney | London Borough of Hackney | Thames | Hackney Wick | 0 | 82 | 0 | 0 | 0 | 0 | 1934 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 7066 |  | THO999F/044A/003A
Larkspur Close Tottenham Surface Water - Haringey | London Borough of Hackney | Thames | Tottenham | 0 | 10 | 0 | 0 | 0 | 0 | 500 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 1000 |  | THO999F/013A/002A
Clayhall Flood Alleviation | London Borough of Redbridge | Thames | Clayhall, Redbrige | 0 | 125 | 0 | 0 | 0 | 0 | 996 | TBC | 0 | 0 | 0 | 0 | 235 | 0 | 235 | 0 | 217.3005 |  | THO999F/024A/010A
Loxford Water Seven Kings Surface Water Alleviation - Redbridge | London Borough of Redbridge | Thames | Ilford | 0 | 20 | 40 | 0 | 0 | 0 | 430 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 7983 |  | THO999F/024A/007A
Mayes Brook Surface Water Flood Alleviation, Redbridge | London Borough of Redbridge | Thames | Ilford | 0 | 40 | 0 | 0 | 0 | 0 | 410 | 2021 on | 45 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 11131 |  | THO999F/024A/008A
Central Camberwell Flood Alleviation | London Borough of Southwark | Thames | Camberwell, London Borough of Southwark | 0 | 58 | 50 | 0 | 50 | 0 | 1307 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 1894.53 |  | THO999F/027A/009A
Covingham & Nythe Flood Alleviation | Swindon BC | Thames | Covingham and Nythe | 0 | 50 | 0 | 0 | 0 | 0 | 550 | 2016 to 2018 | 350 | 0 | 150 | 0 | 80 | 0 | 80 | 0 | 5870 |  | THC001E/000A/013A
Wanborough Flood Mitigation | Swindon Borough Council | Thames | Wanborough, east Swindon | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 2016 to 2018 | 240 | 0 | 120 | 0 | 10 | 0 | 10 | 0 | 2229 |  | THO999F/006A/019A
Boxford Flood Alleviation | West Berkshire Council | Thames | Boxford | 0 | 5 | 0 | 0 | 0 | 0 | 585.5 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 280 |  | THO999F/011A/021A
Dunstan Green | West Berkshire Council | Thames | Town | 0 | 0 | 0 | 0 | 0 | 0 | 1946.9994 | 2016 to 2018 | 806.283 | 922.717 | 13 | 0 | 185 | 0 | 185 | 0 | 7753 |  | THO999F/011A/011A
Grazeley Green | West Berkshire Council | Thames | Village | 0 | 0 | 0 | 0 | 50 | 0 | 524 | 2018 to 2021 | 7 | 363 | 13 | 0 | 20 | 0 | 20 | 0 | 352 |  | THO999F/011A/020A
Lambourn Surface Water Management | West Berkshire Council | Thames | Lambourn | 0 | 33.5 | 0 | 0 | 0 | 0 | 680.322 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 4537 |  | THO999F/011A/019A
Newbury & Thatcham Property Level Protection | West Berkshire Council | Thames | Newbury & Thatcham, West Berkshire | 0 | 100.3 | 0 | 0 | 17.7 | 0 | 708 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 138.794 |  | THC007E/000A/016A
Boundary Brook / Stapleford | Environment Agency | Trent | Trowell and Stapleford, Nottinghamshire | 0 | 0 | 0 | 0 | 0 | 0 | 1488 | 2021 on | 350 | 0 | 0 | 0 | 0 | 0 | 340 | 0 | 3316.203 |  | TRC003E/000A154A
Calthorpe (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 53.509 | 0 | 0 | 297.448 | 0 | 2609.336 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 6031 |  | TRC003E/000A/060A
Cocker Beck, Lowdham, Flood Alleviation | Environment Agency | Trent | Lowdham, Nottinghamshire, Cocker Beck | 0 | 50 | 0 | 50 | 0 | 0 | 2300 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 4969.51 |  | TRC003E/000A164A
Day Brook, Old Basford, Flood Alleviation | Environment Agency | Trent | Old Basford, Nottingham | 0 | 0 | 0 | 0 | 0 | 0 | 2350 | 2021 on | 245.108 | 30 | 312.392 | 0 | 0 | 0 | 230 | 0 | 842.754 |  | TRC003E/000A163A
Greythorne Dyke Pumping Station Refurbishment | Environment Agency | Trent | West Bridgford, Nottinghamshire | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 2016 to 2018 | 50 | 0 | 150 | 0 | 80 | 0 | 80 | 0 | 0 |  | TRC003E/000A198A
Gunthorpe, River Trent Flood Defence | Environment Agency | Trent | Gunthorpe, Nottinghamshire | 0 | 50 | 0 | 50 | 0 | 0 | 1200 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 848.608 |  | TRC003E/000A165A
Isle of Axholme, Candy Farm Pumping Station Improvements | Environment Agency | Trent | Isle of Axholme | 0 | 0 | 0 | 0 | 0 | 0 | 1185.01 | 2016 to 2018 | 510 | 525.01 | 0 | 0 | 90 | 0 | 90 | 0 | 8.615 |  | TRC002E/000A/006A
Kings Norton (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 18.6 | 0 | 0 | 98 | 0 | 784.263 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 61 |  | TRC003E/000A/061A
Northfield (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 29.762 | 0 | 0 | 26.114 | 0 | 365.917 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 2009 |  | TRC003E/000A/062A
Rising Brook, Rugeley, Town Centre Flood Alleviation | Environment Agency | Trent | Rugeley, Staffordshire | 0 | 0 | 0 | 0 | 70 | 0 | 1500 | 2016 to 2018 | 800 | 0 | 630 | 0 | 75 | 0 | 75 | 0 | 9545 |  | TRC003E/000A/518A
River Soar Flood Risk Management | Environment Agency | Trent | Leicester, Leicestershire | 0 | 378 | 0 | 0 | 250 | 0 | 6906 | 2018 to 2021 | 4278 | 0 | 2000 | 0 | 1660 | 0 | 1660 | 0 | 29980.2 | Time Constrained Contribution | TRC003E/000A167A
Sandyford Brook, Stafford, Intergated Model | Environment Agency | Trent | Stafford | 0 | 25 | 0 | 25 | 30 | 0 | 3107 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 7824 |  | TRC003F/000A/001A
Selly Park North (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 131 | 0 | 0 | 122 | 0 | 1690.584 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 0 | 3369 |  | TRC003E/000A/056A
Stonehouse Brook (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 60.3 | 0 | 0 | 81.7 | 0 | 947.059 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 0 | 216 |  | TRC003E/000A/058A
The Bourn (River Rea) Flood Alleviation | Environment Agency | Trent | River Rea, Birmingham | 0 | 94.392 | 0 | 0 | 495.554 | 0 | 3932.434 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 792 |  | TRC003E/000A/059A
Willow Brook Flood Alleviation | Environment Agency | Trent | Belgrave, Leicester, Willow Brook | 0 | 1032 | 0 | 0 | 0 | 0 | 11352 | 2018 to 2021 | 9320 | 0 | 1000 | 0 | 3410 | 0 | 3410 | 0 | 60803.839 | Time Constrained Contribution | TRC003E/000A166A
Retford Beck, Grove Lane and Blackstope Lane, Flood Mitigation | Bassetlaw District | Trent | Retford, Retford Beck | 0 | 0 | 0 | 0 | 0 | 0 | 989 | 2021 on | 118 | 7 | 100 | 0 | 0 | 0 | 110 | 0 | 2.019 |  | TRC003F/000A/033A
Smeath Lane, Clarborough - Culvert Replacement | Bassetlaw District | Trent | Clarborough, Bassetlaw District, Notts | 0 | 0 | 0 | 0 | 25 | 0 | 336 | 2018 to 2021 | 119 | 35 | 157 | 0 | 25 | 0 | 25 | 0 | 956 |  | TRC003F/000A/078A
Fisher Close Community Protection | Birmingham City Council | Trent | Frankley, Birmingham | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2018 to 2021 | 35 | 0 | 5 | 0 | 15 | 0 | 15 | 0 | 37.773 |  | TRC003F/000A/122A
Lodge Hill, Birmingham, Flood Alleviation | Birmingham City Council | Trent | Birmingham | 0 | 0 | 0 | 0 | 0 | 0 | 446 | 2016 to 2018 | 128 | 100 | 218 | 0 | 20 | 0 | 20 | 0 | 133 |  | TRC003F/000A/064A
Pensby Close Community Protection | Birmingham City Council | Trent | Springfield, Birmingham | 61.5 | 0 | 0 | 0 | 0 | 0 | 70.5 | 2016 to 2018 | 0 | 0 | 9 | 0 | 5 | 0 | 5 | 0 | 136.896 |  | TRC003F/000A/118A
Sparkhill, Birmingham, River Cole, Community Protection | Birmingham City Council | Trent | Birmingham | 0 | 20 | 0 | 0 | 0 | 0 | 854 | 2016 to 2018 | 392 | 379 | 25 | 0 | 70 | 0 | 70 | 0 | 77 |  | TRC003F/000A/065A
Bramble Brook, Slack Lane and Great Northern Road Culverts | Derby City Council | Trent | Bramble Brook, Derby | 0 | 61.463 | 0 | 0 | 30 | 0 | 790.463 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0 | 2097.0393 |  | TRC003F/000A/096A
Cotton Brook (Upper) Culvert Renewal in Peartree Road area | Derby City Council | Trent | Cotton Brook, Derby | 0 | 129.375 | 0 | 0 | 25.875 | 0 | 1585.628 | 2018 to 2021 | 1306.055 | 0 | 124.323 | 0 | 175 | 0 | 175 | 0 | 15722.5922 |  | TRC003F/000A/093A
Cuttle Brook, Increased catchment storage | Derby City Council | Trent | Cuttle Brook, Derby | 0 | 57.376 | 0 | 0 | 28.688 | 0 | 551.7228 | 2018 to 2021 | 318.8898 | 25 | 121.769 | 0 | 110 | 0 | 110 | 0 | 15518.8443 |  | TRC003F/000A/086A
River Torne trib, Rossington, Flood Alleviation Study | Doncaster MBC | Trent | Doncaster | 0 | 0 | 0 | 0 | 0 | 0 | 145.3 | 2018 to 2021 | 135.3 | 0 | 0 | 0 | 45 | 0 | 45 | 0 | 0.108 |  | TRC003F/000A/045A
Dam Brook, Breadsall, Flood Alleviation | Erewash District (B) | Trent | Breadsall, Dam Brook and Boosemoor Brook | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 2016 to 2018 | 25 | 30 | 28 | 0 | 10 | 0 | 10 | 0 | 0.274 |  | TRC003F/000A/043A
Ferry Drain, South Street Pumping Refurbishment | Isle of Axholme and North Notts Water Level MB | Trent | Epworth, Doncaster | 0 | 11 | 0 | 0 | 14 | 0 | 239 | 2016 to 2018 | 133 | 0 | 81 | 0 | 65 | 0 | 65 | 0 | 4.862 |  | TRC002I/000A/006A
Heckdyke, 3 Bridges and 4 Bridges Pumping Station Refurbishment | Isle of Axholme and North Notts Water Level MB | Trent | Heckdyke, Doncaster | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 2018 to 2021 | 65 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 2.782 |  | TRC002I/000A/004A
Skyers Drain, Greenholme Pumping Station Refurbishment | Isle of Axholme and North Notts Water Level MB | Trent | Epworth, Doncaster | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 2018 to 2021 | 100 | 0 | 120 | 0 | 35 | 0 | 35 | 0 | 2.36 |  | TRC002I/000A/002A
Long Whatton and Diseworth Flood | Leicestershire CC | Trent | Long Whatton and Diseworth, North West Leicestershire on the Long Whatton and Diseworth Brook | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 2018 to 2021 | 110 | 0 | 20 | 0 | 30 | 0 | 30 | 0 | 770 |  | TRC003F/000A/114A
Carr Lane Dyke, Parklands Estate, West Butterwick | North Lincolnshire Council | Trent | Carr Lane Dyke, West Butterwick | 15 | 0 | 0 | 0 | 0 | 0 | 72 | TBC | 0 | 13 | 37 | 0 | 10 | 0 | 10 | 0 | 0.243 |  | TRC003F/000A/052A
Broxtowe Park Brook : Capital Maintenance and Flood Risk Management | Nottingham City Council | Trent | Nuthall / Stockhill, Nottingham | 0 | 60 | 30 | 10 | 20 | 0 | 1129 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 1255 |  | TRC003F/000A/074A
Daron Gardens / Edern Gardens, Top Valley | Nottingham City Council | Trent | Top Valley, Nottingham (no watercourse, surface water management scheme) | 0 | 0 | 0 | 0 | 0 | 0 | 419 | 2018 to 2021 | 229 | 65 | 95 | 0 | 35 | 0 | 35 | 0 | 232.5 |  | TRC003F/000A/080A
Mapperley Park Surface Water Management | Nottingham City Council | Trent | Mapperley Park, Nottingham | 0 | 40 | 0 | 0 | 0 | 0 | 989 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 2902 |  | TRC003F/000A/076A
River Leen Bobbers Mill Flood Alleviation | Nottingham City Council | Trent | Bobbers Mill, Nottingham | 0 | 50 | 0 | 0 | 0 | 0 | 2699 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 359 |  | TRC003F/000A/092A
Tottle Brook Flood Alleviation | Nottingham City Council | Trent | Wollaton, Nottingham | 0 | 30 | 0 | 10 | 10 | 0 | 799 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 400 |  | TRC003F/000A/083A
Woolsington Close, Strelley: Surface Water Management | Nottingham City Council | Trent | Strelley, Nottingham | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 2016 to 2018 | 133 | 48 | 38 | 0 | 15 | 0 | 15 | 0 | 140 |  | TRC003F/000A/073A
Hucknall Titchfield Park Brook | Nottinghamshire CC | Trent | Hucknall, Titchfield Park Brook | 0 | 0 | 0 | 0 | 20 | 0 | 500 | 2018 to 2021 | 375 | 0 | 105 | 0 | 90 | 0 | 90 | 0 | 1743.2183 |  | TRC003F/000A/098A
Southwell Flood Alleviation | Nottinghamshire CC | Trent | Southwell, Potwell Dyke, Halam Hill Watercourse | 0 | 0 | 0 | 0 | 20 | 0 | 1675 | 2016 to 2018 | 720 | 300 | 635 | 0 | 235 | 0 | 235 | 0 | 3404.6327 |  | TRC003F/000A/081A
Blyton Warping Drain, Ravensfleet Pumping Station Refurbishment | Scunthorpe and Gainsborough WMB | Trent | East Stockwith, Gainsborough | 0 | 0 | 0 | 0 | 0 | 0 | 573 | 2016 to 2018 | 323 | 0 | 250 | 0 | 60 | 0 | 60 | 0 | 13.797 |  | TRC003I/000A/002A
Jenny Hurn Drain, Jenny Hurn Pumping Station Refurbishment | Scunthorpe and Gainsborough WMB | Trent | Wildsworth, Gainsborough | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 2018 to 2021 | 79 | 0 | 181 | 0 | 85 | 0 | 85 | 0 | 4.02 |  | TRC003I/000A/001A
Jenny Hurn Drain, Whoofer Pumping Station Refurbishment | Scunthorpe and Gainsborough WMB | Trent | Wildsworth, Gainsborough | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 2018 to 2021 | 10 | 0 | 57 | 0 | 5 | 0 | 5 | 0 | 1.114 |  | TRC003I/000A/004A
South Ings Drain, Susworth Pumping Station Refurbishment | Scunthorpe and Gainsborough WMB | Trent | Susworth, Scunthorpe | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2018 to 2021 | 42 | 0 | 108 | 0 | 45 | 0 | 45 | 0 | 2.95 |  | TRC003I/000A/003A
Acacia crescent, Bilbrook | Staffordshire County Council | Trent | Bilbrook, Staffordshire | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2018 to 2021 | 4 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 13.252 |  | TRC003F/000A/125A
Brown Edge Flood Alleviation | Staffordshire County Council | Trent | Brown Edge, Staffordshire Moorlands | 0 | 10 | 0 | 0 | 4 | 0 | 94 | 2018 to 2021 | 80 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 564.008 |  | TRC003F/000A/088A
Dunston, River Penk, Property Level Protection | Staffordshire County Council | Trent | Dunston | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 2018 to 2021 | 8 | 14 | 1 | 0 | 5 | 0 | 5 | 0 | 67 |  | TRC003F/000A/032A
Endon Flood Alleviation | Staffordshire County Council | Trent | Endon, Staffordshire Moorlands | 0 | 22 | 0 | 0 | 0 | 0 | 172 | 2021 on | 138 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1131.362 |  | TRC003E/000A155A
Hamstall Ridware Flood Alleviation | Staffordshire County Council | Trent | Hamstall Ridware | 0 | 0 | 0 | 0 | 0 | 0 | 75.3 | 2021 on | 5 | 3 | 0 | 0 | 0 | 0 | 10 | 0 | 114.51 |  | TRC003F/000A/095A
Hobnock Road Property Level Protection | Staffordshire County Council | Trent | Essington | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 12 | 1.5 | 1.5 | 0 | 5 | 0 | 5 | 0 | 75 |  | TRC003E/000A157A
Lower Penn Flood Alleviation | Staffordshire County Council | Trent | Lower Penn, near Smestow Brook | 0 | 2 | 0 | 2 | 0 | 0 | 90 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 91.374 |  | TRC003F/000A/102A
Norton Lane Property Level Protection | Staffordshire County Council | Trent | Great Wyrley | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 12 | 1.5 | 1.5 | 0 | 5 | 0 | 5 | 0 | 75 |  | TRC003E/000A158A
Rollestone on Dove, Surface Water Flood Alleviation | Staffordshire County Council | Trent | Rollestone on Dove | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 2016 to 2018 | 38 | 112 | 0 | 0 | 15 | 0 | 15 | 0 | 273 |  | TRC003F/000A/056A
Upper Longdon PLP | Staffordshire County Council | Trent | Upper Longdon | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2018 to 2021 | 4 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 24 |  | TRC003F/000A/079A
Village Brook (Endon) Flood Alleviation | Staffordshire County Council | Trent | Village Brook , Endon | 0 | 22 | 0 | 0 | 0 | 0 | 171 | 2018 to 2021 | 112 | 25 | 12 | 0 | 0 | 0 | 60 | 0 | 1131.362 |  | TRC003F/000A/087A
Cuckstool Dyke, Sutton-on-Trent Improvements | Trent Valley IDB | Trent | Sutton-on-Trent, Newark | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 2016 to 2018 | 33 | 0 | 62 | 0 | 45 | 0 | 45 | 0 | 0.482 |  | TRC003I/000A/008A
Marton Pumping Station Refurbishment | Trent Valley IDB | Trent | Marton , Gainsborough | 0 | 0 | 0 | 0 | 35 | 0 | 412 | 2018 to 2021 | 305 | 0 | 72 | 0 | 55 | 0 | 55 | 0 | 6842 |  | TRC002I/000A/008A
Sewer Drain, Torksey Pumping Sation Replacement | Trent Valley IDB | Trent | Torksey, Lincoln | 0 | 0 | 0 | 0 | 12.5 | 0 | 749 | 2016 to 2018 | 500 | 0 | 224 | 0 | 480 | 0 | 480 | 0 | 18.356 |  | TRC003I/000A/009A
Whitacre Heath | Warwickshire CC | Trent | Whiteacre Heath, River Tame | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 2018 to 2021 | 35 | 12 | 30 | 0 | 0 | 0 | 10 | 0 | 225 |  | TRC003F/000A/127A
Parrett Barrier Site Investigation | Environment Agency | Wessex | Chilton Tinity, Bridgwater | 100 | 150 | 0 | 0 | 70 | 0 | 25176 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 0 | 131024.431 |  | WXC007E/000A/211A
Stolford Flood Defence | Environment Agency | Wessex | Stolford | 36 | 0 | 0 | 0 | 0 | 0 | 595 | 2016 to 2018 | 217 | 166 | 30 | 0 | 20 | 0 | 20 | 0 | 4775 |  | WXC008E/000A/032a
Creekmoor Flood Defences | Borough of Poole | Wessex | Creekmoor, Poole | 0 | 100 | 0 | 0 | 0 | 0 | 1588 | 2018 to 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 20086.5 |  | WXS001F/000A/037A
Bournemouth Beach Management Phase 2 | Bournemouth Borough Council | Wessex | Bournemouth | 0 | 0 | 0 | 0 | 0 | 0 | 11022.667 | TBC | 4576.381 | 400 | 1870.286 | 0 | 0 | 0 | 0 | 2595 | 474825.89 |  | WXS001C/000A/034A
Bristol City, Surface Water Management, Southmead Site | Bristol City Council | Wessex | Bristol | 15 | 0 | 0 | 0 | 0 | 0 | 92.55 | 2018 to 2021 | 65.35 | 0 | 12.2 | 0 | 35 | 0 | 35 | 0 | 337.17 |  | WXC005F/000A/120A
Clevedon Sea Wall Capital Maintenance | North Somerset Council | Wessex | Clevedon | 0 | 0 | 0 | 0 | 60 | 0 | 620 | 2016 to 2018 | 520 | 0 | 40 | 0 | 0 | 60 | 0 | 60 | 7372 |  | WXC006F/000A/159A
Taunton flood alleviation improvements | Taunton Deane Borough Council (TDBC) | Wessex | River Tone in Taunton and Bradford-on-Tone | 0 | 75 | 75 | 0 | 675 | 0 | 11282 | 2021 on | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 4483.1 |  | WXC007E/000A/218A
Weymouth Bay Coastal Defences | Weymouth & Portland BC | Wessex | Weymouth | 0 | 250 | 0 | 250 | 555 | 0 | 7055 | 2016 to 2018 | 1950 | 750 | 3005 | 0 | 445 | 0 | 445 | 0 | 9770 |  | WXS002E/000A/071A
Chitterne Attenuation of Surface Water | Wiltshire Council | Wessex | Chitterne, Wiltshire, BA12 | 95 | 0 | 0 | 35 | 40 | 0 | 170 | 2016 to 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1514.622 |  | WXC005F/000A/164A
Orcheston Surface Water Attenuation | Wiltshire Council | Wessex | Orcheston, Wiltshire, SP3 | 25 | 0 | 0 | 10 | 50 | 0 | 85 | 2016 to 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1067.314 |  | WXC005F/000A/165A
Tilshead Surface Water Attenuation | Wiltshire Council | Wessex | Tilshead, Salisbury, SP3 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 2016 to 2018 | 148 | 40 | 47 | 0 | 0 | 0 | 0 | 0 | 2088.758 |  | WXC005F/000A/166A
Bentley Pumping Station Replacement | Environment Agency | Yorkshire | Bentley, North Swaith Dike | 75 | 0 | 0 | 0 | 0 | 0 | 2100 | 2021 on | 525 | 0 | 1500 | 0 | 425 | 0 | 425 | 0 | 22.5672 |  | YOC356E/000A/063A
Clifton Ings and Rawcliffe Meadows Barrier Bank | Environment Agency | Yorkshire | York, River Ouse | 0 | 120 | 0 | 0 | 0 | 0 | 1513 | 2016 to 2018 | 1380 | 0 | 13 | 0 | 300 | 0 | 300 | 0 | 8229.325 |  | YOC353E/000A/058A
East Hull (Bransholme) Flood Alleviation | Environment Agency | Yorkshire | East Hull | 25 | 25 | 0 | 0 | 0 | 0 | 10075 | 2021 on | 6952 | 0 | 2640 | 0 | 1260 | 0 | 1260 | 0 | 3867 |  | YOO000E/000A/058A
Great Culvert Pumping Station Refurbishment | Environment Agency | Yorkshire | Bransholme, Foredyke Stream | 25 | 25 | 0 | 0 | 0 | 0 | 1358 | 2021 on | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3867 |  | YOC357E/001A/005A
Hebble Brook Culverts Repairs | Environment Agency | Yorkshire | Halifax, Hebble Brook | 0 | 0 | 0 | 0 | 0 | 0 | 335 | TBC | 24 | 0 | 311 | 0 | 1 | 0 | 1 | 0 | 146.44 |  | YOC355E/000A/096A
Hebden Bridge Flood Alleviation | Environment Agency | Yorkshire | Hebden Bridge, West Yorkshire | 300 | 0 | 0 | 50 | 0 | 0 | 5200 | 2016 to 2018 | 668 | 1082 | 2900 | 0 | 235 | 0 | 235 | 0 | 3706.8 |  | YOC355E/001A/002A
Mytholmroyd Flood Alleviation | Environment Agency | Yorkshire | Mytholmroyd | 0 | 0 | 0 | 80 | 0 | 0 | 3740 | 2016 to 2018 | 1000 | 860 | 1740 | 0 | 340 | 0 | 340 | 0 | 2769.9 |  | YOC355E/000A/029A
Main Foss Channel Improvements | Ainsty 2008 IDB | Yorkshire | Willowgarth,Poppleton York | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 2016 to 2018 | 18 | 0 | 17 | 0 | 50 | 0 | 50 | 0 | 255 |  | YOC353I/000A/047A
Aldham Bridge - River Dove Upstream Improvements | Barnsley MBC | Yorkshire | Barnsley MBC | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 32 | 0 | 68 | 0 | 15 | 0 | 15 | 0 | 0 |  | YOC356F/000A/001A
Grimethorpe - High Street | Barnsley MBC | Yorkshire | Barnsley MBC | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2018 to 2021 | 18 | 0 | 32 | 0 | 5 | 0 | 5 | 0 | 0 |  | YOC356F/000A/071A
Hemingfield - Tingle Bridge | Barnsley MBC | Yorkshire | Barnsley MBC | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 2018 to 2021 | 3.45 | 0 | 11.55 | 0 | 5 | 0 | 5 | 0 | 9.843 |  | YOC356F/000A/003A
Hoyland - Sheffield Road | Barnsley MBC | Yorkshire | Barnsley MBC | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 2018 to 2021 | 6.9 | 0 | 23.1 | 0 | 5 | 0 | 5 | 0 | 0 |  | YOC356F/000A/004A
Wombwell Ings Flood Storage, Darfield, Barnsley | Barnsley MBC | Yorkshire | Barnsley | 200 | 0 | 0 | 0 | 0 | 0 | 745 | 2016 to 2018 | 0 | 0 | 545 | 0 | 25 | 0 | 25 | 0 | 0 |  | YOC356F/000A/030A
Old Main Drain Wawne 1 | Beverley & North Holderness IDB | Yorkshire | Old Main Drain Wawne | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 2018 to 2021 | 28 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 489.377 |  | YOC357I/000A/018A
Canker Dyke, Wistons Lane, Elland | Calderdale MBC | Yorkshire | Right bank of Canker Dyke off Wistons Lane, Elland. | 0 | 2.3 | 0 | 0 | 0 | 7.7 | 60 | TBC | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 146.44 |  | YOC355F/000A/090A
Kershaw Road, Walsden | Calderdale MBC | Yorkshire | Hillslope to the West of Walsden Water, Walsden. | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 2016 to 2018 | 85 | 0 | 315 | 0 | 5 | 0 | 5 | 0 | 679 |  | YOC355F/000A/095A
Rochdale Canal & Tributaries | Calderdale MBC | Yorkshire | Rochdale Canal between Salford and Millwood in Todmorden | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 2016 to 2018 | 210 | 100 | 100 | 0 | 205 | 0 | 205 | 0 | 1885 |  | YOC355F/000A/103A
Tapton Terrace Property Level Protection Flood Mitigation | Chesterfield | Yorkshire | Chesterfield | 0 | 0 | 0 | 0 | 0 | 0 | 181.6 | 2018 to 2021 | 160 | 0 | 21.6 | 0 | 25 | 0 | 25 | 0 | 602.081 |  | YOC356F/000A/060A
Renishaw Flood Alleviation | Derbyshire County Council | Yorkshire | Renishaw | 31 | 0 | 0 | 0 | 0 | 0 | 212.6 | 2016 to 2018 | 60 | 0 | 78.6 | 0 | 55 | 0 | 55 | 0 | 635.795 |  | YOC356F/000A/056A
Kearsley Brook Flood Alleviation | Doncaster MBC | Yorkshire | Conisbrough, Doncaster | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 2016 to 2018 | 150 | 25 | 25 | 0 | 35 | 0 | 35 | 0 | 353.6 |  | YOC356F/000A/050A
Aldbrough Seaside Road | East Riding of Yorkshire Council | Yorkshire | Aldbrough | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 2016 to 2018 | 25 | 0 | 10 | 0 | 15 | 0 | 15 | 0 | 347.341 |  | YOC357F/000A/071A
Beeford Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Beeford | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 2016 to 2018 | 200 | 50 | 50 | 0 | 160 | 0 | 160 | 0 | 3641.528 |  | YOC357F/000A/025A
Beverley Victoria Road Culvert Reinstatement | East Riding of Yorkshire Council | Yorkshire | Beverley | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2016 to 2018 | 90 | 0 | 10 | 0 | 90 | 0 | 90 | 0 | 1871.215 |  | YOC357F/000A/075A
Bubwith Culvert Connection | East Riding of Yorkshire Council | Yorkshire | Bubwith | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2016 to 2018 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 199.024 |  | YOC351F/000A/004A
Burnby Culvert | East Riding of Yorkshire Council | Yorkshire | Hayton | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 2016 to 2018 | 40 | 0 | 20 | 0 | 25 | 0 | 25 | 0 | 744.384 |  | YOC351F/000A/006A
Cherry Burton The Meadows | East Riding of Yorkshire Council | Yorkshire | Cherry Burton | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 2018 to 2021 | 90 | 70 | 70 | 0 | 140 | 0 | 140 | 0 | 3015.173 |  | YOC357F/000A/078A
Driffield Kellythorpe Groundwater | East Riding of Yorkshire Council | Yorkshire | Driffield | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2016 to 2018 | 70 | 0 | 10 | 0 | 90 | 0 | 90 | 0 | 1913.117 |  | YOC357F/000A/114A
Goole Hook Drain Culvert Improvements | East Riding of Yorkshire Council | Yorkshire | Goole | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 50 | 50 | 50 | 0 | 255 | 0 | 255 | 0 | 5564.318 |  | YOC353F/000A/003A
Keyingham North Culvert | East Riding of Yorkshire Council | Yorkshire | Keyingham | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 70 | 40 | 40 | 0 | 120 | 0 | 120 | 0 | 2566.893 |  | YOC357F/000A/089A
Kilham Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Kilham | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2016 to 2018 | 114 | 0 | 36 | 0 | 215 | 0 | 215 | 0 | 4754.571 |  | YOC357F/000A/090A
Langtoft Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Langtoft | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 2018 to 2021 | 50 | 50 | 50 | 0 | 65 | 0 | 65 | 0 | 1370.653 |  | YOC357F/000A/091A
Leven Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Leven | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 2018 to 2021 | 264.029 | 0 | 0 | 0 | 100 | 0 | 100 | 0 | 1922.239 |  | YOC357F/000A/009A
Lockington Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Lockington | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 25 | 50 | 25 | 0 | 65 | 0 | 65 | 0 | 1512.364 |  | YOC357F/000A/094A
Middleton on the Wolds Culverting | East Riding of Yorkshire Council | Yorkshire | Middleton | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 2018 to 2021 | 100 | 10 | 10 | 0 | 80 | 0 | 80 | 0 | 1988.735 |  | YOC357F/000A/096A
Minor Capital Support Year 19/20 | East Riding of Yorkshire Council | Yorkshire | Area Wide | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 776.096 |  | YOC357F/000A/097A
Minor Capital Support Year 20/21 | East Riding of Yorkshire Council | Yorkshire | Area Wide | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 776.096 |  | YOC357F/000A/098A
Minor Capital Support Year 21/22 | East Riding of Yorkshire Council | Yorkshire | Area Wide | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2021 on | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 776.096 |  | YOC357F/000A/099A
Minor Capital Support Year 22/23 | East Riding of Yorkshire Council | Yorkshire | Area Wide | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2021 on | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 776.096 |  | YOC357F/000A/100A
Minor Capital Support Year 23/24 | East Riding of Yorkshire Council | Yorkshire | Area Wide | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2021 on | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 776.096 |  | YOC357F/000A/101A
North Cave New Cut to Wetlands | East Riding of Yorkshire Council | Yorkshire | North Cave | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 2018 to 2021 | 25 | 10 | 40 | 0 | 50 | 0 | 50 | 0 | 1336.175 |  | YOC357F/000A/105A
North Ferriby Church Street | East Riding of Yorkshire Council | Yorkshire | North Ferriby | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 2016 to 2018 | 80 | 0 | 30 | 0 | 80 | 0 | 80 | 0 | 1672.191 |  | YOC357F/000A/045A
Patrington Haven Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Patrington | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 2018 to 2021 | 50 | 15 | 15 | 0 | 30 | 0 | 30 | 0 | 563.267 |  | YOC357F/000A/106A
South Cave Village Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | South Cave | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 2016 to 2018 | 600 | 100 | 100 | 0 | 410 | 0 | 410 | 0 | 8884.376 |  | YOC357F/000A/054A
Swinefleet Flood Alleviation | East Riding of Yorkshire Council | Yorkshire | Swinefleet | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 2016 to 2018 | 10 | 20 | 20 | 0 | 25 | 0 | 25 | 0 | 475.657 |  | YOC356F/000A/058A
Clayton West and Scissett Flood Alleviation | Kirklees Council | Yorkshire | Clayton West and Scissett, Kirklees, West Yorkshire | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 2018 to 2021 | 120 | 70 | 110 | 0 | 30 | 0 | 30 | 0 | 885 |  | YOC356F/000A/073A
Cleckheaton Flood Alleviation | Kirklees Council | Yorkshire | Cleckheaton, Kirklees, West Yorkshire | 0 | 0 | 0 | 90 | 10 | 0 | 1700 | 2018 to 2021 | 775 | 0 | 25 | 0 | 0 | 0 | 300 | 0 | 7315 |  | YOC355F/000A/046A
Dewsbury Flood Alleviation | Kirklees Council | Yorkshire | Dewsbury, Kirklees, West Yorkshire | 0 | 200 | 0 | 0 | 0 | 0 | 4200 | 2021 on | 1905 | 0 | 40 | 0 | 0 | 0 | 535 | 0 | 8590 |  | YOC355E/000A/010A
Holmfirth Flood Alleviation | Kirklees Council | Yorkshire | Holmfirth, Kirklees, West Yorkshire | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2021 on | 75 | 0 | 25 | 0 | 0 | 0 | 90 | 0 | 4075 |  | YOC355F/000A/057A
Huddersfield A62 Corridor Flood Alleviation | Kirklees Council | Yorkshire | A62 Corridor, north-east Huddersfield, Kirklees, West Yorkshire | 170 | 0 | 0 | 0 | 0 | 0 | 1400 | 2016 to 2018 | 1080 | 0 | 120 | 0 | 195 | 0 | 195 | 0 | 3560 |  | YOC355F/000A/036A
Ings Crescent Flood Alleviation | Kirklees Council | Yorkshire | Liversedge, Kirklees, West Yorkshire | 0 | 0 | 0 | 15 | 5 | 0 | 210 | 2018 to 2021 | 150 | 0 | 30 | 0 | 30 | 0 | 30 | 0 | 378 |  | YOC355F/000A/059A
Kirklees Culvert Programme | Kirklees Council | Yorkshire | Various - locations across Kirklees LLFA | 75 | 0 | 0 | 0 | 0 | 0 | 510 | TBC | 185 | 0 | 180 | 0 | 270 | 0 | 270 | 0 | 1351 |  | YOC355F/000A/030A
Radulf Gardens Flood Alleviation | Kirklees Council | Yorkshire | Liversedge, Kirklees, West Yorkshire | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 2018 to 2021 | 40 | 55 | 25 | 0 | 15 | 0 | 15 | 0 | 198 |  | YOC355F/000A/076A
Ravensthorpe Flood Alleviation | Kirklees Council | Yorkshire | Ravensthorpe, Kirklees, West Yorkshire | 0 | 0 | 0 | 50 | 50 | 0 | 1400 | 2018 to 2021 | 525 | 50 | 75 | 0 | 0 | 0 | 150 | 0 | 5330 |  | YOC355E/000A/068A
Cotton Mill Beck Culvert, Valley Road, Morley | Leeds City Council | Yorkshire | Valley Road, Morley. Cottonmill Beck | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 2016 to 2018 | 82 | 0 | 25 | 0 | 10 | 0 | 10 | 0 | 525 |  | YOC354F/000A/001A
Farnley Wood Beck Flood Alleviation, Cottingley, Leeds | Leeds City Council | Yorkshire | Cottingley, Leeds. Farnley Wood Beck. | 0 | 0 | 0 | 50 | 25 | 0 | 390 | 2021 on | 40 | 0 | 250 | 0 | 0 | 0 | 15 | 0 | 0 |  | YOC354F/000A/008A
Mickletown Flood Alleviation (including set back banks), Leeds | Leeds City Council | Yorkshire | Mickletown, Leeds. River Aire | 0 | 0 | 0 | 0 | 100 | 0 | 1600 | 2016 to 2018 | 400 | 0 | 1000 | 0 | 115 | 0 | 115 | 0 | 360 | Time Constrained Contribution | YOC354F/000A/033A
Thorner Beck Flood Alleviation, Thorner, Leeds | Leeds City Council | Yorkshire | Thorner, Leeds. Thorner Beck | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 2018 to 2021 | 96 | 0 | 4 | 0 | 15 | 0 | 15 | 0 | 404 |  | YOC354F/000A/002A
Wakefield Road Flood Alleviation, Garforth, Leeds | Leeds City Council | Yorkshire | Wakefield Road, Garforth, Leeds. Lin Dike Watercourse | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 2018 to 2021 | 80 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 433 |  | YOC354F/000A/005A
Holbeck Flood Risk Management Plan (Unit 15) | North Yorkshire County Council | Yorkshire | Holbeck | 0 | 0 | 0 | 0 | 0 | 0 | 539.44 | 2018 to 2021 | 459.44 | 40 | 40 | 0 | 0 | 0 | 55 | 0 | 7377.9064 |  | YOC351F/000A/014A
Malton Railway Pipe crossing | North Yorkshire County Council | Yorkshire | Malton | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 2016 to 2018 | 16 | 0 | 4 | 0 | 50 | 0 | 50 | 0 | 500 |  | YOC351F/000A/018A
Middle Hull Flood Risk Management Plan (Unit 17) | North Yorkshire County Council | Yorkshire | Middle Hull | 0 | 0 | 0 | 0 | 0 | 0 | 140.4 | 2018 to 2021 | 100.4 | 20 | 20 | 0 | 0 | 0 | 10 | 0 | 1645.4676 |  | YOC351F/000A/015A
North York Flood Risk Management Plan (Unit 26) | North Yorkshire County Council | Yorkshire | North York | 0 | 50 | 0 | 0 | 0 | 0 | 635.12 | 2021 on | 505.12 | 40 | 40 | 0 | 0 | 0 | 65 | 0 | 8829.9783 |  | YOC353F/000A/028A
Pickering & Costa Becks Flood Risk Management Plan (Unit 14) | North Yorkshire County Council | Yorkshire | Pickering & Costa Becks | 0 | 0 | 0 | 0 | 0 | 0 | 682.96 | 2018 to 2021 | 602.96 | 40 | 40 | 0 | 0 | 0 | 70 | 0 | 9556.0143 |  | YOC351F/000A/013A
River Dove Uplands Flood Risk Management Plan (Unit 11) | North Yorkshire County Council | Yorkshire | River Dove Uplands | 0 | 0 | 0 | 0 | 0 | 0 | 677.44 | 2018 to 2021 | 597.44 | 40 | 40 | 0 | 0 | 0 | 70 | 0 | 9472.2409 |  | YOC351F/000A/010A
River Seven Flood Risk Management Plan (Unit 12) | North Yorkshire County Council | Yorkshire | River Seven | 0 | 0 | 0 | 0 | 0 | 0 | 160.4 | 2018 to 2021 | 100.4 | 30 | 30 | 0 | 0 | 0 | 10 | 0 | 1625.4676 |  | YOC351F/000A/011A
Howdendyke Pumping Station Refurbishment | Ouse & Humber Drainage Board | Yorkshire | Howdendyke, Howden | 0 | 0 | 0 | 0 | 0 | 0 | 231.285 | 2016 to 2018 | 107.835 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 16952 |  | YOC357I/000A/037A
Rawcliffe Pumping Stations Refurbishment & Other Works | Rawcliffe DB | Yorkshire | Rawcliffe (River Aire and River Don) | 0 | 66.9571 | 0 | 0 | 61.0679 | 0 | 855.826 | 2021 on | 0 | 0 | 0 | 0 | 55 | 0 | 395 | 0 | 15271.2 |  | YOC356I/000A/003A
Filey Flood Alleviation | Scarborough Borough Council | Yorkshire | Filey, North Yorkshire, YO15 | 0 | 0 | 0 | 0 | 0 | 0 | 5015 | 2018 to 2021 | 2739 | 1850 | 30 | 0 | 0 | 0 | 595 | 0 | 13588 |  | YOS351F/000A/011A
Robin Hoods Bay Works | Scarborough Borough Council | Yorkshire | Robin Hoods Bay, North Yorkshire, YO22 | 0 | 0 | 0 | 0 | 0 | 0 | 1820 | 2016 to 2018 | 787 | 0 | 983 | 0 | 0 | 60 | 0 | 60 | 6993 |  | YOS351C/000A/068A
Scarborough South Bay Spa Seawall | Scarborough Borough Council | Yorkshire | Scarborough North Yorkshire, YO11 | 260 | 0 | 0 | 0 | 0 | 0 | 13760 | 2016 to 2018 | 11200 | 0 | 2300 | 0 | 0 | 380 | 0 | 380 | 100804 |  | YOS351C/000A/084A
Whitby Church Street Flood Alleviation | Scarborough Borough Council | Yorkshire | Whitby, North Yorkshire, YO21 Abbey Cliff SSSI, River Esk | 79 | 0 | 0 | 0 | 0 | 0 | 1039 | 2016 to 2018 | 653 | 0 | 61 | 0 | 55 | 0 | 55 | 0 | 5165 |  | YOS351C/000A/089A
Bond Ings Pumping Station | Selby Area Internal Drainage Board | Yorkshire | South of Sherburn in Elmet | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 2016 to 2018 | 24.75 | 0 | 30.25 | 0 | 5 | 0 | 5 | 0 | 1905 |  | YOC353I/000A/035A
Little Airmyn Pumping Station | Selby Area Internal Drainage Board | Yorkshire | Airmyn, west of Goole, River Aire | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 2018 to 2021 | 382.5 | 0 | 467.5 | 0 | 30 | 0 | 30 | 0 | 8650 |  | YOC354I/000A/003A
Sheaf Catchment Flood Alleviation | Sheffield City Council | Yorkshire | Sheffield/River Sheaf, Porter Brook | 0 | 600 | 0 | 150 | 500 | 0 | 12350 | 2018 to 2021 | 7250 | 0 | 3600 | 0 | 625 | 0 | 625 | 0 | 254526.0764 |  | YOC356E/000A/048A
Sheffield Upper Don Flood Alleviation | Sheffield City Council | Yorkshire | Sheffield/Upper River Don, River Loxley | 0 | 600 | 0 | 200 | 400 | 0 | 11900 | 2018 to 2021 | 6550 | 0 | 3800 | 0 | 1320 | 0 | 1320 | 0 | 261822.6405 |  | YOC356F/000A/086A
Sheffield Watercourses - Culvert Renewal Programme | Sheffield City Council | Yorkshire | Sheffield, South Yorkshire/Critical Watercourse Culverts | 0 | 200 | 0 | 0 | 0 | 0 | 8060 | 2016 to 2018 | 5529.816 | 0 | 1450 | 0 | 1700 | 0 | 2000 | 0 | 55539.0365 |  | YOC356F/000A/087A
Three Brooks Environmental, Manor, Sheffield | Sheffield City Council | Yorkshire | Sheffield/Car Brook, Kirkbridge Dyke, Jervis Lumb watercourses | 0 | 0 | 0 | 50 | 100 | 0 | 2545 | 2018 to 2021 | 900 | 75 | 1400 | 0 | 150 | 0 | 150 | 0 | 17635.6487 |  | YOC356F/000A/089A
Upper Blackburn Brook Flood Alleviation | Sheffield City Council | Yorkshire | Sheffield/Blackburn Brook, Charlton Brook | 0 | 0 | 0 | 50 | 140 | 0 | 2020 | 2018 to 2021 | 1100 | 0 | 500 | 0 | 250 | 0 | 250 | 0 | 27989.7304 |  | YOC356E/000A/049A
Carr Beck - Flood Alleviation Phase 1 | Wakefield Council | Yorkshire | Cutsyke, Castleford Carr Beck area | 0 | 0 | 0 | 0 | 6 | 0 | 585 | 2018 to 2021 | 390 | 0 | 183 | 0 | 205 | 0 | 205 | 0 | 32.5761 |  | YOC355F/000A/114A
Ea Beck - Flood Alleviation Phase 1 | Wakefield Council | Yorkshire | South Kirkby/South Elmsall Area, EA beck | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 2016 to 2018 | 360 | 90 | 290 | 0 | 205 | 0 | 205 | 0 | 307.34 |  | YOC356F/000A/092A
Oakenshaw Beck Flood Alleviation - Drain Beck, Walton | Wakefield Council | Yorkshire | Walton, Wakefield | 0 | 0 | 0 | 0 | 13 | 0 | 80 | 2016 to 2018 | 67 | 0 | 0 | 0 | 65 | 0 | 65 | 0 | 181000
0
0

## Pipeline Programme
Flood and Coastal Erosion Risk Management (FCERM) Pipeline Programme - England
[5 empty] | Estimated funding required before 2021 dependent on full business case approval and securing required contributions | [6 empty] | Households with a better level of protection by March 2021 |  | Total households with a better level of protection when schemes are complete
Project Name | Risk Management Authority | Regional Flood and Coastal Committee (RFCC) | Location | Estimated Total Project Cost (£k) | Required in 2015/16 (£k) | Indicative to 2021 (£k) | RFCC local levy (£k) | Public (incl. Internal Drainage Board Precept) (£k) | Private (£k) | Further Required (£k) | Estimated earliest construction start | from flooding | from coastal erosion | from flooding | from coastal erosion | Economic benefits (Net Present Value, £k) | Other major benefits / reason for the scheme including estimate of householders better protected | NPN
Development Pipeline - May Move into Development Programme Subject to Securing Contributions
Chalkney Mill Refurbishment | Environment Agency | Anglian Eastern | White Colne | 350 | 50 | 300 | 0 | 0 | 0 | 0 | 2016 to 2018 | 0 | 0 | 0 | 0 | 0 |  | AEO000E/000A/417A
Northwick Flood and Drainage, Canvey Island | Environment Agency | Anglian Eastern | Canvey Island, Essex | 471 | 0 | 51 | 30 | 0 | 0 | 390 | TBC | 0 | 0 | 0 | 0 | 0 |  | AEO000E/000A/341A
Seawick Sea Defence | Environment Agency | Anglian Eastern | Seawick, Essex | 2500 | 0 | 150 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 90 | 0 | 27500 |  | AES504E/000A/033A
Shoebury Common Flood Defence Improvements | Southend-on-Sea Borough Council | Anglian Eastern | Shoeburyness | 7213.463 | 71 | 3322 | 750 | 0 | 0 | 1479 | 2016 to 2018 | 235 | 0 | 235 | 0 | 83684 |  | AES504F/000A/008A
Bawdsey Manor and Deben Estuary Mouth Works | Suffolk Coastal District Council | Anglian Eastern | Bawdsey Manor. | 615 | 0 | 80 | 0 | 0 | 0 | 535 | 2016 to 2018 | 0 | 0 | 0 | 1 | 735 |  | AES503C/000A/003A
Felixstowe North recharge, groynes and part seawall | Suffolk Coastal District Council | Anglian Eastern | Felixstowe | 1515 | 0 | 15 | 0 | 0 | 0 | 70 | 2021 on | 0 | 0 | 0 | 30 | 1635 |  | AES503C/000A/008A
Paston Brook Culverts Improvements | Environment Agency | Anglian Northern | Peterborough | 1220 | 0 | 650 | 0 | 0 | 75 | 65 | 2021 on | 0 | 0 | 60 | 0 | 492.772 |  | ANC404E/005A/002A
Welland Flood Banks refurbishment | Environment Agency | Anglian Northern | Lower Welland | 6383.99 | 0 | 60 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 300 | 0 | 5080.647 |  | ANC404E/000A/057A
Damford Pumping Station Flood Resilience | Black Sluice Internal Drainage Board | Anglian Northern | Damford | 65 | 0 | 32.5 | 0 | 0 | 9 | 23.5 | 2018 to 2021 | 10 | 0 | 10 | 0 | 1041.438 |  | ANC403I/005A/014A
Bagley Brook Outfall replacement | Environment Agency | English Severn and Wye | Shrewsbury, Bagley Brook | 150 | 0 | 150 | 0 | 0 | 0 | 0 | 2018 to 2021 | 0 | 0 | 0 | 0 | 188.35 |  | SNC001E/000A129A
Church Walk, Medlar with Wesham, Lancashire | Lancashire County Council | North West | Wesham, Lancashire | 20 | 0 | 15 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 10 | 0 | 4 |  | NWC009F/000A/018A
Newcastle Quayside Flood Alleviation | Newcastle City Council | Northumbria | Newcastle Quayside, River Tyne | 5480 | 0 | 800 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 0 | 0 | 42931 |  | NOC304F/000A/031A
Seahouses Main Pier Rehabilitation | Northumberland County Council | Northumbria | Seahouses Harbour, Northumberland | 5088.58 | 0 | 2372.58 | 0 | 0 | 0 | 1025 | 2018 to 2021 | 0 | 140 | 0 | 140 | 31902.286 |  | NOS301C/000A/061A
Tyneside Sustainable Sewerage | Northumbrian Water | Northumbria | Central Motorway, Newcastle | 3155.96 | 0 | 188.8 | 82.5 | 0 | 0 | 0 | 2021 on | 0 | 0 | 0 | 0 | 7000 |  | NOC304W/000A/001A
Bayards Cove Individual Property Protection | Environment Agency | South West | Dartmouth, Devon | 50 | 0 | 25 | 25 | 0 | 0 | 0 | 2018 to 2021 | 10 | 0 | 10 | 0 | 250 |  | SWC015E/000A/029A
Haldon & Princess Piers Structural Repairs | Torbay Council | South West | Torquay | 5765.21 | 0 | 75 | 0 | 150 | 0 | 0 | 2021 on | 0 | 0 | 0 | 0 | 15116.996 |  | SWS006C/000A/044A
Lower Totton Tidal Flood Alleviation | Environment Agency | Southern | Bartley Water | 700.7 | 0 | 561.69 | 0 | 0 | 0 | 79.01 | 2016 to 2018 | 145 | 0 | 145 | 0 | 5669 |  | SOO002E/000A/301A
Manor Farm, River Test - Regional Habitat Creation Programme | Environment Agency | Southern | River Test | 2020 | 970 | 800 | 0 | 0 | 0 | 0 | 2016 to 2018 | 0 | 0 | 0 | 0 | 807 |  | SOO002E/000A/187A
Shoreham Western Harbour Arm Flood Defence | Worthing BC | Southern | Shoreham, West Sussex | 12000 | 0 | 1200 | 0 | 0 | 0 | 400 | 2021 on | 0 | 0 | 140 | 0 | 5650.538 |  | SOS004C/002A/017A
Little Hadham A120 Bypass flood storage area | Environment Agency | Thames | North of Little Hadham, in East Hertfordshire. | 1559 | 0 | 540 | 660 | 0 | 0 | 0 | 2021 on | 0 | 0 | 45 | 0 | 2730.8641 |  | THC033E/001A/005A
The Woking Initial Assessment | Environment Agency | Thames | Woking, Surrey | 10216 | 0 | 650.75 | 300 | 0 | 0 | 8449.25 | 2021 on | 0 | 0 | 70 | 0 | 1869.319 |  | THC011E/001A/002A
Marlow Surface Water Drainage | Buckinghamshire County Council | Thames | Marlow, Buckinghamshire | 1050 | 0 | 310.45 | 189.55 | 0 | 0 | 0 | TBC | 0 | 0 | 100 | 0 | 2032.273 |  | THC043E/000A/035A
Hertford Surface Water Study | Hertfordshire CC | Thames | Various locations in Hertfor, Hertfordshire | 1127 | 0 | 23.25 | 51.75 | 0 | 0 | 0 | 2021 on | 0 | 0 | 30 | 0 | 0 |  | THO999F/052A/002A
Long Marston and Surrounding Area Surface Water Study | Hertfordshire CC | Thames | Long Marston, Hertfordshire | 35 | 16.429 | 0 | 18.571 | 0 | 0 | 0 | 2021 on | 0 | 0 | 10 | 0 | 48.331 |  | THO999F/052A/003A
Watford Combined Surface Water and Fluvial Flood Risk Study | Hertfordshire CC | Thames | Various sites along the Colne Valley, Watford, Hertfordshire | 75 | 8.75 | 25 | 41.25 | 0 | 0 | 0 | 2021 on | 0 | 0 | 10 | 0 | 89.616 |  | THO999F/052A/005A
Wick Road Surface Water Flood Alleviation - Hackney | London Borough of Hackney | Thames | Homerton | 501.8 | 0 | 72 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 400 | 0 | 11326.516 |  | THO999F/044A/002A
Stanstead Abbots flood alleviation |  | Thames | Stanstead Abbots | 1050 | 0 | 554.214 | 495.786 | 0 | 0 | 0 | TBC | 0 | 0 | 0 | 0 | 0 |  | _D
Isle of Axholme, North Soak Syphon Automatic Weedscreen | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 5 | 0 | 0 |  | TRC002E/000A/014A
Isle of Axholme, River Idle Asset Improvements | Environment Agency | Trent | Isle of Axholme Flood Risk Management Strategy | 36 | 0 | 14.4 | 0 | 0 | 0 | 0 | 2018 to 2021 | 0 | 0 | 15 | 0 | 0 |  | TRC002E/000A/017A
River Leen, Queens Medical Centre Embankment | Environment Agency | Trent | River Leen, right bank adjacent the Queens Medical Centre Hospital | 650 | 0 | 500 | 150 | 0 | 0 | 0 | 2016 to 2018 | 70 | 0 | 70 | 0 | 8963.34 |  | TRC003E/000A156A
Tidal Trent, Torksey Gate Automation Improvements | Environment Agency | Trent | Tidal Trent Flood Risk Management Strategy | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 2018 to 2021 | 2775 | 0 | 2775 | 0 | 33453 |  | TRC002E/000A/018A
Holgate Beck Pumping Station Replacement | Environment Agency | Yorkshire | York, Holgate Beck | 1500 | 50 | 350 | 0 | 1100 | 0 | 0 | 2021 on | 125 | 0 | 125 | 0 | 32.461 |  | YOC353E/000A/061A
Upper Calder Flood Risk Reductions | Environment Agency | Yorkshire | Upper Calder | 2964 | 497 | 0 | 960 | 693 | 0 | 0 | TBC | 625 | 0 | 630 | 0 | 0 |  | YOC355E/000A/073A
Walsden Water-Todmorden Flood Alleviation Phase 3 | Environment Agency | Yorkshire | Todmorden, Walsden Water | 35996 | 353 | 3 | 0 | 0 | 0 | 0 | TBC | 0 | 0 | 620 | 0 | 0 |  | YOC355E/001A/001A
Works arising from City of York Flood Defence Improvement Strategy | Environment Agency | Yorkshire | York | 25000 | 0 | 250 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 4000 | 0 | 33261 |  | YOC353E/000A/040A
Calder Ryburn Flood Alleviation | Calderdale MBC | Yorkshire | Ryburn | 325 | 0 | 11 | 0 | 0 | 0 | 14 | 2021 on | 0 | 0 | 25 | 0 | 215 |  | YOC355F/000A/088A
Rough Hall Lane, Wainstalls | Calderdale MBC | Yorkshire | The southern part of Wainstalls Lodge Lane and Kelly Lane | 60 | 0 | 3 | 0 | 0 | 0 | 7 | 2021 on | 0 | 0 | 5 | 0 | 63 |  | YOC355F/000A/104A
Shaw Wood Road, Springside | Calderdale MBC | Yorkshire | Bottom of Shaw Wood Road, adjacent the Rochdale Canal. | 90 | 0 | 5.5 | 0 | 0 | 0 | 4.5 | 2021 on | 0 | 0 | 10 | 0 | 270 |  | YOC355F/000A/105A
Shoebroad Clough | Calderdale MBC | Yorkshire | Hillslope to the East of Walsden Water | 170 | 0 | 14 | 0 | 0 | 0 | 6 | 2021 on | 0 | 0 | 30 | 0 | 723 |  | YOC355F/000A/106A
Smithy Lane, Colden | Calderdale MBC | Yorkshire | Hillside South West of Colden | 85 | 0 | 2 | 0 | 0 | 0 | 8 | 2021 on | 0 | 0 | 5 | 0 | 35 |  | YOC355F/000A/107A
Stubbing Drive | Calderdale MBC | Yorkshire | Hillside South west of Hebden Bridge town centre | 110 | 0 | 6 | 0 | 0 | 0 | 4 | 2021 on | 0 | 0 | 15 | 0 | 354 |  | YOC355F/000A/109A
Swineshead Clough | Calderdale MBC | Yorkshire | Hillslope to the East of Walsden Water | 170 | 0 | 20 | 0 | 0 | 0 | 0 | 2021 on | 0 | 0 | 30 | 0 | 723 |  | YOC355F/000A/118A
Rotherham to Kilnhurst Phase 2 Flood Alleviation | Rotherham MBC | Yorkshire | Rotherham Town Centre to Kilnhurst, Rotherham, South Yorkshire | 19000 | 0 | 17 | 0 | 0 | 0 | 633 | TBC | 0 | 0 | 115 | 0 | 0 |  | YOC356F/000A/097A
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
2691
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
20
100
20
0
0
0
0
602
0
12
0
0
309
0
0
0
0
0
0
2322
90
0
0
0
350
0
0
9
0
0
0
0
0
0
0
0
0
0
68
25
0
94
62
56
56
53
47
31
16
0
0
130
81
13
10
0
12
57
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
139
0
122
20
0
139
0
0
0
0
2387
22
0
0
11
52
0
0
0
0
3
120
0
106
52
50
50
50
50
26
30
14
0
100
80
70
0
0
0
274
0
0
0
1213
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
2820
2800
225
0
29
0
0
0
0
0
630
0
0
618
114
0
98
550
0
0
0
0
0
0