FCO SPF PROJECT EVALUATION

Sections 1-3 to be filled out by Programme Teams / Post

Project Details
Project Number / (GB-3-xxxxxx ABC) / ABC = 3 digit country code from OECD	PHR COB 151401
Project Title	Capacity building for effective participation of women victims of the armed conflict in Colombia
Project Cost (total cost / cost to FCO if different)	Initial proposal: £44,032 / Final spend: £39,150
Project Start/End Dates	28 October 2013 – 15 March 2014
Programme	Human Rights and Democracy Programme (HRDP)
Country/Countries	Colombia
Official Development Assistance Y/N	Y

Project Purpose (from proposal form)
Women victims of the armed conflict and the Colombian government are strengthened to guarantee effective participation of women in public policy making scenarios within the framework of the “Victims and Land Restitution Law (2011)”(“Victims Law”)

Project Background / Context including what the project set out to achieve (150 words max)
The “Victims Law” sets out a framework for reparations to victims of the conflict. The “Protocol for the Effective Participation for Victims of the Armed Conflict” (2013) (the Protocol) outlines how victims can engage in the planning and implementation of public policies on reparations and creates spaces at the local, “departmental” (regional) and national levels for victims to engage. Women victims face particular challenges in being heard in these processes (e.g. lack of education, few opportunities for leadership, trauma from sexual violence) so the Victims Unit requested the support of MAPP/OAS to pilot a methodology to increase women’s participation in two departments, with a view to rolling it out to others. MAPP/OAS worked with local women’s organisations to produce a report of the main challenges faced by women victims in participating in the Victims Working Tables, facilitated workshops on women’s rights, and helped participants to develop their proposals for the Working Table action plans.

Evaluation summary (150 words max)
Overall the project achieved its objectives. MAPP/ OAS are a capable implementer that delivered effectively. Feedback from beneficiaries on the workshops was overwhelmingly positive. It helped to create a network of women victims who are continuing to work together. It also developed links between the women and authorities in the regions responsible for delivering on the Victims Law. There were different opportunities and challenges in each region. The Victims Unit was pleased with the methodology and is planning to roll it out to 10 other departments. / The short length of the project was challenging. MAPP/OAS had not anticipated that the vulnerability of the women participants meant they needed more emotional support and time to establish relationships to be able to participate. In addition, practical barriers to their participation slowed down the pace of the workshops. A key challenge is sustainability and ensuring their voices are heard and acted upon in practice.

Questions
Did the project achieve the project purpose?	Y
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	There was an under spend of £4,890. / Due to the implementer’s administrative procedures 10% of the budget was saved. Some of the activity costs were covered by the implementer’s own resources.
Was the project completed on time? (Y/N) / If not, why not?	Y
Were the Project benefits sustained after project completion?	Y

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green
Green		Y

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Working with victims of conflict is sensitive, and it is critical to engage a respected, credible implementer with expertise of working with women victims in the regions. This is important to managing expectations and avoiding potential harm to the beneficiaries. / Engaging victims and increasing their capacity to participate in these processes takes time. It is important to get projects off the ground as soon as possible in the project year cycle to maximise benefits. / Providing ongoing psychological and practical support to victims is necessary to ensure their meaningful and continued participation in these processes. However, it is difficult to secure funding for this. This needs to be considered when funding these types of projects. / Projects can have unexpected benefits which are important to recognise and record. The relationships formed between the women and their increased awareness of their rights was felt by the implementer to be the most significant, but unanticipated, achievements of the project. / There are administrative challenges of working with an international organisation due to rigid bureaucratic processes and budgets which are not compatible with HRDP contracts. This creates extra work for Post and can be a real logistical challenge. In this case, overall this was offset by the effectiveness of the implementer, but is an important learning point for the HRDP.

Recommendations for future projects
Future projects could: / Support the Victims Unit and local women’s organisations in other departments to engage women in local and regional Victims Working Tables using the methodology developed. / Focus on supporting and increasing the participation of women victims of sexual violence, as an especially vulnerable group of women victims. / Strengthening network of women victims’ of gender and sexual based violence, as a way of re-building social tissue broken by the conflict, supporting other victims to access services, and monitor and lobby for implementation of laws and government programmes.