FCO SPF PROJECT EVALUATION

Sections 1-3 to be filled out by Programme Teams / Post

Project Details
Project Number / (GB-3-xxxxxx ABC) / ABC = 3 digit country code from OECD	PHR COB 331401
Project Title	Enhancing government proficiency to implement the UN Guiding Principles on Business and Human Rights (UNGPs) in contemporary Colombia
Project Cost (total cost / cost to FCO if different)	Initial proposal: £84,118 / Final spend: £82,118
Project Start/End Dates	24 June2013 – 28 February 2014
Programme	Human Rights and Democracy Programme (HRDP)
Country/Countries	Colombia
Official Development Assistance Y/N	Y

Project Purpose (from proposal form)
Colombian government, civil society and business are in the position to effectively implement the UNGPs.

Project Background / Context including what the project set out to achieve (150 words max)
The project aimed to support the government to develop policy and tools to implement the UNGPs in Colombia. To do this, Fundación Ideas para la Paz (FIP) worked with the Presidential Programme for Human Rights and International Humanitarian Law (now the Presidential Counsellor for Human Rights) to develop Guidelines for a Chapter on Business and Human Rights for the national public policy on human rights. These Guidelines formed the basis for the chapter itself, published July 2014, which will become Colombia’s National Action Plan (NAP), the first in the region. FIP also partnered with the Procuraduría General (PGN) to develop an administrative order (“directive”) tasking all public officials to implement the UNGPs and setting out specific actions that they must take to do so, together with sanctions for non-compliance. This project builds on two previous years’ work with the three partners funded by the HRDP. This provided a solid platform of consultations and engagement with businesses and civil society across the country.

Evaluation summary (150 words max)
Overall, the project delivered its intended outputs - significant developments in national policy on business and human rights (BHR). It consolidated a successful first two years to embed BHR firmly in the government’s agenda, and the engagement of government partners was high. FIP consulted widely with civil society and business, and feedback was positive from both sets of stakeholders. The key challenge will be how the government implements both the chapter and the directive. For the former, the prize is to get it into the National Development Plan, thus unlocking resources to implement it. The change in administration following the October elections has slowed progress on this front. For the latter, the main challenge is building the capacity of officials on BHR, particularly in the regions. The potential longer-term benefits to UK interests are clear: a more responsible and human rights compliant business environment supports prosperity objectives to increase UK investment in Colombia.

Questions
Did the project achieve the project purpose?	Y
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Y / (£1,444 under the target spend, variance due to exchange rate)
Was the project completed on time? (Y/N) / If not, why not?	Y
Were the Project benefits sustained after project completion?	Y

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green
Green		Y

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Development of a NAP on BHR takes time and resources. The outputs delivered during the 10-month timescale of this project built on the foundation of two years’ work and a much broader process of developing a national human rights policy. / Wide consultation with civil society and business is critical for the developing NAPs. However, this requires careful balance between business and civil society participants so as not to be seen as favouring one over the other. This is particularly so in Colombia where there is mistrust rooted in the conflict. / Leadership and buy-in from government to collaborate with business and civil society is essential. This was a real strength of the project. / Consultation with grassroots organisations and communities affected by business operations in the regions outside Bogotá and the main cities is important, but challenging to execute in practice. It is important needs to consider how best to do this when implementing the two project outputs. / Agreeing clear Terms of Reference (ToR) at the outset is essential for complex multi-partner projects. ToR should set out each partner’s role, responsibilities, and portion of the overall budget. It should also be agreed in the ToR how the project is to be “badged”; it is important for the UK to get credit for its funding. / There is rich learning and lessons for other countries wanting to develop NAPs, and Posts wanting to support this via project funding. It would be useful to work up a short summary for the network of the process, key challenges and what works.

Recommendations for future projects
Future projects could focus on: / Civil society and/ or access to remedy, e.g. increasing civil society organisation capacity to engage in multi-stakeholder initiatives; strengthening access to information; capacity building for grassroots organisations at a local level; supporting human rights defenders (HRDs) working on corporate accountability; focusing on lawyers/ improving judicial mechanisms; and developing non-judicial grievance mechanisms. / Corporate responsibility to respect, e.g. collaborations with industry associations on human rights due diligence or grievance mechanisms; and capacity building in high-risk sectors.