FCO SPF PROJECT EVALUATION

Sections 1-3 to be filled out by Programme Teams / Post

Project Details
Project Number	FOE14031
Project Title	Zambia Debates!
Project Cost	£150,000
Project Start – End Dates	1 August 2013 – 28 February 2014
Programme	Human Rights and Democracy Programme (HRDP)
Country	Zambia
Official Development Assistance	Yes

Project Purpose
To improve the capacity of the media in Zambia to facilitate increased dialogue and debate between ordinary Zambians and their leaders on issues of concern to them, including human rights and their right to better service delivery.

Project Background / Context including what the project set out to achieve (150 words max)
This project aimed to support ZNBC, the state broadcaster, and three community radio stations to produce audience-led, issue-based debate programmes. The objective was to create opportunities for dialogue and debate between ordinary Zambians and their leaders and to encourage citizens to hold their government to account. This was in response to an identified lack of space in the media for such interaction and some concern about government media restrictions and growing intolerance for opposition views. BBC Media Action trained staff from each partner in journalism and technical skills, particularly on the ability to conduct rigorous research and to produce good quality debate content. This resulted in 15 outdoor radio debates and two television debates, including a ground breaking primetime debate on press freedom in Zambia. The implementer also provided media awareness training for 24 civil society organisations to support them to better utilise and engage with the media.

Evaluation summary (150 words max)
Overall the project delivered its intended outputs successfully. Participants from the radio stations and ZNBC felt that the training was effective and delivered to a high standard. The radio and television debates attracted large audiences and were generally well received. In some cases calls for improvements in service provision made during the debates resulted in a positive response from the authorities and concrete action. The project helped to open the space for communication between the authorities and citizens on issues of importance to them. This is reflected by the partner’s continuation of audience led programmes, increased demand, and the format being picked up by other media. The training for civil society was also well received, however its effectiveness and impact to delivering the project purpose was less clear. That Zambia is not a country of concern raises some questions as to the overall relevance to this fund. That said it was a timely intervention, delivered well and had positive impact, the type of project well worth considering in non-priority countries.

Questions
Did the project achieve the project purpose?	Yes
Did the project come in on budget? / If no, why and what was the difference in cost?	Yes
Was the project completed on time? / If not, why not?	Yes
Were the Project benefits sustained after project completion?	Yes

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green
Green		X

Guide to overall rating:
Green – project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
The project’s success depended partly on the implementer having previously worked with three out of the four partner media organisations. Good relationships and previous projects provided a firm foundation to enable this project to get off the ground quickly. / Starting where people were at generated engagement and contributed to the project meeting its objectives. For example going out into local communities for ‘outside broadcasts’ and asking people what they wanted to talk about in the debates. This was particularly important for engaging rural communities, where transport times and practicalities could otherwise make it difficult for potential participants to take part. / It can be challenging to engage government representatives in audience led debates in a context where this is not the norm. Outreach with government representatives was important to getting them to participate in debates, as their concerns and preconceptions about audiences and the media sometimes acted as disincentives to take part. / Media capacity building projects take time and resources often beyond the 10-12 month timeframe of HRDP grants. Time was a significant challenge in delivering this project. / An important impact of the project was its contribution to opening the space for interactive debate between Zambians and their leaders, which helps to support freedom of expression and democracy. However, this impact is particularly difficult to measure.

Recommendations for future projects
Future projects could focus on: / Democracy/ freedom of association – this remains an area of concern in Zambia and there will be national elections in 2016. / Women’s rights – are a key area of concern, particularly violence against women. This could be a good strategic fit with HRDP’s women’s rights priority. / Torture prevention – there may be scope to explore projects relating to prision conditions (arguably one of the most severe human rights issues in country) if it fit under the the torture prevention strategy.