## Slide 1: Childhood Flu Immunisation Programme 2013/14 Pilot Feedback

## Slide 2: Contents
Background
Pilots
Summary of areas participating, models and uptake achieved
Key messages from the primary school pilot areas
Key messages from the secondary school pilot
Summary of staffing requirements
Other general recommendations / issues

## Slide 3: Background
The Joint Committee on Vaccination and Immunisation recommended that the flu immunisation programme should be extended to include all children aged two to less than 17 years
Vaccination will provide important protection to children, and offer indirect protection to people at high risk of complications from flu, including infants, older people, and those in clinical risk groups
The programme will eventually offer the vaccination to over 9 million children in England each year
Vaccination can only take place within a short period (September - December)
Due to the scale of the programme JCVI recommended a phased roll-out

## Slide 4: Pilots
Pilots set up to assess all aspects of set up and delivery including:
  workload and staffing requirements
  acceptability to parents and children
  impact on delivery settings
  impact on other immunisation and child health programmes
  logistics of vaccine supply and delivery
Seven geographic pilot areas selected to enable delivery to be assessed across a wide variety of settings: Bury, Cumbria, South East Essex, Gateshead, Leicester City, East Leicestershire & Rutland (LLR) and London (Newham and Havering).
Six of the pilot areas delivered the programme using a school based programme. Due to the rural location Cumbria chose a local pharmacy and General Practice based model

## Slide 5
Site | Uptake | Model | Provider | High risk children vaccinated by pilot team | Inactivated vaccine for with contraindications given by pilot team
Bury * | 63.5% | School based | Private Provider | Yes | Yes
Cumbria | 35.8% | Community | Pharmacy/GP | Yes | Referral to GP
Gateshead | 52.3% | School based | School nursing service | Referral to GP | Referral to GP
Havering | 63.8% | School based | Trust immunisation team | Yes | Yes
Leicester | 51.7% | School based | Trust immunisation team | Yes | Referral to GP
Newham | 45.6% | School based | Trust immunisation team | Yes | Yes
SE Essex** | 71.5% | School based | Trust immunisation team | Yes | Yes
Summary of models of service delivery in
each pilot and uptake achieved

## Slide 6: Cumulative uptake of LAIV in primary school-age children in pilot sites 2013-14, England

## Slide 7: Gateshead school nursing model - key messages
Programme delivered by qualified school nurses is
      good model to ensure safety
      costly and may not be scalable- further piloting required
Having a parent attend for vaccination will
      ensure correct identification of child guaranteed
      is more disruptive for schools
      may adversely impact on uptake
      not be recommended for the future
Referring children at high risk to GP
      may lead to reduced uptake in the most vulnerable children
      increases clinical time to triage consent forms

## Slide 8: Cumbria community model - key messages (1)
Pharmacies can deliver high volume of vaccines in the community
      over 80% of 13,000 vaccines given by pharmacies
Pharmacists are very enthusiastic to be involved
      also interested in vaccinating in schools
Pharmacist delivery was well accepted by parents (based on evaluation from those attending)

## Slide 9
Large number of pharmacy providers
      time consuming for contracting
      increase potential for wastage with vaccine distribution
    Pharmacies can supply timely vaccine uptake data
      web-based system provided ‘live’ data
      enabled timely project monitoring and management
Model may work well as back-up to delivery in school delivery
Cumbria community model
– key messages (2)

## Slide 10: Bury independent provider model - key messages
Independent provider can work successfully in schools provided that
      early and on-going engagement of schools and stakeholders (Bury Council, PHE, NHSE, Bury CCG)
      collaboration between area teams, providers, and schools (including school nursing service)
      involvement of Local Authority Department for Education, Director of Children’s Services
    Acceptance of consent forms on the day can be problematic
      needs system and staff to deal with this

## Slide 11: Leicestershire & Rutland immunisation team model – key messages
Immunisation team approach largely successful
good communication with schools required to ensure:
      appropriate input and involvement of school staff
      most efficient and effective approach to children
      provision of appropriate facilities for vaccination session
Administrative support team key to success and required to
        order goods and vaccine, prepare documentation
        arrange delivery of materials/vaccines (maintaining cold chain)
        scheduling communication with parents
        logistics and administration on the day, data entry
        work in shifts (12 hour days)
      Porcine gelatine content of Fluenz had an impact on uptake

## Slide 12: Havering immunisation team model - key messages
Immunisation team model largely successful
      early engagement with schools essential
      significant problems with recruitment and HR processes for temporary staff
Significant clinical burden triaging consent forms and contacting parents
      need early identification of ‘high risk’ children
      prioritise special schools
Certificates and stickers for vaccinated children popular!

## Slide 13: Newham immunisation team - key messages
Immunisation team model was largely successful
      positive engagement with schools/wider community essential to minimise impact
      significant problems with recruitment and HR processes for temporary staff
Partnership with other agencies was vital to the project’s success
      including children centres, GPs, education, communication team
Porcine gelatine content of vaccine potentially adversely affected uptake

## Slide 14: Essex immunisation team - key messages
Immunisation team model was largely successful
      adjusted timetabling for HPV immunisation and National Child Measurement programmes
      staff in existing posts utilised for programme
      able to appoint additional staff on year-long contracts
Health care assistants provide a cost effective skill mix
      administering vaccines under Patient Specific Direction signed off by a nurse prescriber with access to the children’s clinical records
    Self-administration for eligible children in Year 6 was successful
      well received by pupils, approximately 65% self administered
      more time consuming than nurse administration

## Slide 15: Bury private provider - secondary school pilot
  Overall secondary school pilot in years 7-11 was successful
        uptake 55% (492/897 vaccinated)
        took 4.5 hours across 2 days (2 mins per child)
Group self administration didn't go well
        further piloting required
Whole class approach not tried due to concerns about
        privacy for consent checking
        classes moved round every 30 mins
Used procedure recommended as used for school photos
        pupils provided with an appointment time at registration
        attended assembly hall in groups of about ten pupils

## Slide 16: Staffing recommendations
Generally need around 3-6 nurses and 2 administrators per primary school:
      3-4 nurses (Leicester and Havering)
      2 nurses + 2 admin for each 100 children, plus 1 additional nurse for every 100 children (Bury)
Temporary staff created additional work for recruitment and HR
Health care support workers can work but need prescribers
Having dedicated driver allocated to programme to deliver vaccine to schools worked well (Bury)

## Slide 17: General issues and recommendations (1)
Set-up time for programmes is critical:
  ideally liaise with schools in summer term
  visits to schools recommended so that requirements of programme understood and facilities assessed
  communications strategy: local press, newsletters, website, consider visiting school assemblies etc.
Notes: School visits may not be required in subsequent years

## Slide 18: General issues and recommendations (2)
Administrative burden is considerable – and includes two different groups of staff:
    Clinical
      triage of consent forms to assess clinical eligibility
      contacting parents for further detail about clinical conditions e.g. asthma
    Non-clinical
      preparation of materials
      liaison with school to distribute and collection of materials
      coordination at vaccination sessions (school and immunisation team)
      data collection and sharing
    Estimate that administration requires 2-3 times more time than vaccination