## Internal_-_High
Internal Pen Test Risks - High

Severity (from ITHC Report)	Reference	CVSS Score	Vulnerability	Solution	Target Date	Date Completed	Action/Mitigation	Open/Closed
High	ASA-696	10.0	Sensitive information found on Windows network shares	Remove sensitive data from share and make staff aware that sensitive information should not be stored unencrypted or in shared areas.			Files deleted and updated information included in monthly newsletter.	Closed
High	ASA-697	10.0	Servers missing critical Windows patches	Patch servers			WSUS server has been installed and all patches have been installed. Patching Policy has been re-reviewed by head of ICT and signed off.	Closed

## Internal_-_Medium
Internal Pen Test Risks - Medium

Severity (from ITHC Report)	Reference	CVSS Score	Vulnerability	Solution	Target Date	Date Completed	Action/Mitigation	Open/Closed
Medium-High	ASA-707	7.5	LM Hash enabled	LM hash storage disabled in Domain GPO and Default GPO			GPO setting tested and released to enable only NTLMv2	Closed
Medium-High	ASA-704	7.5	User accounts protected by weak passwords	Enable password complexity on Domain			Complexity enabled on wider domain. Mandatory 9 character passwords enforced. GCSX users have also got two factor authentication using smart cards for logon	Closed
Medium-Low	SVC-141		Web server supports plaintext basic authentication	Enable SSL on webserver			The webserver is provided by a third party supplier. A ticket has been raised with their helpdesk. The server does not host any PSN-originating data. Users have been informed to change their password and training given to reinforce that they should not share passwords on different systems.	Open
Medium-Low	SVR-001	6.0	Telnet enabled on device	Disable telnet, and if remote access required enable SSH			It is not possible to disable telnet on this device. However a host-based firewall has been configured to block port 23.	Open

## External
External Pen Test Risks

Severity (from ITHC Report)	Reference	CVSS Score	Vulnerability	Solution	Target Date	Date Completed	Action/Mitigation	Open/Closed
High	ADT-928	10.0	Web application vulnerable to SQL Injection	Ensure all user input is parameterised (where possible			Vendor has provided a patch and vulnerability has been closed after retest. All user input is is tightly checked.	Closed
High	SVC-131	10.0	IIS Servers have Internet Printing Protocol Enabled	Disable IPP			IPP disabled	Closed
Medium-High	SVC-113		Unsupported Operating System detected (Microsoft Windows 2000)	Upgrade to a supported Operating System			Server in question has been decommissioned and a Windows 2008 R2 server set up to host the site.	Closed