FCO SPF PROJECT EVALUATION

Project Details
Project Number	PHR KEN 331402
Project Title	Business and Human Rights Training Courses (Kenya)
Project Cost (total cost / cost to FCO if different)	£16,759.56
Project Start/End Dates	Sept 2013 – March 2014
Programme	Human Rights and Democracy Programme (HRDP)
Country/Countries	Kenya
Official Development Assistance Y/N	Yes

Project Purpose (from proposal form)
To accelerate the development of responsible business practices in emerging economies by raising awareness and building capacity to implement the UN Guiding Principles on Business and Human Rights (UNGPs) by business and their partners.

Project Background / Context including what the project set out to achieve (150 words max)
Companies in Kenya face many human rights related challenges such as poor working conditions, land issues, community tensions, gender equality, corruption etc. These tensions are expected to rise as companies move into previously underdeveloped areas. As such, a human rights approach can help these companies manoeuvre within these difficult territories, attracting foreign investment, and increase their chances for exports to international consumer markets. This project sought to increase the capacity of businesses to respect and support human rights.

Evaluation summary (150 words max)
The project run by the management consultancy twentyfifty, aimed to support take-up of the UNGPs in Kenya through working with members of Kenya’s UN Global Compact network. The primary activity was to design and deliver a tailored training course to a small group of Kenyan manufacturers. twentyfifty worked closely with the Kenya Association of Manufacturers (KAM), as local leaders of the national UN Global Compact network, to market the training and design the course. 30 business delegates attended the two-day course. Around one third of the participants were from a major ICT company, with others from the food, drink, steel, electricity and salt extraction sectors. Within the timescale of the project, it did not prove possible to measure the operational impact on the participant businesses. But the course feedback was strong and Global Compact Network Kenya (GCNK)/ KAM are interested in delivering further training to its members.

Questions
Did the project achieve the project purpose?	Partly
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Yes
Was the project completed on time? (Y/N) / If not, why not?	Partly. All the activities that happened took place before the end of the Financial Year, but the follow-up activities with participants to gauge impact were cancelled due to insufficient time.
Were the Project benefits sustained after project completion?	Partly

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green	X
Green

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
A preparatory visit was crucial to the overall success of the project; building trust and understanding between project partners. / Continuous oversight and communication between project partners is essential to keep delivery on track. / The one-year project cycle makes it important to approve projects quickly so implementers have as much time as possible to complete project activities. / Training courses are most effective when they are carefully tailored to the local country context. / Establish a clear strategy and time-line for follow up with course participants to test and sustain project outcomes.

Recommendations for future projects
The British High Commission (BHC) in Nairobi should continue to focus on Business and Human Rights and work through industry bodies like KAM. The operating environment is difficult, but there are signs of industry demand and increased awareness of the issues. / There is potential for twentyfifty and/or GCNK/ KAM to continue training courses of this type. For any future projects we recommend more strategic thinking is given as to how training fits into the overall needs in the manufacturing sector. / BHC Nairobi should continue to engage with and encourage KAM to take a leadership role on this issue in the manufacturing sector in Kenya.