FCO SPF PROJECT EVALUATION

Project Details
Project Number	GB-3-231301
Project Title	Integrating safeguards against torture in the law and practice of Kazakhstan
Project Cost (total cost / cost to FCO if different)	£33,000
Project Start/End Dates	29 June 2012 to 28 February 2013
Programme	Human Rights and Democracy Programme
Country/Countries	Kazakhstan
Official Development Assistance Y/N	Yes

Project Purpose (from proposal form)
Promote integration of the 2011 UN Human Rights Committee recommendation towards Kazakhstan on putting an end to torture through specific legislative, institutional and capacity building measures.

Project Background / Context including what the project set out to achieve (150 words max)
In 2011, the UN Human Rights Committee recommended that Kazakhstan should ensure that “allegations of torture and ill-treatment are effectively investigated, perpetrators are prosecuted and punished with appropriate sanctions, and victims receive adequate reparation.” At the time, there was no comprehensive policy on the establishment of an independent mechanism for torture complaints; any compensation awarded to torture victims came from the perpetrators (international obligations require the State to provide effective remedy); and there was a degree of public apathy regarding allegations of torture. / This project therefore aimed to draft best practice recommendations in these areas for use by government and civil society, and to integrate these into the ongoing reform of Kazakhstan’s Criminal Procedure Code, Criminal Code, police and prosecutorial functions, as well as using them in an alternative report to the UN Committee Against Torture. In addition, the project aimed to raise public awareness of the importance of combating torture.

Evaluation summary (150 words max)
This was an extremely timely project, and its purpose and indicators of success were very much aligned to the aims of the Programme Fund and those of the Embassy. The implementer is well-respected in Kazakhstan, and feedback from stakeholders on the outputs of the project was positive, praising the implementer’s expert knowledge and professionalism. The project produced three comprehensive policy papers setting out detailed recommendations on independent investigation of torture allegations, effective safeguards against torture, and compensation to victims of torture. These can be used by the government and civil society when reforming current legislation. / However, the project suffered from the indicators of success being overly ambitious and largely outside of the implementer’s control; legislative change was not likely to occur within one year. The project would therefore benefit from being re-evaluated once the criminal codes are reformed to determine what impact, if any, the recommendations from this project had.

Questions
Did the project achieve the project purpose?	Not in the time-span of the project.
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Yes
Was the project completed on time? (Y/N) / If not, why not?	Yes
Were the project benefits sustained after project completion?	Difficult to assess in the short-term.

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber	X
Amber	Green
Green

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Expectations of legislative change need to be more realistic, e.g. the project had as an indicator of success that “recommendations on the independent mechanism for torture complaints are adopted”. In reality, as the implementer recognised in their completion report, 2-3 years would be needed for such a change to take place. / It is important to drill down into what the implementer understands by “advocacy” and “campaigns” in project proposals. Another indicator of success for this project was “wide anti-torture campaign is launched by civil society”, with one of the outputs being “anti-torture advocacy campaign to promote legislative and institutional reforms in Kazakhstan”. However, in reality, this seemed to equate to a single conference attended by experts. / Indicators of success must be within the implementer’s control, and must be realistic and clearly defined. / Projects must be easily measurable and base-lined. / Project proposals need to be more explicit about key project stakeholders’ roles (e.g. the Kazakhstan Coalition against Torture) and how they will be leveraged.

Recommendations for future projects
The FCO needs to examine the one-year cycle for projects, and whether that is truly viable for most human rights projects, given that progress on these is often incremental. / Kazakhstan faces a number of challenges in terms of addressing torture: prisons are far from cities, so it is difficult for NGOs to access them to investigate torture issues; the general public are inclined to be tough on crime; and civil society is still at a fairly early stage of development. Interviews suggested that future work in this area should focus on increasing the capacity of civil society, training defence lawyers appropriately, facilitating ad-hoc visits to prisons, and increasing awareness of the National Preventive Mechanism against Torture and Ill-Treatment amongst lawyers, police, prison guards etc.