FCO SPF PROJECT EVALUATION

Project Details
Project Number	PHR KEN 331401
Project Title	“Nairobi Process: A Pact for Responsible Business” relating to oil and gas exploration companies in Kenya
Project Cost (total cost / cost to FCO if different)	£89,929
Project Start/End Dates	23 August 2013 – 23 August 2014
Programme	Human Rights and Democracy Programme Fund
Country/Countries	Kenya
Official Development Assistance Y/N	Y

Project Purpose (from proposal form)
Advancing the implementation of relevant business and human rights standards within the oil and gas sector in Kenya.

Project Background / Context including what the project set out to achieve (150 words max)
Kenya has recently granted 47 oil and gas exploration licences. This has raised expectations of economic benefits by government, business and local communities. Experience elsewhere in Africa suggests that if the licences are not managed carefully then competing expectations of these actors can lead to community tensions and security risks. The core aim of the project was to advance the implementation of the UN Guiding Principles on Business and Human Rights (UNGPs) and the Voluntary Principles on Security and Human Rights (VPs) within the oil and gas sector in Kenya. It was a multifaceted project, which set out a number of ambitious goals: embed the VPs in the operational policies of Kenya’s security sector, establish a multi-stakeholder process to develop a shared understanding of community issues, develop the capacity of the Kenyan National Human Rights Commission (KNHRC) and other East African national human rights commissions, develop a methodology for “strategic human rights impact assessments”, establish a credible focal point for these issues in Kenya, and improve the legislative environment.

Evaluation summary (150 words max)
The potential benefits of this project to UK interests are clear: a secure and human rights compliant environment to invest in oil and gas extraction, sustainable benefits to the Kenyan economy and recognition of the interests of affected local communities. The project, while overly ambitious for its first year, made a reasonable impact on advancing the implementation of the UNGPs and VPs. IHRB established itself in Nairobi and established a good relationship with the Kenyan National Human Rights Commission. IHRB engaged well with business and VP member states, although it proved more difficult to regularly engage government and grassroots civil society. There was limited evidence that all parties were brought together in “multi-stakeholder convenings” (although in the second phase there are signs this is starting to happen). However, businesses are looking at their operational security policies and starting to use the Kenyan Oil and Gas Association (KOGA) to discuss approaches. IHRB also actively influenced legislative processes (e.g. the Petroleum Bill). Better project design and narrative reporting would have made performance easier to measure, but there was sufficient evidence to see foundations for longer-term impact.

Questions
Did the project achieve the project purpose?	Partly
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Yes
Was the project completed on time? (Y/N) / If not, why not?	N/A – this is a multi-year project that is continuing
Were the Project benefits sustained after project completion?	Yes

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green	x
Green

Guide to overall rating:
Green - project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Outputs and activities should be ambitious but capable of being delivered within the timescale of the project; if the issues are complex then consider a scoping or pilot project first, if time allows. / Ensure indicators/milestones are aligned to relevant outputs and activities, so that performance can be monitored and evaluated as easily as possible. / Projects that are politically complex and depend on engagement with a number of actors need careful planning and practical risk planning, but also close communication and some flexibility between the FCO and implementer. / Business and human rights projects with a multi-stakeholder approach require a careful balance not to be seen to be favouring one party over another (e.g. government, business, civil society), in particular when some actors may be easier to access than others. / In emerging markets in developing countries, business and human rights approaches need strategies to ensure actors not only have the political will and knowledge to implement the UNGPs and VPs, but they also have the resources to do so.

Recommendations for future projects
The project would no doubt benefit from being on a more stable financial footing. The FCO can play a role in encouraging the involvement of other donors (e.g. EU, DFID) who can provide multi-year funding. / The FCO and DFID continue to coordinate closely on their approach to human rights and development issues raised by Kenya’s emerging oil and gas sector. / Greater online transparency about the Nairobi Process, e.g. to share activity and learning in Kenya, East Africa and globally.