FCO SPF PROJECT EVALUATION

Project Details
Project Number	GB-3-131301
Project Title	Strengthening religious freedom in the Republic of Kazakhstan
Project Cost (total cost / cost to FCO if different)	£36,000
Project Start/End Dates	29 June 2012 – 6 March 2013
Programme	Human Rights and Democracy Programme
Country/Countries	Kazakhstan
Official Development Assistance Y/N	Y

Project Purpose (from proposal form)
To improve the legal framework for religious freedom in Kazakhstan and to increase public tolerance and awareness about religious freedom and its international standards.

Project Background / Context including what the project set out to achieve (150 words max)
After gaining independence, freedom of religion became well-established in Kazakhstan, and the number of religious denominations grew from 671 in 1990 to 4,427 in 2010. However, recent anti-terrorism legislation threatened to limit this freedom, e.g. by discriminating against smaller religious groups, restricting missionary activities, and resulting in law enforcement officials targeting vulnerable groups such as asylum seekers and members of Islamic groups. A lack of understanding of religious freedom standards, and a lack of information about different religious groups, has led to increased tensions in society, and is particularly problematic amongst state officials, judges, prosecutors, police and lawyers, as well as new members of Parliament. The project therefore aimed to increase public tolerance and awareness about religious freedoms by delivering training, and to improve the legal framework by providing government stakeholders with recommended amendments to bring legislation on religious freedom in line with international standards.

Evaluation summary (150 words max)
This was an extremely relevant project given the introduction of new legislation which threatened to lead to discrimination against religious minorities. It represented good value for money, delivering on all its stated outputs; 739 participants were trained and 15 recommendations for amendments to the legislation were developed. / The training courses received a great deal of praise from the authorities and other key stakeholders, and look likely to continue. However, it would have been helpful had the courses been more formally evaluated. In addition, although our interviews suggested that awareness of FoRB had increased amongst participants, we found no hard evidence of increased public tolerance. / There was also no evidence that the legal framework had improved, although the suggested amendments to the legislation could be taken off the shelf if the authorities decided on reform in future. Overall, the project would have been more effective with a narrower focus and greater measurability.

Questions
Did the project achieve the project purpose?	Not fully.
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Yes
Was the project completed on time? (Y/N) / If not, why not?	Yes
Were the Project benefits sustained after project completion?	Yes

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green	X
Green

Guide to overall rating:
Green - project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria
Top 5 Lessons learned
If a project involves developing legislative amendments, it is important for there to be a strategy for influencing the government to adopt them, and to be clear what the likelihood of success might be. / Training courses must have evaluation built into them; the provision of evaluation forms for participants at the end of each course is a fairly easy way of gathering some evidence on the effectiveness or otherwise of the training. / Training of trainers must be built into projects in order to ensure sustainability and there should be a clear plan to disseminate any knowledge or training. / Freedom of religion or belief is a sensitive issue in Kazakhstan, so cooperation with national authorities when arranging training courses etc. is important. / It is important to identify audiences carefully in advance, focusing on those who can make the most difference to achieving the project’s objectives. The implementers themselves identified in their lessons learned that the most important issue was proper implementation of the law by officials, including judges.

Recommendations for future projects
Careful thought must be given to indicators of success for training courses; “the number of participants trained” is not an indicator of success – thousands of participants could attend, but with no real-life outcome. To truly measure if a course has been successful, there would need to be evidence of a change in behaviour as result of the training. / Posts must agree the use of evaluation forms with future implementers who propose running training courses. / It is important for Post and the Programme Team to check whether the project purpose is within the implementer’s gift, and whether it matches up with the stated indicators of success. In this case, the purpose of improving the legal framework in Kazakhstan was overly ambitious and, in any case, did not align with the indicator of success, which was less ambitious: “a number of amendments are developed and presented to government stakeholders” (although this also raises the question of whether developing such amendments is an achievement if they are not then adopted). / In Kazakhstan, it will be important to continuing raising public awareness of the importance of freedom of religion or belief, de-linking it from terrorism.