FCO SPF PROJECT EVALUATION

Project Details
Project Number	GB-3-331301
Project Title	Promoting UN Guiding Principles (UNGPs) on business and human rights in Kazakhstan
Project Cost (total cost / cost to FCO if different)	£38,500
Project Start/End Dates	29 June 2012 to 28 February 2013
Programme	Human Rights and Democracy Programme
Country/Countries	Kazakhstan
Official Development Assistance Y/N	Yes

Project Purpose (from proposal form)
To promote implementation of the UNGPs on Business And Human Rights in Kazakhstan through public awareness campaign, research and advocacy.

Project Background / Context including what the project set out to achieve (150 words max)
In May 2011, workers from the Ozenmunaigas oil field in Zhanaozen, Western Kazakhstan, went on strike for unpaid danger money, higher wages and better working conditions. In December 2011, there were clashes between protesters and police; a number of workers were killed and many more injured. Clearly, ignoring the impact of business policies on human rights may lead to devastating circumstances. However, in Kazakhstan, there is currently little knowledge of the UNGPs, or how far businesses and legislation comply with them. / The project therefore aimed to: / increase awareness of the UNGPs amongst government, civil society and the general public; / draw up recommendations on implementation of the UNGPs; / assess compliance of Kazakhstan’s legislation and business practices with the UNGPs; and / draw up methodology for conducting human rights impact assessments in the business context.

Evaluation summary (150 words max)
This was an ambitious project on an area of great relevance to Kazakhstan. It was particularly successful in raising awareness of the UNGPs amongst parliamentarians and NGOs, and resulted in the production of high-quality research documents and recommendations that can be used by the government if they so choose. The project would have benefitted from identifying specific audiences for the public awareness campaign and from a more informed approach on engaging with the business community and trade unions. However, overall, this project was worth funding and represented good value for money; it was a pilot project on a new thematic area in a difficult operating environment, and the implementer and wider civil society now have a foundation on which to build.

Questions
Did the project achieve the project purpose?	Yes, largely.
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Yes
Was the project completed on time? (Y/N) / If not, why not?	Yes
Were the project benefits sustained after project completion?	Yes

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber
Amber	Green	X
Green

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Implementers need to consider carefully how best to engage the business community in the target country, e.g. in this instance, a working group/round table would probably have worked better than sending out questionnaires. Post and Programme Board will need to ensure that the implementer has a credible plan. / It is important to identify your audience prior to running a public awareness campaign, e.g. in this instance targeting students would probably have been most effective, and more measurable than citing the general public. / It is important to identify key sectors of the business community on which to focus efforts. / We should investigate how UK-based consultancy companies are helping businesses abroad implement corporate social responsibility (CSR). If they have built up local expertise, this could help UK companies with operations abroad develop good CSR/business and human policies in-country. / Where appropriate, to aid with sustainability and to increase reach, it could be helpful to convert the key points of the publications into a more digestible format, such as PowerPoint, that could be uploaded onto the internet.

Recommendations for future projects
Post should examine whether proposed initiatives can be packaged as part of existing government strategies in order to gain further host country support for the project. For example, the Kazakhstan government has a Strategy 2050 which aims to get Kazakhstan into the top 30 countries by 2050 – showing compliance with the UNGPs could be part of that. / Projects with “awareness raising” as an aim need to have a proper communications strategy in place, with audience analysis, measurable impacts, and a tighter focus.