FCO SPF PROJECT EVALUATION

Project Details
Project Number	GB-3-121301
Project Title	Elections & Democracy in Kazakhstan
Project Cost (total cost / cost to FCO if different)	£54,700
Project Start/End Dates	15 June 2012 – 31 March 2013
Programme	Human Rights & Democracy Programme
Country/Countries	Kazakhstan
Official Development Assistance Y/N	Yes

Project Purpose (from proposal form)
Introduction of necessary amendments to the election law of the Republic of Kazakhstan to bring the law into line with democratic standards through initiation of a wide public discussion.

Project Background / Context including what the project set out to achieve (150 words max)
Since 2005, amendments to election law in Kazakhstan have generally been drafted and adopted by Parliament without public consultation. These amendments have substantially limited the rights of voters, candidates and observers, creating opportunities for manipulation of election results, and significantly limiting transparency. Currently, civil society has no formal process through which to engage with government on election issues, and the media does not cover electoral issues between elections. The project therefore aimed to: / set up a Council of Observers, comprising representatives of local NGOs and members of civil society, in order to develop an agreed set of draft amendments to the current election law; / sign a Memorandum of Understanding (MOU) between civil society representatives and the authorities on an intention to work together on changes to the electoral legislation; and / engage with local media so that they cover election issues in the period between elections.

Evaluation summary (150 words max)
This was clearly an ambitious project, whose purpose of amending Kazakhstan’s electoral law was simply not within the implementer’s gift. It is also difficult to measure the breadth and impact of public discussion on these issues. However, it achieved a number of outcomes that could contribute to achieving that purpose, e.g. setting up a Council of Observers to work with the authorities on electoral issues, and agreeing an MOU between civil society representatives and the leading political party. It also brought civil society together to agree a set of draft amendments to the current election law, which could be taken off the shelf quickly and easily if the law were reformed at some future point. This helped increase the capacity of civil society with regards to electoral issues, and gave them greater impact. Overall, the project put in place building blocks for future reform so represented good value for money.

Questions
Did the project achieve the project purpose?	No, since this was too ambitious and outside of the implementer’s control.
Did the project come in on budget? (Y/N) / If no, why and what was the difference in cost?	Yes
Was the project completed on time? (Y/N) / If not, why not?	No, the project was extended due to a delay in the Implementer’s MOU negotiations with the government/parliament.
Were the Project benefits sustained after project completion?	Yes, in that the Council of Observers is still in place.

Overall Red / Amber / Green rating for project

Overall Rating for project (put X in relevant box)
Red
Red	Amber	X
Amber	Green
Green

Guide to overall rating:
Green- project performed well under each of the evaluation criteria: relevance, efficiency, effectiveness, sustainability, impact and management
Green/Amber – project performed well under most criteria and adequately in others
Amber/Red – project performed adequately under some criteria but poorly in others
Red – project performed poorly under most criteria

Top 5 Lessons learned
Measurability of impact must be built into the project, e.g. how can an implementer measure awareness-raising? / It is important to know what the right approach for a country is. In some countries an incremental approach may be more effective. Post and the implementer should ensure that they provide a suitable justification for a particular approach. / It is important to ensure that the project purpose is realistically achievable within the timeframe available. / Where implementers hope to engage the media, they must have a detailed and realistic media engagement and advocacy strategy. / Indicators of success and outputs must be something that is within the implementer’s control.

Recommendations for future projects
Post and Programme Team should challenge future project bids with regards to whether the project purpose is realistic and within the implementer’s control. / Elections are clearly a sensitive issue in Kazakhstan, and taking an incremental approach was probably right in this context. Improvements to election processes are likely to take a number of years, so it will be important for Post to maintain a longer-term relationship with the implementer (which appears to be well plugged into both civil society and government), and monitor the evolution of the MOU. / The Programme Team must bring forward its processes in order to allow projects to commence at the start of the financial year, in order to allow them sufficient time to deliver.