## Sheet2
Project Name	St Helena Airport
Department	DFID
IPA RAG rating / (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the IPA Annual Report)	Amber
Description / Aims	The project aims to establish sustainable air services to St Helena to promote economic development and increased financial self-sufficiency, leading eventually to graduation from UK budgetary support. This will be done through the construction of an airport and the introduction of scheduled air services. The project also includes support to the operation of the airport for a period of ten years and the construction of a wharf. The project will put in place the necessary legal, regulatory and monitoring framework, and includes a series of reforms to be implemented by the St Helena Government to open up the island to inward investment and increased tourism.
Departmental commentary on actions planned or taken on the IPA RAG rating.	The Delivery Confidence Assessment rating at the last Gateway Review (April 2014) was Amber/Green. However, the Senior Responsible Owner, with the agreement of the Project Board, reduced the rating to Amber in September 2015 in light of significant issues with the navigational equipment (now resolved) and delays to achieving readiness for airport certification. Action has been taken to allocate additional resources to address these issues.
Project - Start Date / (Latest approved start date)	15/03/2005
Project - End Date / (Latest approved end date)	31/08/2026
Departmental narrative on schedule, including any deviation from planned schedule (if necessary)	By end September 2015, construction of the airport was more than 90% complete, with all infrastructure at the airport expected to be ready for operations by end February 2016. Commissioning of permanent fuel facilities is unlikely until later in 2016, but contingency measures have been put in place to ensure the supply of aviation fuel. Currently the project is running to time for airport opening in mid 2016, and to budget, although significant challenges remain.
2015/16 Budget (£million)	£25.98
2015/16 Forecast (£million)	£25.56
Variance Budget / Forecast %age	Budget variance less than 5%.
Total budgeted whole life costs (£million) (including Non-government costs)	£445.17
Departmental Narrative on Budget / Forecast variance for 2015/16 where more than +/- 5%	Budget variance less than 5%.
Departmental Narrative on Budgeted Whole Life Costs	The whole life costs cover the 40 year design life of the airport. The costs are attributable to both the UK Government and St Helena Government; with UK Government commitment due to cease in 2026 after 10 years of airport operations. / Areas of expenditure included when calculating the whole-life cost are: planning, design, construction, operations, maintenance, asset renewal and/or disposal. / As the project is forecasting so far into the future (2046) there are high levels of uncertainty pertaining to some of the costs.