## Annex 2 App2 FAL WI
Appendix 2: Methodology for assessing penalty for project underperformance ( FAL Schedule 3a)
The methodology below will be used to run scenarios and assess appropriate financial penalty for an operation’s underperformance in delivery of outputs.
The methodology is flexible and allows :
1) Outputs to be varied according to what has been contracted / is most appropriate for specific Priority Axes and individual operations.
2) Weightings to be varied depending upon the level of underperformance :
a) Where underperformance is between 16% and 25% a weighting of 5% would normally be applied
b) Where underperformance is between 26% and 50% a weighting of 10% would normally be applied
c) Underperformance of over 50% would normally result in a weighting of at least 15%.
NB: Variance of up to15% would normally be dealt with via change request.
Underperformance weightings are suggested only and, with justification approved by the GDT senior management, can be reduced or increased as appropriate.
Identification of the outputs to be included and weightings to be applied is entirely at the discretion of the GDT team .
Methodology for calculating penalty for operation underperformance
Methodology
| OUTPUTS TO BE INCLUDED IN THE CALCULATION (Up to 4 outputs to be selected according to Priority Axis and those contracted for this operation) |  | OUTPUT 1 | OUTPUT 2 | OUTPUT 3 | OUTPUT 4 |  | EXAMPLE
|  |  | Output reference / ID | Output reference / ID | Output reference / ID | Output reference / ID
|  |  | Output description / Indicator | Output description / Indicator | Output description / Indicator | Output description / Indicator
Basic Facts | Total Project Value ( a) | £ value as per schedule 1 of FAL / details as per latest variation |  |  |  |  | 2000000
| Contracted Target ( b) |  | Number contracted as per schedule 3 of FAL | Number contracted as per schedule 3 of FAL | Number contracted as per schedule 3 of FAL | Number contracted as per schedule 3 of FAL | 150 | 200 | 600 | 600 | 1550
| Evidenced / actual achievement ( c) |  | Number actually achieved at time of calculation | Number actually achieved at time of calculation | Number actually achieved at time of calculation | Number actually achieved at time of calculation | 100 | 50 | 200 | 400 | 750
Calculated Variance | Variance (number) (d) |  | (b) - ( c) | (b) - ( c) | (b) - ( c) | (b) - ( c) | 50 | 150 | 400 | 200 | 800
| Variance (%) ( e) |  | (d) / (b) x 100 | (d) / (b) x 100 | (d) / (b) x 100 | (d) / (b) x 100 | 33.3333 | 75 | 66.6667 | 33.3333
Weighting | Up to 15% below target = normally deal with via project change process 16% and 25% below a weighting of 5% would normally be applied 26% and 50% below a weighting of 10% would normally be applied Over 50% below would normally result in a weighting of at least 15% (f) |  | identify weighting as appropriate ( see e) | identify weighting as appropriate ( see e) | identify weighting as appropriate ( see e) | identify weighting as appropriate ( see e) | 0.05 | 0.15 | 0.15 | 0.05
| Indicator Value (£) (g) |  | Weighting * total project value |  |  |  | 193548.3871 | 258064.5161 | 774193.5484 | 774193.5484 | 2000000
Penalty | Establish the value of the variance for each indicator as a proportion of the value of the operation.
| Underperformance value (£) (h) |  | (g) x (f) | (g) x (f) | (g) x (f) | (g) x (f) | 9677.4194 | 38709.6774 | 77419.3548 | 38709.6774
| Potential Reduction Value (£) (i) | sum all (h)s |  |  |  |  | 9677.4194
Note on C25: Author: Input value here

## Sheet1
Applying Methodology for Under Performance
Methodology
Key Value
|  |  | Enter output below | Enter output below | Enter output below | Enter output below
Basic Facts | Enter Project Value (ERDF or ESF value) | 2000000
| Enter contracted Target |  | 500 | 500 | 40 | 60
| Enter evidenced Achievement |  | 459 | 450 | 35 | 38
Calculated Variance | Shortfall/Access (No.) |  | 41 | 50 | 5 | 22
| Shortfall/Access (%) |  | 8.2 | 10 | 12.5 | 36.6667
Value of each indicator as a proportion of the value of the project. Assume that results are more important than outputs.
| Enter weighting to be applied |  | 5% | 10% | 5% | 10%
| Indicator Value (£) |  | 100000 | 200000 | 100000 | 200000
Establish the value of the variance for each indicator
| Shortfall/Access Value (£) |  | 8200 | 20000 | 12500 | 73333.3333
| Potential Reduction Value (£) | 114033.3333