ODUG Action Log – 12th March 2013

All actions for next meeting unless otherwise stated

Secretariat
Circulate minutes and actions from eleventh meeting	TJ	Completed
Publish note and actions from eleventh meeting on data.gov.uk	TJ	New
Send BIS DSB team electronic invites to all scheduled ODUG meetings	TJ	New

Collaboration Space
Advise ODUG members when they need to log into the collaboration space to prioritise new tranches of data requests	TJ/JT	Ongoing

ODUG Benefits Cases
General
Recast current Benefits Cases into the newly agreed format	All	New

National Address Dataset – Lead HS/BB
Write-up background assumptions to numbers in National Address Dataset Benefits paper	BB	Completed
Draft ODUG response to Ofcom consultation on PAF licensing – deadline 21 March 2013	BB	Completed
Incorporate Group comments to draft response to Ofcom consultation	BB	Completed
Survey of ~20 SMEs on use of National Address Data and PAF	BB	Carried forward
Provide feedback to Group on progress of DSB implementation report – waiting on draft from BIS	HS	Carried forward

Historic Price Paid Information – Lead SH
Identify further cases studies to support Historic Price Paid Information benefits case	SH	Carried forward
Set up meeting with Land Registry	EP	New

Historic Weather Observations – Lead JC
Contact Met data-user SMEs for input to benefits case. TJ to provide some new contacts	TJ/JC	Carried forward
Set up meeting with Met Office, including other potential users of Met Office Historic Weather Observations	TJ/JC	New

VAT Register – Lead PM
Strengthen and expand evidence base for benefits case	PM	New
Paper to Transparency Board	HS	New

OS Derived Data Licensing Restrictions – with River Networks and Rights of Way - Lead GS
Meet with the Environment Agency about flooding data	CR/JT	Carried forward
Set up meeting with OS	HS	New

Cadastral land polygons – Lead BB
Develop benefits case	BB	Carried forward

DVLA Bulk data – Lead PM
Nominate lead ODUG member for this benefits case	TJ	Completed
Develop benefits case	PM	New

Local Government data – Lead GS
Nominate lead ODUG member for this benefits case	TJ	Completed
Develop benefits case	GS/AM/JT	New

Charity Commission Register- Lead AM
Nominate lead ODUG member for this benefits case	TJ	Completed
Develop benefits case	AM	New

Energy Performance Certificates – Lead PM
Nominate lead ODUG member for this benefits case	TJ	Completed
Develop benefits case	PM	New

Open Data Licensing – GS/JTe
ODUG and ODI to deliver joint paper on Open Data Licensing Issues	JTe/GS	Carried forward

Data.gov.uk Workstream
Data.gov.uk to provide number of visits for each ODUG benefits case	RA	Carried forward
Coordinate use and application of statuses externally on data.go.uk and internally on collaboration space	TJ/JT	Completed
Add display of progress on Open Data Strategy commitments to reporting tool	JT	Carried forward
Review privacy implications for the new reporting tool	JT	Completed
Feedback on final version of proposed dataset reporting tool (when advised ready to review)	All	Completed
Work with data.gov.uk team on feasibility assessment of posting reporting tool on the data.gov.uk site	JT/ TJ/ RA	Completed
Propose comms plan for launching reporting tool	JT/TJ	Completed

Include supportive data requests from legacy list into current work	CR/JT	Carried forward
ODUG to write to depts. about progress on data publication commitments in respective the Pipeline and their Open Data Strategy Commitments	TJ/JT	Carried forward
Review of all legacy requests to make sure those appropriate to use for support of current ODUG benefits cases are taken into account	SH	New

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	JT	Carried forward
ODUG Branding	DL/PM	Carried forward
Draw up and share key points to make and slides on ODUG	DL	Carried forward
ODUG schedule of comms events and stakeholder engagement plan	DL/EP	Carried forward
Draft ODUG 6-month review	DL/TJ	New
Develop plan for an ODUG event	DL/EP	Carried forward

KPIs and Risk
Review for next meeting	TJ/HS	Ongoing

Other
Publish minutes of Code of Practise Workshop on data.gov	AM/TJ	Completed