ODUG Action Log – 24 October 2012

All actions for next meeting unless otherwise stated

Secretariat
Circulate membership of each of the Transparency Sector Boards	Carried forward
Circulate minutes and actions from sixth meeting	Complete
Publish note and actions from sixth meeting on data.gov.uk	Complete

Collaboration Space
Finalise visualisation and voting ability for .csv extract of data request form
Amend declaration of interest paragraph, re-circulate and amend submitted forms. Publish forms as part of member profiles on DGU	Carried forward
Submit easy-to-read-and-understand case studies to collaboration space

Business Case process
Draft ODUG strategy paper	Carried forward
Outline two-step approach to developing data requests to business case / By Tuesday 30 October

Data Requests and data.gov.uk Workstream
Refine flow chart for filtering of data requests process	Complete
Share plans for ODUG landing page on DGU and timings	Complete

Open Data Roadmap Workstreams (to be discussed at next ODUG meeting when new data requests available from data.gov.uk submissions)
ToR for this workstream
Work with OD community to define a set of principles for the release of open data
Develop respective strategic and business cases for allocated data requests

Metrics and Costs of Data Workstream
ToR for workstream	Carried forward
Request draft Deloitte paper

Business Models and Barriers
Consider existing signposting to data already released	Carried forward

Licensing
First draft of paper to set out licensing issues related to the use of open data for group discussion

KPIs and Risk
Review for next meeting

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	Carried forward
ODUG Branding	Carried forward
Draw up and share key slides on ODUG	Carried forward
List of events ODUG members are attending and list of relevant events
ODUG schedule of comms events	Carried forward
Stakeholder engagement plan
Key points to make about ODUG
Press pack for publication of Addressing paper
Draft letter to Smart Cities competition	Complete

Addressing Workstream
ODUG response to PAF Advisory Board consultation – due 31 October / Members to feed comments in time for 31 October submission	Complete