ODUG Action Log – 25 September 2012
All actions for next meeting unless otherwise stated

Secretariat
Circulate membership of each of the Transparency Sector Boards	Carried forward
Circulate minutes and actions from fifth meeting
Publish note and actions from fifth meeting on data.gov.uk

Collaboration Space

Business Case process
Draft ODUG strategy paper	Carried forward

Data Requests and data.gov.uk Workstream
Produce .csv file	Carried forward
Formalise arrangement for monitoring and responding to incoming requests

Open Data Roadmap Workstreams (to be discussed at next ODUG meeting when new data requests available from data.gov.uk submissions)
ToR for this workstream
Work with OD community to define a set of principles for the release of open data [this action may fit in Business Case workstream]
Consistent use of benefits categories (growth to be used instead of economic)

Metrics and Costs of Data Workstream
ToR for workstream	Carried forward

Business Models and Barriers
Consider existing signposting to data already released

Licensing
First draft of paper to set out licensing issues related to the use of open data for group discussion

KPIs and Risk
Review for next meeting

Communications Workstream
Set up facility for sentiment monitoring for ODUG and provide a baseline assessment	Carried forward
ODUG Branding	Carried forward
Draw up and share key slides on ODUG	Carried forward
List of events ODUG members are attending and list of relevant events
ODUG schedule of comms events	Carried forward
Stakeholder engagement plan

Addressing Workstream
ODUG response to PAF Advisory Board consultation – due 31 October