Open Data User Group

Action Log – 14th August 2012

Secretariat

Circulate membership of each of the Transparency Sector Boards
Circulate 54 case studies on data.gov.uk
Publish note and actions from second ODUG meeting online
Publish online list of ODUG members’ interests. A proforma will be circulated
Standard format for ODUG papers – word doc with simple header/footer and numbering format

Elevator pitch and data.gov.uk

Circulate a second version of the draft elevator pitch by the end of the week to include themes and other members to comment
Filter data.gov.uk list of datasets and circulate to the group
Take preparations for the metrics workstream forward
Circulate process diagram for comment
Meet early next week to set out the requirements for elevator pitch submission and other functionality on DGU

Pipeline

Members to come back to highlight where there is a high level of interest in these dataset on behalf of the community they represented
Meet with CO Transparency Team to clarify latest dataset status
Explore opportunities to get metrics off data.gov.uk e.g. on number of data downloads

National Addressing

Draft position statement on National Addressing as Core Data
Review draft position statement

Licensing

Take licensing work stream forward

Knowledge Management

Circulate links to Departments Open Data Strategies on data.gov.uk
Set up the collaboration space. Different group members will curate different areas of the collaboration space. A guidance note will be provided to the group
Define themes for intelligence sharing on ODUG collaborative platform
Circulate drafts of Cabinet Office user journeys to the group
Produce first draft of document setting out barriers to the use of open data and get 6 business models from Andrew Stott

KPIs/Risks

Combine KPI and Risk Register and pass to the Chair for comment prior to the next meeting

Communications

Set up facility for sentiment monitoring for ODUG and provide a baselines assessment
Draw up and share key slides on ODUG
Include conference/presentation activities as a knowledge base on the collaboration platform
Come to next meeting with details of process each member will use to engage with their open data community sector.
Circulate list of handles for Twitter and email addresses and create Twitter list for ODUG members
Get some branding designed –