## Title Sheet
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Quality and price questions, weightings and scoring criteria for framework procurements. Questions are mandatory for competitive procurements. Framework User to select questions for Direct Award or Future School procurements.
EC Harris LLP

## Version Control
Version History
Date | Editor | Version | Status | Comment
2017-11-13 | David Whitehead | v1 | FINAL
2018-03-22 | David Whitehead | v2 | FINAL | Document amended for use with Invitation to Submit Proposal (ISP) in addition to Invitation to Tender (ITT). Title amended accordingly. Addition of quality question 3.2 Addition of 500 words to quality question 3.1 Addition of 500 words to quality question 4.2 Amendment to pricing requirement 7.1
EC Harris LLP

## Sub-Criteria
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Criteria | Sub-Criteria |  | Weighting
Quality | 1 | Overall Approach | 15%
| 2 | Procurement and Supply Chain Management | 10%
| 3 | Design Management | 15%
| 4 | Cost and Risk Management | 15%
| 5 | Construction Management | 5%
Price | 6 | Pricing Proposal | 20%
| 7 | Pricing Methodology | 20%
| Total |  | 100%

## Scoring Criteria
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Evaluation of Quality Questions and Pricing Methodology | Score
No response provided or is significantly deficient as to what has been asked | 0
Inadequate detail provided or proposals are unsatisfactory, or response does not directly address the question | 1
Response only partly answers the question and the detail missing is significant and/or a significant part of the proposals are unsatisfactory | 2
Response substantially answers the question but lacks some detail and/or part of the proposals are unsatisfactory | 3
Response substantially answers all elements of the question. Any missing or unsatisfactory details are minor | 4
Response to all elements of the question is satisfactory and in sufficient detail | 5
Evaluation of Pricing Proposal
Score range: 0 to 20 On-budget bid = 10 marks +/- marks determined by % below/above budget x multiplier of 10. = +/- 1 mark for every 1% below/above budget until maximum score of 20 and minimum score of zero. Score calcuated to two decimal places.

## Quality Questions
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Quality Sub-Criteria | Sub-Criteria Weighting | Question No. | Question | Question Weighting | Invitation to Tender | Invitation to Submit Proposal
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words | 5% | Mandatory Question | Please Select
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words | 10% | Mandatory Question | Please Select
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. | 10% | Mandatory Question | Please Select
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) | 10% | Mandatory Question | Please Select
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words | 5% | Mandatory Question | Please Select
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words | 7.5% | Mandatory Question | Please Select
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words | 7.5% | Mandatory Question | Please Select
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words | 5% | Mandatory Question | Please Select
Total | 60% |  |  | 60%

## Pricing Requirements
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Price Sub-criteria | Sub-Criteria Weighting | Question No. | Question | Question Weighting | Invitation to Tender | Invitation to Submit Proposal
Pricing Proposal | 20% | 6.1 | Please provide a realistic pricing proposal for this scheme in the form of a completed pricing schedule. The pricing schedule is provided at ITT Appendix J. | 20% | Mandatory Question | Mandatory Question
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data | 20% | Mandatory Question | Mandatory Question
Total | 40% |  |  | 40%

## Summary
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
[ ] Procurement
Criteria | Sub-Criteria | Weighted Scores
|  | Bidder 1 | Bidder 2 | Bidder 3 | Bidder 4 | Bidder 5 | Bidder 6 | Bidder 7
|  | [BIDDER NAME1] | [BIDDER NAME2] | [BIDDER NAME3] | [BIDDER NAME4] | [BIDDER NAME5] | [BIDDER NAME6] | [BIDDER NAME7]
Quality (60%) | Overall Approach | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Procurement and Supply Chain Management | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Design Management | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cost and Risk Management | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Construction Management | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Total Quality Score | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Price (40%) | Pricing Proposal | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Pricing Methodology | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Total Price Score | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Assessed Score |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## Evaluation Scorecard - Bidder 1
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME1]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Evaluation Scorecard - Bidder 2
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME2]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Evaluation Scorecard - Bidder 3
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME3]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Evaluation Scorecard - Bidder 4
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME4]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Evaluation Scorecard - Bidder 5
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME5]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Evaluation Scorecard - Bidder 6
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME6]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Evaluation Scorecard - Bidder 7
ESFA Construction Framework
ITT/ISP Appendix K - Evaluation Matrix (Medium/Low Bands)
Bidder: |  | [BIDDER NAME7]
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Evaluator's Comments | Score | Question Weighting | Weighted Score
Overall Approach | 15% | 1.1 | Please provide a realistic pre-construction programme with commentary to demonstrate when key milestones will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | 1.2 | Please describe who you understand to be the key stakeholders for the scheme and how you will engage with and manage those stakeholders in order to ensure an affordable and deliverable solution Maximum of 1,000 words |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Procurement and Supply Chain Management | 10% | 2.1 | Please demonstrate your team and supply chain capability and capacity to deliver this specific scheme. Including: a) Describing how you will organise and structure your team for the scheme, including key roles and responsibilities; b) Providing project related CVs for a maximum of eight key members of your team, which demonstrate the individuals’ relevant experience for this scheme. The CVs provided should include bid manager, lead architect and lead environmental engineering consultant; c) Where applicable, describing how you will select your team and supply chain for the future schools in the batch ensure the efficient delivery of those schemes Maximum of 1,000 words (1,500 if section c applies) plus an organisation chart and CVs no longer than 1 page of A4 each. The organisation chart must not include details of responsibilities, which should be included in the 1,000 words of narrative. |  |  | 10% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Design Management | 15% | 3.1 | Please describe how you will manage the design process and deploy your team to ensure quality and cost-efficient proposals for this scheme. Please address the following stages in your answer: a) Design Development Stage b) Submission of a Planning Application c) Preparation and submission of Contractor’s Proposals d) Contract finalisation Your response should include a schedule of meetings, identifying who is required at each e) Where applicable, please describe how you will manage the engagement processes for the future schools in the batch to ensure the efficient delivery of those schemes Maximum of 2,000 words (2,500 where section e applies) |  |  | 10% | 0%
|  | 3.2 | Please describe how will you ensure the effective delivery and integration of ICT infrastructure requirements and FF&E (including legacy assets and equipment) in the design solution for this scheme Maximum of 1,000 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Cost and Risk Management | 15% | 4.1 | Please describe what you consider to be the key challenges and risks specifically associated with the delivery of this scheme and how you will manage them. Maximum of 1,000 words |  |  | 7.5% | 0%
|  | 4.2 | Please describe your specific approach to the identification and management of price risk for the project to ensure the scheme is developed within your proposed cost envelope. Where appropriate, your response should include a list of any additional surveys to be undertaken, their timing and rationale. Maximum of 1,500 words |  |  | 7.5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Construction Management | 5% | 5.1 | Please provide a realistic construction programme and commentary to demonstrate the construction phasing strategy and when key dates will be met. Any deviations from the dates issued by the Framework User should be justified in the commentary. Maximum of 1 x A3 programme and 750 words |  |  | 5% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Quality Total | 60% | Total Quality Score |  |  |  |  | 0%
Sub-criteria | Sub-Criteria Weighting | Question Number | Total Budget for Contractor Responsibilities | Bidder's Proposed Sum | % Difference | Question Weighting | Weighted Score
Pricing Proposal | 20% | 6.1 |  |  | #DIV/0! | 20% | #DIV/0!
|  | Total for Sub-Criterion |  |  |  |  | #DIV/0!
Sub-criteria | Sub-Criteria Weighting | Question Number | Question | Moderated Comments | Moderated Score | Question Weighting | Weighted Score
Pricing Methodology | 20% | 7.1 | Please provide a commentary on your pricing proposal demonstrating how the project/site information provided and your school building expertise have been applied to produce a figure that is realistic and achievable. Your response should include: a) Reference to the base build; preliminaries; externals; abnormals; PCSA value and milestone payments; b) Justification of any significant differences from the pricing provided in your framework bid; b) Confirmation that the full scope of works is included Maximum of 1,500 words plus any supporting quantitative data |  |  | 20% | 0%
|  | Total for Sub-Criterion |  |  |  |  | 0%
Price Total | 40% | Total Price Score |  |  |  |  | #DIV/0!
TOTAL SCORE | [6 empty] | #DIV/0!
Notes:
6.1 Calculation
% Difference x Multiplier of 10 | #DIV/0!
x 10 marks | #DIV/0!
Score | #DIV/0!
Adjusted Score | #DIV/0!
EC Harris LLP

## Admin
Please Select
Response Required
Response Not Required